## MAIN PROCESS
TRADE | Task | Status | Sub | Start week | End week | Obs | Actual Date | End Date | Negotiated | Ball Park | Budget | Cost | WO | 38
GENERAL CONDITIONS | Surveyor Documents |  | PLANING | 38
GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work |  | PLANING | 38
GENERAL CONDITIONS | Permits |  | PLANING | 38
GENERAL CONDITIONS | Post Permits |  | PROJECT MANAGER | 39
GENERAL CONDITIONS | Place Dumpsters |  | PROJECT MANAGER | 39
GENERAL CONDITIONS | DEMO OF STRUCTURE |  | PROJECT MANAGER | 39
SITE WORK | Tree Removal |  | PROJECT MANAGER | 39
SITE WORK | Grading and soil leveling |  | PROJECT MANAGER | 39
SITE WORK | Filling Dirt |  | PROJECT MANAGER | 39
FOUNDATION | Foundation Form and Excavation |  | PROJECT MANAGER | 40
FOUNDATION | Concrete Piers |  | PROJECT MANAGER | 40
PLUMBING | Inground Plumbing |  | PROJECT MANAGER | 41
FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar |  | PROJECT MANAGER | 42 |  | INSPECTION | INSPECTION
FOUNDATION | Concrete Pour |  | PROJECT MANAGER | 43 |  | we wait 3 weeks after
GENERAL CONDITIONS | Demo Preparation |  | PROJECT MANAGER | 44 |  | For remodeling
FRAMING | Framing |  | PROJECT MANAGER | 44 |  | for remodeling is week 1
EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) |  | PROJECT MANAGER | 44 |  | same week as framing
DOORS AND WINDOWS | Exterior Windows and Doors |  | PROJECT MANAGER | 44 |  | same week as framing
EXTERIOR SHEATING | External Water Proofing |  | PROJECT MANAGER | 44 |  | same week as framing | INSPECTION
SIDING / BRICK | Siding or bricl |  | PROJECT MANAGER | 45 |  | next week after framing
ROOFING | Roofing |  | PROJECT MANAGER | 45 |  | next week after framing
PLUMBING | Plumbing Rough In and Top out |  | PROJECT MANAGER | 45 |  | it can be the same week as roofing | INSPECTION
ELECTRICAL | Electrical Rough In |  | PROJECT MANAGER | 45 |  | it can be the same week as roofing | INSPECTION
MECHANICAL | Mechanic (HVAC) Rough in |  | PROJECT MANAGER | 45 |  | it can be the same week as roofing | INSPECTION
ELECTRICAL | Communications and Data Rough In |  | PROJECT MANAGER | 45 |  | it can be the same week as roofing
OTHERS | Things that goes inside the walls |  | PROJECT MANAGER | 45 |  | it can be the same week as roofing
INSULATION | Wall Insulation |  | PROJECT MANAGER | 45 |  | one week after rought ins | INSPECTION
INSULATION | Roof Insulation (New Houses |  | PROJECT MANAGER | 45 |  | At anymoment after rought ins | INSPECTION
DRYWALL | Sheet Rock |  | PROJECT MANAGER | 46 |  | one week after the insulaiton inspection
DRYWALL | Hardybacker Installation |  | PROJECT MANAGER | 46 |  | same as sheet rock
DRYWALL | Wet Areas Water Proofing Redguard |  | PROJECT MANAGER | 46 |  | same as sheet rock
DRYWALL | Tape Bet and Texture |  | PROJECT MANAGER | 46 |  | same as sheet rock
TILES | Tiles |  | PROJECT MANAGER | 47 |  | one week after sheetrock
DOORS AND WINDOWS | Interior Doors Installation |  | PROJECT MANAGER | 47 |  | one week after sheetrock
CARPENTRY | Finish Carpentry |  | PROJECT MANAGER | 47 |  | one week after sheetrock
PAINT | Paint |  | PROJECT MANAGER | 48 |  | one week after interior door installation
PAINT | Painting of Walls |  | PROJECT MANAGER | 48 |  | Same week as paint prep
PAINT | Painting of Ceiling |  | PROJECT MANAGER | 48 |  | Same week as paint prep
FLOORING | Leveling and floating of floors |  | PROJECT MANAGER | 48 |  | One week after paiting
FLOORING | Floor Installation |  | PROJECT MANAGER | 48 |  | Same week as floor installation
FLOORING | Moldures and Baseboard Installation |  | PROJECT MANAGER | 49 |  | One wee after floor installation
FLOORING | Trim, baseboards and Mantel Painting |  | PROJECT MANAGER | 50 |  | One week after moldures and baseboard installation
CABINETS | Kitchen Cabinets Fabrication |  | PROJECT MANAGER | 46 |  | At any moment after drywall
CABINETS | Vanities Cabinets Fabrication |  | PROJECT MANAGER | 46 |  | At any moment after drywall
CABINETS | Kitchen Cabinets Installation |  | PROJECT MANAGER | 12 |  | After Floor Installation
CABINETS | Vanities Installation |  | PROJECT MANAGER | 50 |  | After Floor Installation
COUNTERTOP | Countertop Intallation |  | PROJECT MANAGER | 51 |  | After Kitcen and Vanities Installation
TILES | Tiles Backsplash |  | PROJECT MANAGER | 52 |  | After COuntertops Installation
OTHERS | Smoke Detectors Installation |  | PROJECT MANAGER | 52 |  | After COuntertops Installation
ROOFING | Gutters |  | PROJECT MANAGER | 52 |  | After COuntertops Installation
GLASS | Shower Glass, Mirrors and other accesories |  | PROJECT MANAGER | 52 |  | After COuntertops Installation
PLUMBING | Fixture Installation |  | PROJECT MANAGER | 52 |  | After COuntertops Installation
ELECTRICAL | Accesories Installation |  | PROJECT MANAGER | #REF! |  | After COuntertops Installation
OTHERS | Finishes and Touch ups |  | PROJECT MANAGER | #REF! |  | After all accesories Installed
OTHERS | DELIVERY |  | PROJECT MANAGER | #REF! |  | One week after

## SPECIFICATIONS
ELECTRICAL | OVEN | 60 AMP | 60/3
ELECTRICAL | DISHWASHER | 20AMP | 2023-12-02
ELECTRICAL | COOKTOP | 60 AMP | 60/3
ELECTRICAL | COOKTOP | 40 AMP | 2023-10-03
ELECTRICAL | COOKTOP | 50AMP | 2023-08-03
ELECTRICAL | REFRIGERATOR | 20AMP | 2023-12-02

## Dave barron
CATEGORY | Process Name | SubProcess Name | DEPARTMENT | WEEK | COMMENTS | INSPECTION | START WEEK | 38
GENERAL CONDITIONS | Surveyor Documents |  | PLANING | 38
GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work |  | PLANING | 38
GENERAL CONDITIONS | Permits |  | PLANING | 38
GENERAL CONDITIONS | Post Permits |  | PROJECT MANAGER | 39
GENERAL CONDITIONS | Place Dumpsters |  | PROJECT MANAGER | 39
GENERAL CONDITIONS | DEMO OF STRUCTURE |  | PROJECT MANAGER | 39
SITE WORK | Tree Removal |  | PROJECT MANAGER | 39
SITE WORK | Grading and soil leveling |  | PROJECT MANAGER | 39
SITE WORK | Filling Dirt |  | PROJECT MANAGER | 39
FOUNDATION | Foundation Form and Excavation |  | PROJECT MANAGER | 40
FOUNDATION | Concrete Piers |  | PROJECT MANAGER | 40
FOUNDATION | Inground Plumbing |  | PROJECT MANAGER | 41
FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar |  | PROJECT MANAGER | 42 | INSPECTION | INSPECTION
FOUNDATION | Concrete Pour |  | PROJECT MANAGER | 43 | we wait 3 weeks after
GENERAL CONDITIONS | Demo Preparation |  | PROJECT MANAGER | 44 | For remodeling
FRAMING | Framing |  | PROJECT MANAGER | 44 | for remodeling is week 1
EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) |  | PROJECT MANAGER | 44 | same week as framing
DOORS AND WINDOWS | Exterior Windows and Doors |  | PROJECT MANAGER | 44 | same week as framing
EXTERIOR SHEATING | External Water Proofing |  | PROJECT MANAGER | 44 | same week as framing | INSPECTION
ROOFING | Roofing |  | PROJECT MANAGER | 45 | next week after framing
PLUMBING | Plumbing Rough In |  | PROJECT MANAGER | 45 | it can be the same week as roofing | INSPECTION
ELECTRICAL | Electrical Rough In |  | PROJECT MANAGER | 45 |  | INSPECTION
MECHANICAL | Mechanic (HVAC) Rough in |  | PROJECT MANAGER | 45 |  | INSPECTION
ELECTRICAL | Communications and Data Rough In |  | PROJECT MANAGER | 45
OTHERS | Things that goes inside the walls |  | PROJECT MANAGER | 45
INSULATION | Wall Insulation |  | PROJECT MANAGER | 45 |  | INSPECTION
INSULATION | Roof Insulation (New Houses |  | PROJECT MANAGER | 45 |  | INSPECTION
DRYWALL | Sheet Rock |  | PROJECT MANAGER | 46 | one week after the insulaiton inspection
DRYWALL | Hardybacker Installation |  | PROJECT MANAGER | 46 | same as sheet rock
DRYWALL | Wet Areas Water Proofing Redguard |  | PROJECT MANAGER | 46 | same as sheet rock
DRYWALL | Tape Bet and Texture |  | PROJECT MANAGER | 46 | same as sheet rock
TILES | Tiles |  | PROJECT MANAGER | 47 | one week after sheetrock
DOORS AND WINDOWS | Interior Doors Installation |  | PROJECT MANAGER | 47 | one week after sheetrock
CARPENTRY | Finish Carpentry |  | PROJECT MANAGER | 47 | one week after sheetrock
PAINT | Paint Prep |  | PROJECT MANAGER | 48 | one week after interior door installation
PAINT | Painting of Walls |  | PROJECT MANAGER | 48 | Same week as paint prep
PAINT | Painting of Ceiling |  | PROJECT MANAGER | 48 | Same week as paint prep
FLOORING | Leveling and floating of floors |  | PROJECT MANAGER | 48 | One week after paiting
FLOORING | Floor Installation |  | PROJECT MANAGER | 48 | Same week as floor installation
FLOORING | Moldures and Baseboard Installation |  | PROJECT MANAGER | 49 | One wee after floor installation
PAINT | Trim, baseboards and Mantel Painting |  | PROJECT MANAGER | 50 | One week after moldures and baseboard installation
CABINETS | Kitchen Cabinets Installation |  | PROJECT MANAGER | 12 | After Floor Installation
CABINETS | Vanities Installation |  | PROJECT MANAGER | 50 | After Floor Installation
COUNTERTOP | Countertop Intallation |  | PROJECT MANAGER | 51 | After Kitcen and Vanities Installation
OTHERS | Smoke Detectors Installation |  | PROJECT MANAGER | 52 | After COuntertops Installation
PLUMBING | Fixture Installation |  | PROJECT MANAGER | 52 | After COuntertops Installation
ELECTRICAL | Electrodomestic Installation |  | PROJECT MANAGER | 52 | After COuntertops Installation
ELECTRICAL | Accesories Installation |  | PROJECT MANAGER | 52 | After COuntertops Installation
OTHERS | Finishes and Touch ups |  | PROJECT MANAGER | 53 | After all accesories Installed
OTHERS | DELIVERY |  | PROJECT MANAGER | 54 | One week after
Daniel Powell | concreto |  |  |  | 39
Daniel Powell | Framing |  |  |  | 42
Daniel Powell | exterior sheeting |  |  |  | 43
Daniel Powell | door windows |  |  |  | 43
Daniel Powell | Roofing |  |  |  | 43
Daniel Powell | Gutters |  |  |  | 45
Daniel Powell | Bricks |  |  |  | 43
Daniel Powell | electrical rough in |  |  |  | 43
Daniel Powell | plumbing rough in and top out |  |  |  | 43
Daniel Powell | hvac rough in |  |  |  | 43
Daniel Powell | Insulation |  |  |  | 45
Daniel Powell | Sheetrock tape and bet texture |  |  |  | 46
Daniel Powell | Paint |  |  |  | 46
Daniel Powell | Tiles |  |  |  | 46
Daniel Powell | Finishing electrical |  |  |  | 47
Daniel Powell | Finish plumbing |  |  |  | 47
Daniel Powell | Other touch ups |  |  |  | 48

## TASK SCHEDULED
WO | CUSTOMER NAME | CUSTOMER ADDRESS | CODE | DESCRIPTION | UNIT / WEEK | QUANTITY | TYPE | BUDGET
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | Inground Plumbing | WEEK | 39 | TASK
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | Plumbing Rough In & Top out | WEEK | 46 | TASK
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | Fixture Installation | WEEK | 51 | TASK
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | LABOR PER SERVICE - ADDITION | UNIT | 3 | LABOR | 1125
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | LABOR PER SERVICE -REMOVE AND REPLACE | UNIT | 6 | LABOR | 540
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | LABOR PER SERVICE - INSTALL | UNIT | 1 | LABOR | 60
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | BUILD UP SHOWER BASE | SQ FT | 28 | LABOR | 770
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | SHOWER FAUCET - BG | UNIT | 1 | MATERIAL | 275
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | BATHROOM FAUCET - BG | UNIT | 2 | MATERIAL | 250
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | SINK - BG | UNIT | 1 | MATERIAL | 200
PALO001 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PLUMBING | ROMAN FAUCET - BG | UNIT | 1 | MATERIAL | 100
PALO0011 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PAINT | LABOR - NEW CONSTRUCTION (BUILDING SQ FT) | SQ FT | 625 ' | LABOR | 1312.5
PALO0011 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PAINT | LABOR - TRIM PAINT | LNFT | 92 ' | LABOR | 66.24
PALO0011 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PAINT | LABOR - FRONT DOOR PAINT | EA |  | LABOR | 0
PALO0011 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PAINT | MATERIAL - WALL PAINT | UNIT | 2 ' | MATERIAL | 210
PALO0011 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PAINT | MATERIAL - CEILING PAINT | UNIT | 1 ' | MATERIAL | 105
PALO0011 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PAINT | MATERIAL - TRIM PAINT | UNIT | 1 ' | MATERIAL | 51
PALO0011 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PAINT | OTHER MATERIALS | GLOBAL | 1 ' | MATERIAL | 348
PALO002 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FOUNDATION | Foundation Form and Excavation | WEEK | 38 | TASK
PALO002 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FOUNDATION | Concrete Piers | WEEK | 39 | TASK
PALO002 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar | WEEK | 40 | TASK
PALO002 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FOUNDATION | Concrete Pour | WEEK | 41 | TASK
PALO002 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FOUNDATION TOTAL | FORM WORK | SQ FT | 204 | ALL INCLUDED | 128.52
PALO002 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FOUNDATION TOTAL | PIERS | UNIT | 12 | ALL INCLUDED | 2688
PALO002 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FOUNDATION TOTAL | GRADE BEAMS / FOOTINGS | LF | 99 | ALL INCLUDED | 519.75
PALO002 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FOUNDATION TOTAL | CONCRETE SLAB | SQ FT | 204 | ALL INCLUDED | 1356.6
PALO003 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ELECTRICAL | Electrical Rough In | WEEK | 46 | TASK
PALO003 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ELECTRICAL | HVAC ROugh In | WEEK | 46 | TASK
PALO003 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ELECTRICAL | Accesories and Fixture Installation | WEEK | 51 | TASK
PALO003 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ELECTRICAL | LABOR - ADDITION - WIRING | SQ FT | 204 ' | LABOR | 1020
PALO003 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ELECTRICAL | LED RECESSED LIGHT | UNIT | 15 | MATERIAL | 187.5
PALO003 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ELECTRICAL | DECORATIVE LIGHT FIXTURE | UNIT | 2 | MATERIAL | 50
PALO003 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ELECTRICAL | CEILING EXHAUST FAN, REF. M.E.P | UNIT | 2 | MATERIAL | 350
PALO003 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ELECTRICAL | ELECTRICAL - MINOR | UNIT | 11 | LABOR | 1375
PALO003 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ELECTRICAL | EXAUST FAN | UNIT | 1 | MATERIAL | 30
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FRAMING | Framing | WEEK | 43 | TASK
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) | WEEK | 44 | TASK
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DOORS AND WINDOWS | Exterior Windows and Doors | WEEK | 44 | TASK
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | EXTERIOR SHEATING | External Water Proofing | WEEK | 44 | TASK
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FRAMING | NEW CONSTRUCTION FRAMING - LABOR | SF | 308 | LABOR | 1101.1
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FRAMING | NEW CONSTRUCTION FRAMING - MATERIAL | SF | 338 | LABOR | 2230.8
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FRAMING | ADDITION REFRAME - STRUCTURAL - LABOR | SF | 204 | LABOR | 1065.9
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FRAMING | ADDITION REFRAME - STRUCTURAL - MATERIAL | SF | 225 | LABOR | 1485
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | EXTERIOR SHEATING | LABOR (SURFACE SQ FT) - SHEATING | SQ FT | 232 | LABOR | 208.8
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | EXTERIOR SHEATING | ZIP SYSTEM 4FT X 8 FT - ROOF SHEATING | UNIT | 24 | MATERIAL | 348.48
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | EXTERIOR SHEATING | ZIP SYSTEM 4FT X 8 FT - WALL SHEATING | UNIT | 8 | MATERIAL | 116.16
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | EXTERIOR SHEATING | ZIP SYSTEM TAPE X 90 FT | UNIT | 4 | MATERIAL | 59.4
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DOORS AND WINDOWS | INTERIOR MDP PREFAB DOORS 80¨ | UN | 3 | MATERIAL | 648
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DOORS AND WINDOWS | POCKET DOOR | UN | 1 | MATERIAL | 510
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DOORS AND WINDOWS | VYNIL WINDOWS - NEW CONSTRUCTION | UN | 2 | MATERIAL | 816
PALO004 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DOORS AND WINDOWS | VYNIL WINDOWS - REMOVE AND REPLACE | UN | 1 | LABOR | 588
PALO005 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | SIDING / BRICK | Siding or bricks | WEEK | 46 | TASK
PALO005 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | STUCCO / SIDING | LABOR - WALL - BRICKS | SQ FT | 328 ' | LABOR | 885.6
PALO005 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | STUCCO / SIDING | MATERIALS - WALL - BRICKS | SQ FT | 360 ' | MATERIAL | 1188
PALO006 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ROOFING | Roofing | WEEK | 45 | TASK
PALO006 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ROOFING | LABOR (CONSTRUCTION SQ FT) - SHINGLES | SQ FT | 771 | ALL INCLUDED | 763.29
PALO006 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ROOFING | SHINGLES | UNIT | 9 | ALL INCLUDED | 504.9
PALO006 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ROOFING | ROOF PROTECTOR UNDERLAYMENT | SQ FT | 771 | ALL INCLUDED | 339.24
PALO006 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ROOFING | GALVANIZED FLASHING | UNIT | 3 | ALL INCLUDED | 462
PALO006 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ROOFING | GAF WEATHERWATCH 100 LN FT (200 SQFT) | UNIT | 3 | ALL INCLUDED | 231
PALO006 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ROOFING | GAF PRO START 120 LN FT - STARTER TRIP SHINGLES | UNIT | 6 | ALL INCLUDED | 145.134
PALO006 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ROOFING | COBRA EXHAUST VENT - RIDGE VENT 20 LN FT | UNIT | 1 | ALL INCLUDED | 30.25
PALO007 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | INSULATION | Wall Insulation | WEEK | 47 | TASK
PALO007 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | INSULATION | LABOR - INSTALLATION COST PER WALL ROLL | SQ FT | 232 ' | LABOR | 111.36
PALO007 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | INSULATION | R15 WALL INSULATION (33 BAGS X 1000 SQ FT) | SQ FT | 15 ' | MATERIAL | 171
PALO008 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | INSULATION | Roof Insulation | WEEK | 49 | TASK
PALO008 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | INSULATION | LABOR - INSTALLATION COST PER CEILING BLOWING-IN | SQ FT | 204 ' | LABOR | 134.64
PALO008 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | INSULATION | R30 BLOWN INSULATION (15 BAGS X 1000 SQ FT) | SQ FT | 12 ' | MATERIAL | 309.6
PALO009 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DRYWALL | Sheet Rock | WEEK | 48 | TASK
PALO009 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DRYWALL | Tape Bet and Texture | WEEK | 48 | TASK
PALO009 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DOORS AND WINDOWS | Interior Doors Installation | WEEK | 49 | TASK
PALO009 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DRYWALL | LABOR - ADDITION WALL - PER SHEET (HANG TAPE BED AND | EA | 15 ' | LABOR | 765
PALO009 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DRYWALL | LABOR - ADDITION CEILING - PER SHEET (HANG, TAPE, BED A | EA | 7 ' | LABOR | 504
PALO009 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DRYWALL | LABOR - PATCH CEILING - PER SHEET (HANG, TAPE, BED AND | EA |  | LABOR | 373.5
PALO009 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DRYWALL | MATERIALS - WALLS | EA | 17 ' | MATERIAL | 209.1
PALO009 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DRYWALL | MATERIALS - CEILINGS | EA | 8 ' | MATERIAL | 98.4
PALO009 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DRYWALL | OTHER MATERIALS | EA | 1 ' | MATERIAL | 210
PALO010 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | TILES | Tiles | WEEK | 49 | TASK
PALO010 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | TILES | LABOR - FLOOR TILES INSTALLATION | SQ FT | 98 ' | LABOR | 705.6
PALO010 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | TILES | LABOR - SHOWER FLOOR TILES INSTALLATION | SQ FT | 28 ' | LABOR | 588
PALO010 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | TILES | LABOR - SHOWER WALL TILES INSTALLATION | SQ FT | 120 ' | LABOR | 1116
PALO010 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | TILES | TILES - FLOOR | SQ FT | 107 ' | MATERIAL | 288.9
PALO010 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | TILES | TILES - SHOWER WALLS | SQFT | 132 ' | MATERIAL | 594
PALO010 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | TILES | TILES - SHOWER FLOOR | SQ FT | 31 ' | MATERIAL | 223.2
PALO010 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | TILES | OTHER MATERIALS | EA | 1 ' | MATERIAL | 330
PALO011 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | PAINT | Painting | WEEK | 49 | TASK
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | Leveling and floating of floors | WEEK | 50 | TASK
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | Floor Installation | WEEK | 50 | TASK
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | Moldures and Baseboard Installation | WEEK | 50 | TASK
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | Trim, baseboards and Mantel Painting | WEEK | 50 | TASK
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | LABOR - INSTALLATION CLICK FLOORING LVP | SQ FT | 336 ' | LABOR | 504
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | LABOR - INSTALLATION CARPET | SQ FT | 522 ' | LABOR | 689.04
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | LABOR - INSTALLATION VINYL FLOOR INSTALLATION | LN FT | 89 ' | LABOR | 96.12
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | LUXURY VINYL FLOORING | SQ FT | 370 ' | MATERIAL | 1221
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | CARPET | SQ FT | 575 ' | MATERIAL | 1345.5
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | CUSTOM BASEBOARDS | EA | 92 ' | MATERIAL | 231.84
PALO012 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | FLOORING | OTHER MATERIAL | EA | 1 ' | MATERIAL | 330
PALO013 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | CABINETS | Custom Cabinets Fabrication | WEEK | 48 | TASK
PALO013 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | CABINETS | Resurface Kitchen Cabinets | WEEK | 51 | TASK
PALO013 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | CABINETS | Vanities Installation | WEEK | 51 | TASK
PALO013 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | CABINETS | CUSTOM PANTRY CABINET PER LN FT | LN FT | 2 ' | ALL INCLUDED | 648
PALO013 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | CABINETS | RESURFACE KITCHEN CABINETS | LN FT | 45 ' | ALL INCLUDED | 3510
PALO013 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | CABINETS | PRE FAB VANITY 72 IN W/QUARTZ | EA | 1 ' | ALL INCLUDED | 1530
PALO014 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | ROOFING | Gutters | WEEK | 51 | TASK
PALO015 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | GLASS | Glass Installation | WEEK | 51 | TASK
PALO015 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DRAIN SYSTEM | Install Drain System | WEEK | 52 | TASK
PALO015 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | GLASS | SHOWER GLASS PANEL 3FT TO 4FT | EA | 1 ' | ALL INCLUDED | 510
PALO016 | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | DRAIN SYSTEM | BASIN DRAIN | EA | 1 ' | ALL INCLUDED | 1080
X | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | GENERAL CONDITIONS | Surveyor Documents | WEEK | 38 | TASK
X | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work | WEEK | 38 | TASK
X | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | GENERAL CONDITIONS | Permits | WEEK | 38 | TASK
X | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | GENERAL CONDITIONS | DEMO OF STRUCTURE | WEEK | 39 | TASK
X | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | OTHERS | DELIVERY | WEEK | 52 | TASK
X | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | GENERAL CONDITIONS TOTAL | DUMPSTER FEES - ISYD | EA | 4 | LABOR | 2112
X | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | GENERAL CONDITIONS TOTAL | GENERAL PROJECT CLEANING - M | EA | 1 | LABOR | 280
X | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | GENERAL CONDITIONS TOTAL | CITY PERMITS | EA | 1 | LABOR | 2800
X | Anthony Romo | 1731 Palo Duro Trail Grapevine, TX 76051 | GENERAL CONDITIONS TOTAL | DEMO | CY | 7 | LABOR | 840
LAKE001 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 3.00 FOUNDATION TOTAL | FORM WORK | SQ FT | 240 | ALL INCLUDED
LAKE001 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 3.00 FOUNDATION TOTAL | PIERS | UNIT | 16 | ALL INCLUDED
LAKE001 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 3.00 FOUNDATION TOTAL | GRADE BEAMS / FOOTINGS | LF | 108 | ALL INCLUDED
LAKE001 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 3.00 FOUNDATION TOTAL | CONCRETE SLAB | SQ FT | 240 | ALL INCLUDED
LAKE001 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | FOUNDATION | Foundation Form and Excavation | WEEK | 38 | TASK
LAKE001 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar | WEEK | 39 | TASK
LAKE001 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | FOUNDATION | Concrete Pour | WEEK | 39 | TASK
LAKE0012 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 12.0 FLOORING | LABOR - POLISHED AND SEALED CONCRETE | SQ FT | 240 | LABOR
LAKE0012 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 12.0 FLOORING | LABOR - INSTALLATION TRIM AND BASEBOARDS | LN FT | 64 | LABOR
LAKE0012 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 12.0 FLOORING | POLISHED AND SEALED CONCRETE | SQ FT | 264 | LABOR
LAKE0012 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 12.0 FLOORING | SOLID WOOD BASEBOARDS | LN FT | 70 | MATERIAL
LAKE0012 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 12.0 FLOORING | OTHER MATERIAL | EA | 1 | MATERIAL
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 1-00 GENERAL CONDITIONS TOTAL | DEMO | CY | 6 | LABOR
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 6.0 FRAMING | ADDITION REFRAME - STRUCTURAL - LABOR | SF | 240 | LABOR
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 6.0 FRAMING | ADDITION REFRAME - STRUCTURAL - MATERIAL | SF | 264 | MATERIAL
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 7.0 EXTERIOR SHEATING | LABOR (SURFACE SQ FT) - SHEATING | SQ FT | 512 | LABOR
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 7.0 EXTERIOR SHEATING | ZIP SYSTEM 4FT X 8 FT - ROOF SHEATING | UNIT | 8 | MATERIAL
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 7.0 EXTERIOR SHEATING | ZIP SYSTEM 4FT X 8 FT - WALL SHEATING | UNIT | 16 | MATERIAL
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 7.0 EXTERIOR SHEATING | ZIP SYSTEM TAPE X 90 FT | UNIT | 7 | MATERIAL
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 9.0 DOORS AND WINDOWS | INTERIOR MDP PREFAB DOORS 80¨ | UN | 2 | MATERIAL
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 9.0 DOORS AND WINDOWS | EXTERIOR ALUMINUM PREFAB DOORS 80¨ | UN | 1 | MATERIAL
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 9.0 DOORS AND WINDOWS | VYNIL WINDOWS - NEW CONSTRUCTION | UN | 2 | MATERIAL
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | GENERAL CONDITIONS | DEMO | WEEK | 41 | TASK
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | FRAMING | Framing | WEEK | 41 | TASK
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) | WEEK | 43 | TASK
LAKE002 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | DOORS AND WINDOWS | Exterior Windows and Doors | WEEK | 43 | TASK
LAKE003 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 13.0 STUCCO / SIDING | LABOR - WALL - BRICKS | SQ FT | 512 | LABOR
LAKE003 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 13.0 STUCCO / SIDING | MATERIALS - WALL - BRICKS | SQ FT | 563 | MATERIAL
LAKE003 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | SIDING / BRICK | Bricks | WEEK | 43 | TASK
LAKE004 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 8.0 ROOFING | LABOR (CONSTRUCTION SQ FT) - SHINGLES | SQ FT | 343 | ALL INCLUDED
LAKE004 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 8.0 ROOFING | SHINGLES | UNIT | 6 | ALL INCLUDED
LAKE004 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 8.0 ROOFING | ROOF PROTECTOR UNDERLAYMENT | SQ FT | 298 | ALL INCLUDED
LAKE004 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | ROOFING | Roofing | WEEK | 43 | TASK
LAKE005 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 4.00 ELECTRICAL | LABOR - ADDITION - SUBPANEL | UNIT | 1 | LABOR
LAKE005 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 4.00 ELECTRICAL | LABOR - ADDITION - WIRING | SQ FT | 240 | LABOR
LAKE005 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 4.00 ELECTRICAL | LED RECESSED LIGHT | UNIT | 4 | MATERIAL
LAKE005 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | ELECTRICAL | Electrical Rough In | WEEK | 43 | TASK
LAKE005 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | ELECTRICAL | Accesories Installation | WEEK | 47 | TASK
LAKE006 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 14.0 HVAC | A/C DUCTING | EA | 1 | ALL INCLUDED
LAKE006 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | MECHANICAL | Mechanic (HVAC) Rough in | WEEK | 43 | TASK
LAKE007 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 11.0 INSULATION | LABOR - INSTALLATION COST PER WALL ROLL | SQ FT | 512 | LABOR
LAKE007 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 11.0 INSULATION | R15 WALL INSULATION (33 BAGS X 1000 SQ FT) | SQ FT | 19 | MATERIAL
LAKE007 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | INSULATION | Wall Insulation | WEEK | 44 | TASK
LAKE008 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 11.0 INSULATION | LABOR - INSTALLATION COST PER CEILING BLOWING-IN | SQ FT | 240 | LABOR
LAKE008 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 11.0 INSULATION | R30 BLOWN INSULATION (15 BAGS X 1000 SQ FT) | SQ FT | 9 | MATERIAL
LAKE008 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | INSULATION | Roof Insulation | WEEK | 44 | TASK
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 10.0 PAINT | LABOR - WALLS UP TO 10 FT | SQ FT | 512 | LABOR
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 10.0 PAINT | LABOR - CEILING | SQ FT | 240 | LABOR
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 10.0 PAINT | LABOR - TRIM PAINT | LNFT | 64 | LABOR
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 10.0 PAINT | MATERIAL - WALL PAINT | UNIT | 2 | MATERIAL
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 10.0 PAINT | MATERIAL - CEILING PAINT | UNIT | 1 | MATERIAL
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 10.0 PAINT | MATERIAL - TRIM PAINT | UNIT | 1 | MATERIAL
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 10.0 PAINT | OTHER MATERIALS | GLOBAL | 1 | MATERIAL
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 20.0 DRYWALL | LABOR - ADDITION WALL - PER SHEET (HANG TAPE BED AND TEXTURE) | EA | 17 | LABOR
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 20.0 DRYWALL | LABOR - ADDITION CEILING - PER SHEET (HANG, TAPE, BED AND TEXTURE) | EA | 9 | LABOR
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 20.0 DRYWALL | MATERIALS - WALLS | EA | 19 | MATERIAL
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 20.0 DRYWALL | MATERIALS - CEILINGS | EA | 11 | MATERIAL
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 20.0 DRYWALL | OTHER MATERIALS | EA | 1 | MATERIAL
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | DRYWALL | Sheet Rock | WEEK | 46 | TASK
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | DRYWALL | Tape Bet and Texture | WEEK | 46 | TASK
LAKE009 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | PAINT | Painting | WEEK | 46 | TASK
LAKE010 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 15.0 TILES | LABOR - FLOOR TILES INSTALLATION | SQ FT | 25 | LABOR
LAKE010 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | TILES | Tiles Installation | WEEK | 46 | TASK
LAKE011 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | ROOFING | Gutters | WEEK | 47 | TASK
LAKE012 | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | FLOORING | Flooring Polished Concrete | WEEK | 47 | TASK
X | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 1-00 GENERAL CONDITIONS TOTAL | FORM SURVEY | EA | 1
X | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 1-00 GENERAL CONDITIONS TOTAL | DUMPSTER FEES - ISYD | EA | 3
X | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 1-00 GENERAL CONDITIONS TOTAL | GENERAL PROJECT CLEANING - M | EA | 1
X | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 1-00 GENERAL CONDITIONS TOTAL | ARCHITECTURAL SET OF PLANS - ADDITION | SQ FT | 240
X | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 1-00 GENERAL CONDITIONS TOTAL | STRUCTURAL SET OF PLANS - ADDITION | SQ FT | 240
X | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 1-00 GENERAL CONDITIONS TOTAL | STRUCTURAL ENGINEERING REPORT | EA | 1
X | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 1-00 GENERAL CONDITIONS TOTAL | ENGINEERING FOUNDATION REPORT | EA | 1
X | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | 1-00 GENERAL CONDITIONS TOTAL | CITY PERMITS | EA | 1
x | Robert Campbell | 111 Lakeside LnLittle Elm, TX 75068 | OTHERS | Delivery Week | WEEK | 48 | TASK
x | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 1-00 GENERAL CONDITIONS TOTAL | DUMPSTER FEES - ISYD | EA | 2 | X
x | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 1-00 GENERAL CONDITIONS TOTAL | GENERAL PROJECT CLEANING - M | EA | 1 | X
x | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | GENERAL CONDITIONS | Surveyor Documents | WEEK | 38 | TASK
x | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work | WEEK | 38 | TASK
x | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | GENERAL CONDITIONS | Permits | WEEK | 38 | TASK
x | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | GENERAL CONDITIONS | Post Permits | WEEK | 38 | TASK
x | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | GENERAL CONDITIONS | Place Dumpsters | WEEK | 38 | TASK
x | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | OTHERS | DELIVERY WEEK | WEEK | 42 | TASK
YALE001 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 1-00 GENERAL CONDITIONS TOTAL | DEMO | CY | 7 | LABOR
YALE001 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | GENERAL CONDITIONS | DEMO OF STRUCTURE | WEEK | 38 | TASK
YALE002 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 4.00 ELECTRICAL | ELECTRICAL - MAJOR | UNIT | 8 | LABOR
YALE002 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 4.00 ELECTRICAL | LED RECESSED LIGHT | UNIT | 4 | MATERIAL
YALE002 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 4.00 ELECTRICAL | DECORATIVE LIGHT FIXTURE | UNIT | 1 | MATERIAL
YALE002 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | ELECTRICAL | Electrical Rough In | WEEK | 38 | TASK
YALE002 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | ELECTRICAL | Accesories Installation | WEEK | 41 | TASK
YALE003 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 5.00 PLUMBING | LABOR PER SERVICE - REMODELING & RELOCATING | UNIT | 6 | LABOR
YALE003 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 5.00 PLUMBING | KITCHEN FAUCET - BG | UNIT | 1 | MATERIAL
YALE003 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 5.00 PLUMBING | KITCHEN SINK - BG | UNIT | 1 | MATERIAL
YALE003 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 5.00 PLUMBING | POT FILLER - BG | UNIT | 1 | MATERIAL
YALE003 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | PLUMBING | Inground Plumbing | WEEK | 38 | TASK
YALE003 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | PLUMBING | Plumbing Rough In | WEEK | 38 | TASK
YALE003 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | PLUMBING | Fixture Installation | WEEK | 41 | TASK
YALE004 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 6.0 FRAMING | LABOR - LOAD BEARING WALL OPEN CONCEPT | LN FT | 16 | LABOR
YALE004 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 6.0 FRAMING | MATERIAL - LOAD BEARING WALL OPEN CONCEPT | LN FT | 16 | MATERIAL
YALE004 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | FRAMING | Framing | WEEK | 38 | TASK
YALE005 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 10.0 PAINT | LABOR - WALLS UP TO 10 FT | SQ FT | 522 ' | LABOR
YALE005 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 10.0 PAINT | LABOR - CEILING | SQ FT | 1722 ' | LABOR
YALE005 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 10.0 PAINT | LABOR - INTERIOR DOOR PAINT | EA | 1 ' | LABOR
YALE005 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 10.0 PAINT | LABOR - TRIM PAINT | LNFT | 67 ' | LABOR
YALE005 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 10.0 PAINT | LABOR - REMOVING POPCORN CEILIJNG | SQ FT | 1722 ' | LABOR
YALE005 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 10.0 PAINT | MATERIAL - WALL PAINT | UNIT | 2 ' | MATERIAL
YALE005 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 10.0 PAINT | MATERIAL - CEILING PAINT | UNIT | 5 ' | MATERIAL
YALE005 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 10.0 PAINT | MATERIAL - TRIM PAINT | UNIT | 1 ' | MATERIAL
YALE005 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 10.0 PAINT | OTHER MATERIALS | GLOBAL | 1 ' | MATERIAL
YALE005 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | PAINT | Painting | WEEK | 39 | TASK
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 12.0 FLOORING | LABOR - INSTALLATION CLICK FLOORING LVP | SQ FT | 1722 ' | LABOR
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 12.0 FLOORING | LABOR - INSTALLATION TRIM AND BASEBOARDS | LN FT | 76 ' | LABOR
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 12.0 FLOORING | LABOR - REMOVE FLOOR TILE | SQFT | 282 ' | LABOR
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 12.0 FLOORING | LABOR - CROWN MOLDING | LN FT | 76 ' | LABOR
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 12.0 FLOORING | CROWN MOLDING | LN FT | 80 ' | MATERIAL
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 12.0 FLOORING | LUXURY VINYL FLOORING | SQ FT | 1895 ' | MATERIAL
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 12.0 FLOORING | SOLID WOOD BASEBOARDS | LN FT | 80 ' | MATERIAL
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 12.0 FLOORING | OTHER MATERIAL | EA | 1 ' | MATERIAL
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | FLOORING | Leveling and floating of floors | WEEK | 40 | TASK
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | FLOORING | Floor Installation | WEEK | 40 | TASK
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | FLOORING | Moldures and Baseboard Installation | WEEK | 40 | TASK
YALE006 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | FLOORING | Trim, baseboards and Mantel Painting | WEEK | 40 | TASK
YALE007 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 13.0 STUCCO / SIDING | WALL - BRICKS | UNIT | 1 ' | LABOR
YALE007 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | SIDING / BRICK | Siding or bricks or stucco | WEEK | 40 | TASK
YALE008 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 15.0 TILES | LABOR - BACKSPLASH TILES INSTALLATION | SQ FT | 110 ' | LABOR
YALE008 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 15.0 TILES | TILES - BACKSPLASH | SQ FT | 115 ' | MATERIAL
YALE008 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 15.0 TILES | OTHER MATERIALS | EA | 2 ' | MATERIAL
YALE008 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | TILES | Tiles Backsplash | WEEK | 41 | TASK
YALE009 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 18.0 CABINETS | CUSTOM BASE CABINET PER LN FT | LN FT | 19 ' | ALL INCLUDED
YALE009 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 18.0 CABINETS | CUSTOM UPPER CABINET PER LN FT | LN FT | 30 ' | ALL INCLUDED
YALE009 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 18.0 CABINETS | KITCHEN ISLAND PANELING | LN FT | 16 ' | ALL INCLUDED
YALE009 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 18.0 CABINETS | BREAKFAST NOOK SLIDING DOOR | UNIT | 1 ' | ALL INCLUDED
YALE009 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | CABINETS | Kitchen Cabinets Fabrication | WEEK | 38 | TASK
YALE009 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | CABINETS | Kitchen Island Fabrication | WEEK | 38 | TASK
YALE009 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | CABINETS | Kitchen Cabinets Installation | WEEK | 40 | TASK
YALE010 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 19.0 COUNTERTOPS | QUARTZ - PURE WHITE | SQFT | 84 ' | ALL INCLUDED
YALE010 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | COUNTERTOP | Countertop Intallation | WEEK | 41 | TASK
YALE011 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 20.0 DRYWALL | LABOR - REMODELING WALL - PER SHEET (HANG TAPE BED A | EA | 5 ' | LABOR
YALE011 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 20.0 DRYWALL | LABOR - REMODELING CEILING - PER SHEET (HANG, TAPE, B | EA | 5 ' | LABOR
YALE011 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 20.0 DRYWALL | MATERIALS - WALLS | EA | 6 ' | MATERIAL
YALE011 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 20.0 DRYWALL | MATERIALS - CEILINGS | EA | 6 ' | MATERIAL
YALE011 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | 20.0 DRYWALL | OTHER MATERIALS | EA | 1 ' | MATERIAL
YALE011 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | DRYWALL | Sheet Rock | WEEK | 38 | TASK
YALE011 | Cindy Ferguson | 733 Yale Dr Allen, TX 75002 | DRYWALL | Tape Bet and Texture | WEEK | 39 | TASK
COUNTY001 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 2.00 SITE WORK TOTALS | GRADING | UNIT | 1 | LABOR | 1080
COUNTY001 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 3.00 FOUNDATION TOTAL | FORM WORK | SQ FT | 600 | ALL INCLUDED | 378
COUNTY001 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 3.00 FOUNDATION TOTAL | PIERS | UNIT | 24 | ALL INCLUDED | 5376
COUNTY001 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 3.00 FOUNDATION TOTAL | GRADE BEAMS / FOOTINGS | LF | 170 | ALL INCLUDED | 892.5
COUNTY001 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 3.00 FOUNDATION TOTAL | CONCRETE SLAB | SQ FT | 600 | ALL INCLUDED | 3990
COUNTY001 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | SITE WORK | Grading and soil leveling | WEEK | 38 | TASK
COUNTY001 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | FOUNDATION | Foundation Form and Excavation | WEEK | 38 | TASK
COUNTY001 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | FOUNDATION | Concrete Piers | WEEK | 38 | TASK
COUNTY001 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar | WEEK | 38 | TASK
COUNTY001 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | FOUNDATION | Concrete Pour | WEEK | 38 | TASK
COUNTY002 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 4.00 ELECTRICAL | LABOR - ADDITION - SUBPANEL | SQ FT | 600 | LABOR | 3600
COUNTY002 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 4.00 ELECTRICAL | LED RECESSED LIGHT | UNIT | 12 | MATERIAL | 150
COUNTY002 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 4.00 ELECTRICAL | CEILING FAN LIGHT FIXTURE | UNIT | 2 | MATERIAL | 250
COUNTY002 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 4.00 ELECTRICAL | DECORATIVE LIGHT FIXTURE | UNIT | 1 | MATERIAL | 75
COUNTY002 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 4.00 ELECTRICAL | EXAUST FAN | UNIT | 1 | MATERIAL | 30
COUNTY002 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | ELECTRICAL | Electrical Rough In | WEEK | 38 | TASK
COUNTY002 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | ELECTRICAL | Electrical For HVAC | WEEK | 39 | TASK
COUNTY002 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | ELECTRICAL | Smoke Detectors Installation | WEEK | 42 | TASK
COUNTY002 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | ELECTRICAL | Accesories Installation | WEEK | 42 | TASK
COUNTY004 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 5.00 PLUMBING | LABOR PER SERVICE - ADDITION | UNIT | 7 | LABOR | 2625
COUNTY004 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 5.00 PLUMBING | TOILET - BG | UNIT | 1 | MATERIAL | 175
COUNTY004 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 5.00 PLUMBING | SHOWER FAUCET - BG | UNIT | 1 | MATERIAL | 275
COUNTY004 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 5.00 PLUMBING | BATHROOM FAUCET - BG | UNIT | 1 | MATERIAL | 125
COUNTY004 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 5.00 PLUMBING | SINK - BG | UNIT | 1 | MATERIAL | 200
COUNTY004 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 5.00 PLUMBING | SUPPORT BAR 18¨ | UNIT | 2 | MATERIAL | 80
COUNTY004 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 5.00 PLUMBING | SHOWER BASE WHITE 60 x 30 | UNIT | 1 | LABOR | 240
COUNTY004 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | PLUMBING | Inground Plumbing | WEEK | 38 | TASK
COUNTY004 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | PLUMBING | Plumbing Rough In | WEEK | 38 | TASK
COUNTY004 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | PLUMBING | Fixture Installation | WEEK | 42 | TASK
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 6.0 FRAMING | ADDITION REFRAME - STRUCTURAL - LABOR | SF | 600 | LABOR | 3135
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 6.0 FRAMING | ADDITION REFRAME - STRUCTURAL - MATERIAL | SF | 660 | MATERIAL | 4356
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 6.0 FRAMING | ADDING A WALL - LABOR (WALL SQ FT) | SF | 108 | LABOR | 148.5
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 6.0 FRAMING | ADDING A WALL - MATERIAL (WALL SQ FT) | SF | 118 | MATERIAL | 356.95
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 6.0 FRAMING | EXTERIOR DECKING - LABOR | SQ FT | 120 | LABOR | 693
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 6.0 FRAMING | EXTERIOR DECKING - MATERIAL | SQ FT | 132 | MATERIAL | 3267
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 7.0 EXTERIOR SHEATING | LABOR (SURFACE SQ FT) - SHEATING | SQ FT | 1380 | LABOR | 1242
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 7.0 EXTERIOR SHEATING | ZIP SYSTEM 4FT X 8 FT - ROOF SHEATING | UNIT | 28 | MATERIAL | 406.56
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 7.0 EXTERIOR SHEATING | ZIP SYSTEM 4FT X 8 FT - WALL SHEATING | UNIT | 22 | MATERIAL | 319.44
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 7.0 EXTERIOR SHEATING | ZIP SYSTEM TAPE X 90 FT | UNIT | 3 | MATERIAL | 44.55
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 9.0 DOORS AND WINDOWS | POCKET DOOR | UN | 3 | MATERIAL | 1530
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 9.0 DOORS AND WINDOWS | EXTERIOR ALUMINUM PREFAB DOORS 80¨ | UN | 1 | MATERIAL | 390
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 9.0 DOORS AND WINDOWS | VYNIL WINDOWS - NEW CONSTRUCTION | UN | 7 | MATERIAL | 2856
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 9.0 DOORS AND WINDOWS | STORM/SCREEN DOOR | UN | 1 | MATERIAL | 270
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | GENERAL CONDITIONS | Demo Preparation | WEEK | 38 | TASK
COUNTY005 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | FRAMING | Patio Decking and Skirt | WEEK | 39 | TASK
COUNTY006 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 8.0 ROOFING | LABOR (CONSTRUCTION SQ FT) - SHINGLES | SQ FT | 780 | ALL INCLUDED | 772.2
COUNTY006 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 8.0 ROOFING | SHINGLES | UNIT | 27 | ALL INCLUDED | 1514.7
COUNTY006 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 8.0 ROOFING | ROOF PROTECTOR UNDERLAYMENT | SQ FT | 780 | ALL INCLUDED | 343.2
COUNTY006 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 8.0 ROOFING | GALVANIZED FLASHING | UNIT | 1 | ALL INCLUDED | 154
COUNTY006 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 8.0 ROOFING | GAF WEATHERWATCH 100 LN FT (200 SQFT) | UNIT | 3 | ALL INCLUDED | 231
COUNTY006 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 8.0 ROOFING | GAF PRO START 120 LN FT - STARTER TRIP SHINGLES | UNIT | 1 | ALL INCLUDED | 24.189
COUNTY006 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 8.0 ROOFING | COBRA EXHAUST VENT - RIDGE VENT 20 LN FT | UNIT | 1 | ALL INCLUDED | 30.25
COUNTY006 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | ROOFING | Roofing | WEEK | 38 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | LABOR - WALLS UP TO 10 FT | SQ FT | 1140 | LABOR | 1026
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | LABOR - CEILING | SQ FT | 600 | LABOR | 792
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | LABOR - SIDING PAINT ( EXTERIOR) | SQ FT | 805 | LABOR | 821.1
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | LABOR - INTERIOR DOOR PAINT | EA | 1 | LABOR | 108
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | LABOR - TRIM PAINT | LNFT | 140 | LABOR | 100.8
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | LABOR - FRONT DOOR PAINT | EA | 1 | LABOR | 330
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | MATERIAL - WALL PAINT | UNIT | 3 | MATERIAL | 315
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | MATERIAL - CEILING PAINT | UNIT | 1 | MATERIAL | 105
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | MATERIAL - TRIM PAINT | UNIT | 1 | MATERIAL | 51
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | MATERIAL - DOORS PAINT | UNIT | 2 | MATERIAL | 102
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 10.0 PAINT | OTHER MATERIALS | GLOBAL | 1 | MATERIAL | 348
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 12.0 FLOORING | LABOR - INSTALLATION CLICK FLOORING LVP | SQ FT | 660 | LABOR | 990
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 12.0 FLOORING | WATER RESISTANT LAMINATED FLOORS | SQ FT | 726 | LABOR | 1873.08
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 12.0 FLOORING | MDF BASEBOARDS | SQ FT | 140 | MATERIAL | 184.8
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 12.0 FLOORING | OTHER MATERIAL | EA | 1 | MATERIAL | 330
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 13.0 STUCCO / SIDING | LABOR - WALL - SIDING | SQ FT | 630 | LABOR | 680.4
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 13.0 STUCCO / SIDING | MATERIALS - WALL - SIDING | SQ FT | 693 | MATERIAL | 1081.08
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 15.0 TILES | LABOR - SHOWER FLOOR TILES INSTALLATION | SQ FT | 20 | LABOR | 420
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 15.0 TILES | LABOR - SHOWER WALL TILES INSTALLATION | SQ FT | 104 | LABOR | 967.2
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 15.0 TILES | TILES - SHOWER WALLS | SQFT | 114 | MATERIAL | 513
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 15.0 TILES | TILES - SHOWER FLOOR | SQ FT | 22 | MATERIAL | 158.4
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 15.0 TILES | TILES - QUARTZ NICHE (36 IN) | EA | 1 | MATERIAL | 72
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 15.0 TILES | OTHER MATERIALS | EA | 1 | MATERIAL | 330
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 17.0 GLASS | SHOWER GLASS DOOR 5FT X 72 IN (FIXED - SLIDING) | EA | 1 | ALL INCLUDED | 750
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 20.0 DRYWALL | LABOR - ADDITION WALL - PER SHEET (HANG TAPE BED AND TEXTURE) | EA | 48 | LABOR | 2448
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 20.0 DRYWALL | LABOR - ADDITION CEILING - PER SHEET (HANG, TAPE, BED AND TEXTURE) | EA | 19 | LABOR | 1368
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 20.0 DRYWALL | MATERIALS - WALLS | EA | 53 | MATERIAL | 651.9
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 20.0 DRYWALL | MATERIALS - CEILINGS | EA | 20 | MATERIAL | 246
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 20.0 DRYWALL | OTHER MATERIALS | EA | 1 | MATERIAL | 210
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | SIDING / BRICK | Siding Installation | WEEK | 40 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | DRYWALL | Sheet Rock | WEEK | 40 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | DRYWALL | Hardybacker Installation | WEEK | 40 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | DRYWALL | Wet Areas Water Proofing Redguard | WEEK | 40 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | DRYWALL | Tape Bet and Texture | WEEK | 40 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | TILES | Tiles | WEEK | 40 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | DOORS AND WINDOWS | Interior Doors Installation | WEEK | 40 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | PAINT | Painting | WEEK | 40 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | FLOORING | Leveling and floating of floors | WEEK | 41 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | FLOORING | Floor Installation | WEEK | 41 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | FLOORING | Moldures and Baseboard Installation | WEEK | 41 | TASK
COUNTY007 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | FLOORING | Trim, baseboards and Mantel Painting | WEEK | 41 | TASK
COUNTY008 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 11.0 INSULATION | LABOR - INSTALLATION COST PER WALL ROLL | SQ FT | 600 | LABOR | 288
COUNTY008 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 11.0 INSULATION | R15 WALL INSULATION (33 BAGS X 1000 SQ FT) | SQ FT | 20 | MATERIAL | 228
COUNTY008 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | INSULATION | Wall Insulation | WEEK | 39 | TASK
COUNTY009 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 11.0 INSULATION | LABOR - INSTALLATION COST PER CEILING BLOWING-IN | SQ FT | 600 | LABOR | 396
COUNTY009 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 11.0 INSULATION | R30 BLOWN INSULATION (15 BAGS X 1000 SQ FT) | SQ FT | 9 | MATERIAL | 232.2
COUNTY010 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 14.0 HVAC | 3 TON HVAC | EA | 1 | ALL INCLUDED | 4680
COUNTY010 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | MECHANICAL | Mechanic (HVAC) Rough in | WEEK | 39 | TASK
COUNTY010 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | MECHANICAL | Mechanic (HVAC) Final | WEEK | 42 | TASK
COUNTY011 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 18.0 CABINETS | PRE FAB VANITY 60 IN W/QUARTZ | EA | 1 | ALL INCLUDED | 1350
COUNTY011 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 18.0 CABINETS | PRE FAB KITCHEN BASE CABINET | LN FT | 6 | ALL INCLUDED | 936
COUNTY011 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | CABINETS | Vanities Installation | WEEK | 41 | TASK
COUNTY012 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 19.0 COUNTERTOPS | QUARTZ - PURE WHITE | SQFT | 15 | ALL INCLUDED | 855
COUNTY012 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | COUNTERTOP | Countertop Intallation | WEEK | 41 | TASK
COUNTY013 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | FOUNDATION | Foundation Hooks | WEEK | 39 | TASK
COUNTY013 | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | ROOFING | Gutters | WEEK | 42 | TASK
X | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 1-00 GENERAL CONDITIONS TOTAL | DUMPSTER FEES - ISYD | EA | 2 | LABOR | 1056
X | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 1-00 GENERAL CONDITIONS TOTAL | GENERAL PROJECT CLEANING | SQ FT | 744 | LABOR | 892.8
X | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 1-00 GENERAL CONDITIONS TOTAL | ARCHITECTURAL SET OF PLANS - ADDITION | SQ FT | 744 | LABOR | 1309.44
X | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 1-00 GENERAL CONDITIONS TOTAL | STRUCTURAL SET OF PLANS - ADDITION | SQ FT | 744 | LABOR | 1071.36
X | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 1-00 GENERAL CONDITIONS TOTAL | ENGINEERING FOUNDATION REPORT | EA | 1 | LABOR | 680
X | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | 1-00 GENERAL CONDITIONS TOTAL | DEMO | CY | 12 | LABOR | 1440
X | DAVE BARRON | 13740 Co Rd 4041 Scurry, TX 75158 | OTHERS | DELIVERY | WEEK | 43 | TASK
STROLL001 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PLUMBING | Plumbing Rough In | WEEK | 42 | TASK
STROLL001 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PLUMBING | Fixtures Installation | WEEK | 49 | TASK
STROLL001 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PLUMBING | TOILET - BG | UNIT | 1 | MATERIAL | 175
STROLL001 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PLUMBING | SHOWER FAUCET - BG | UNIT | 1 | MATERIAL | 275
STROLL001 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PLUMBING | BATHROOM FAUCET - BG | UNIT | 1 | MATERIAL | 125
STROLL001 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PLUMBING | SINK - BG | UNIT | 1 | MATERIAL | 200
STROLL001 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PLUMBING | LABOR PER SERVICE - NEW CONSTRUCTION | UNIT | 8 | LABOR | 3400
STROLL001 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PLUMBING | BUILD UP SHOWER BASE | SQ FT | 30 | LABOR | 825
STROLL002 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | GENERAL CONDITIONS | DEMO OF STRUCTURE | WEEK | 40 | TASK
STROLL002 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | GENERAL CONDITIONS | DEMO | CY | 34 | LABOR | 4080
STROLL003 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | MECHANICAL | Mechanic (HVAC) Rough in | WEEK | 42 | TASK
STROLL003 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | SITE WORK TOTALS | A/C UNITS PAD | UN | 1 | MATERIAL | 120
STROLL003 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | HVAC | 3 TON HVAC | EA | 1 | ALL INCLUDED | 4680
STROLL004 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ELECTRICAL | Electrical Rough In | WEEK | 42 | TASK
STROLL004 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ELECTRICAL | Smoke Detectors Installation | WEEK | 49 | TASK
STROLL004 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ELECTRICAL | Accesories Installation | WEEK | 49 | TASK
STROLL004 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | OTHERS | DELIVERY | WEEK | 50 | TASK
STROLL004 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ELECTRICAL | LED RECESSED LIGHT | UNIT | 16 | MATERIAL | 200
STROLL004 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ELECTRICAL | CEILING FAN | UNIT | 1 | MATERIAL | 175
STROLL004 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ELECTRICAL | EXAUST FAN | UNIT | 1 | MATERIAL | 30
STROLL004 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ELECTRICAL | LABOR - ADDITION - SUBPANEL | UNIT | 1 | LABOR | 400
STROLL004 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ELECTRICAL | LABOR - ADDITION - WIRING | SQ FT | 1000 | LABOR | 5000
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FRAMING | Framing | WEEK | 40 | TASK
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) | WEEK | 41 | TASK
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DOORS AND WINDOWS | Exterior Windows and Doors | WEEK | 41 | TASK
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DOORS AND WINDOWS | Interior Doors Installation | WEEK | 46 | TASK
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FRAMING | ADDITION REFRAME - STRUCTURAL - MATERIAL | SF | 1108 | MATERIAL | 7312.8
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | EXTERIOR SHEATING | ZIP SYSTEM 4FT X 8 FT - ROOF SHEATING | UNIT | 49.5 | MATERIAL | 718.74
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | EXTERIOR SHEATING | ZIP SYSTEM 4FT X 8 FT - WALL SHEATING | UNIT | 42.9 | MATERIAL | 622.91
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | EXTERIOR SHEATING | ZIP SYSTEM TAPE X 90 FT | UNIT | 14 | MATERIAL | 207.9
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DOORS AND WINDOWS | INTERIOR MDP PREFAB DOORS 80¨ | UN | 3 | MATERIAL | 648
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DOORS AND WINDOWS | WOODEN FRENCH DOORS 72 X 80 | UN | 2 | MATERIAL | 1680
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DOORS AND WINDOWS | VYNIL WINDOWS - NEW CONSTRUCTION | UN | 3 | MATERIAL | 1224
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FRAMING | ADDITION REFRAME - STRUCTURAL - LABOR | SF | 1008 | LABOR | 5266.8
STROLL005 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | EXTERIOR SHEATING | LABOR (SURFACE SQ FT) - SHEATING | SQ FT | 1008 | LABOR | 907.2
STROLL006 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ROOFING | Roofing | WEEK | 41 | TASK
STROLL006 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ROOFING | LABOR (CONSTRUCTION SQ FT) - SHINGLES | SQ FT | 1441 | ALL INCLUDED | 1426.59
STROLL006 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ROOFING | SHINGLES | UNIT | 45 | ALL INCLUDED | 2524.5
STROLL006 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ROOFING | ROOF PROTECTOR UNDERLAYMENT | SQ FT | 1441 | ALL INCLUDED | 634.04
STROLL006 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ROOFING | GALVANIZED FLASHING | UNIT | 2 | ALL INCLUDED | 308
STROLL006 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ROOFING | GAF WEATHERWATCH 100 LN FT (200 SQFT) | UNIT | 1 | ALL INCLUDED | 77
STROLL006 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ROOFING | GAF PRO START 120 LN FT - STARTER TRIP SHINGLES | UNIT | 1 | ALL INCLUDED | 24.19
STROLL006 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ROOFING | COBRA EXHAUST VENT - RIDGE VENT 20 LN FT | UNIT | 1 | ALL INCLUDED | 30.25
STROLL007 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PAINT | Painting | WEEK | 46 | TASK
STROLL007 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PAINT | MATERIAL - WALL PAINT | UNIT | 2 | MATERIAL | 210
STROLL007 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PAINT | MATERIAL - CEILING PAINT | UNIT | 1 | MATERIAL | 105
STROLL007 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PAINT | MATERIAL - TRIM PAINT | UNIT | 1 | MATERIAL | 51
STROLL007 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PAINT | MATERIAL - DOORS PAINT | UNIT | 1 | MATERIAL | 51
STROLL007 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PAINT | OTHER MATERIALS | GLOBAL | 1 | MATERIAL | 348
STROLL007 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PAINT | LABOR - NEW CONSTRUCTION (BUILDING SQ FT) | SQ FT | 1008 | LABOR | 2116.8
STROLL007 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PAINT | LABOR - CEILING | SQ FT | 1008 | LABOR | 1330.56
STROLL007 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | PAINT | LABOR - TRIM PAINT | LNFT | 160 | LABOR | 115.2
STROLL008 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | INSULATION | Wall Insulation | WEEK | 43 | TASK
STROLL008 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | INSULATION | R15 WALL INSULATION (33 BAGS X 1000 SQ FT) | SQ FT | 33 | MATERIAL | 376.2
STROLL008 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | INSULATION | LABOR - INSTALLATION COST PER WALL ROLL | SQ FT | 1008 | LABOR | 483.84
STROLL009 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FLOORING | Leveling and floating of floors | WEEK | 47 | TASK
STROLL009 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FLOORING | Floor Installation | WEEK | 47 | TASK
STROLL009 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FLOORING | Moldures and Baseboard Installation | WEEK | 47 | TASK
STROLL009 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FLOORING | Trim, baseboards and Mantel Painting | WEEK | 47 | TASK
STROLL009 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FLOORING | CARPET | SQ FT | 990 | MATERIAL | 2316.6
STROLL009 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FLOORING | MDF BASEBOARDS | SQ FT | 1008 | MATERIAL | 1330.56
STROLL009 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FLOORING | OTHER MATERIAL | EA | 1 | MATERIAL | 330
STROLL009 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | FLOORING | LABOR - INSTALLATION CARPET | SQ FT | 990 | LABOR | 1306.8
STROLL010 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | SIDING / BRICK | Bricks Installation | WEEK | 41 | TASK
STROLL010 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | STUCCO / SIDING / BRICK | MATERIALS - WALL - BRICKS | SQ FT | 1012 | MATERIAL | 5009.4
STROLL010 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | STUCCO / SIDING / BRICK | LABOR - WALL - BRICKS | SQ FT | 920 | LABOR | 3726
STROLL011 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | TILES | Tiles | WEEK | 46 | TASK
STROLL011 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | TILES | TILES - FLOOR | SQ FT | 33 | MATERIAL | 89.1
STROLL011 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | TILES | TILES - SHOWER WALLS | SQFT | 158 | MATERIAL | 711
STROLL011 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | TILES | TILES - SHOWER FLOOR | SQ FT | 33 | MATERIAL | 237.6
STROLL011 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | TILES | TILES - QUARTZ NICHE (36 IN) | EA | 1 | MATERIAL | 72
STROLL011 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | TILES | OTHER MATERIALS | EA | 1 | MATERIAL | 330
STROLL011 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | TILES | LABOR - FLOOR TILES INSTALLATION | SQ FT | 30 | LABOR | 216
STROLL011 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | TILES | LABOR - SHOWER FLOOR TILES INSTALLATION | SQ FT | 30 | LABOR | 630
STROLL011 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | TILES | LABOR - SHOWER WALL TILES INSTALLATION | SQ FT | 144 | LABOR | 1339.2
STROLL012 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | GLASS | Glass Installation | WEEK | 49 | TASK
STROLL012 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | GLASS | SHOWER GLASS DOOR 5FT X 72 IN (FIXED - SLIDING) | EA | 1 | MATERIAL | 750
STROLL013 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | CABINETS | Vanities Installation | WEEK | 48 | TASK
STROLL013 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | CABINETS | PRE FAB VANITY 60 IN W/QUARTZ | EA | 1 | MATERIAL | 1350
STROLL014 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DRYWALL | Sheet Rock | WEEK | 45 | TASK
STROLL014 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DRYWALL | Hardybacker Installation | WEEK | 45 | TASK
STROLL014 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DRYWALL | Wet Areas Water Proofing Redguard | WEEK | 45 | TASK
STROLL014 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DRYWALL | Tape Bet and Texture | WEEK | 45 | TASK
STROLL014 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DRYWALL | MATERIALS - WALLS | EA | 55 | MATERIAL | 676.5
STROLL014 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DRYWALL | MATERIALS - CEILINGS | EA | 35 | MATERIAL | 430.5
STROLL014 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DRYWALL | LABOR - ADDITION WALL - PER SHEET (HANG TAPE BED AND TEXTURE) | EA | 50 | LABOR | 2550
STROLL014 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | DRYWALL | LABOR - ADDITION CEILING - PER SHEET (HANG, TAPE, BED AND TEXTURE) | EA | 35 | LABOR | 2520
STROLL015 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | INSULATION | Roof Insulation (New Houses | WEEK | 45 | TASK
STROLL015 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | INSULATION | R30 BLOWN INSULATION (15 BAGS X 1000 SQ FT) | SQ FT | 15 | MATERIAL | 387
STROLL015 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | INSULATION | LABOR - INSTALLATION COST PER CEILING BLOWING-IN | SQ FT | 1008 | LABOR | 665.28
STROLL016 | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | ROOFING | Gutters | WEEK | 49 | TASK
X | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | GENERAL CONDITIONS | Surveyor Documents | WEEK | 38 | TASK
X | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work | WEEK | 38 | TASK
X | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | GENERAL CONDITIONS | Permits | WEEK | 38 | TASK
X | AMAN MOHAMMED | 3505 Stroll Rd Plano, TX 75025 | GENERAL CONDITIONS | Post Permits | WEEK | 39 | TASK

## BACK UP
WORK ORDERS | Customer | Task | Sub | Status | Negotiated | Ball Park | Budget | Cost | Obs | Start week | End week | Actual Date | End Date
| Dave barron | Patio decking and skirt | [5 empty] | 1800 |  | 39
| Dave barron | Proveedor de siding e vinyl | [5 empty] | 4000 |  | 40
| Dave barron | HVAC inside | Frncisco |  |  |  |  | 3500 | ya pagamos 3500 | 38
| Dave Barron | Electrical hvac | Anthony |  |  |  |  | 1800 |  | 39 |  | 2023-09-26
| Dave barron | Spray foam insulation | [5 empty] | 3000 |  | 39
| Dave barron | Roofing replace | Bryan |  |  |  |  | 2000 |  | 39
| Dave barron | piso drywall y tile | nico |  |  |  |  | 9000 |  | 39 | 41
| Dave barron | comprar materiales | [5 empty] | 10000 |  | 39
| Dave barron | Fixture electrical and plumbing | [5 empty] | 1000 |  | 42
| Dave barron | Gutters | [5 empty] | 1000 |  | 40 |  | 37100
| Dave barron | Other touch up | [7 empty] | 43
| Dave barron | Ganchos | [5 empty] | 1000 |  | 39
| Amanda | concreto | [5 empty] | 3000 |  | 38
| Amanda | Framing | [5 empty] | 2600 |  | 39
| Amanda | exterior sheeting | [5 empty] | 600 |  | 40
| Amanda | door windows | [5 empty] | 600 |  | 40
| Amanda | electrical rough in | [5 empty] | 1000 |  | 40
| Amanda | plumbing rough in and top out | [5 empty] | 2000 |  | 40
| Amanda | hvac rough in | [7 empty] | 40
| Amanda | Insulation | [7 empty] | 40
| Amanda | Sheetrock tape and bet texture | [7 empty] | 41
| Amanda | Paint | [7 empty] | 41
| Amanda | Tiles | [7 empty] | 40
| Amanda | Cabinets fabrication | [7 empty] | 40 | 40
| Amanda | Cabinets installation | [7 empty] | 41
| Amanda | Cabinet paint | [7 empty] | 42
| Amanda | Countertops | [7 empty] | 43
| Amanda | Flooring | [7 empty] | 42
| Amanda | Tiles backsplash | [7 empty] | 43
| Amanda | Finishing electrical | [5 empty] | 200 |  | 44
| Amanda | Finish plumbing | [5 empty] | 1000 |  | 44
| Amanda | Delivery week | [7 empty] | 45
x | Robert Campbell | concreto | [7 empty] | 38 39
x | Robert Campbell | Framing | [7 empty] | 41
x | Robert Campbell | exterior sheeting | [7 empty] | 43
x | Robert Campbell | door windows | [7 empty] | 43
x | Robert Campbell | Roofing | [7 empty] | 43
x | Robert Campbell | Gutters | [7 empty] | 45
x | Robert Campbell | Bricks | [7 empty] | 43
x | Robert Campbell | electrical rough in | [7 empty] | 43
x | Robert Campbell | hvac rough in | [7 empty] | 43 | Only move air ducts
x | Robert Campbell | Insulation | [7 empty] | 44 44
x | Robert Campbell | Sheetrock tape and bet texture | [7 empty] | 46
x | Robert Campbell | Paint | [7 empty] | 46
x | Robert Campbell | Tiles | [7 empty] | 46
x | Robert Campbell | Finishing electrical | [7 empty] | 47
x | Robert Campbell | Delivery week | [7 empty] | 48
| Anthony romo | Concrete form | [7 empty] | 38
| Anthony romo | Inground plumbing | [7 empty] | 39 | Inspection
| Anthony romo | Prepour rebar form | [7 empty] | 40
| Anthony romo | Concrete pour | [7 empty] | 41
| Anthony romo | Framing | [7 empty] | 43
| Anthony romo | exterior sheeting | [7 empty] | 44
| Anthony romo | door windows | [7 empty] | 44
| Anthony romo | electrical rough in | [7 empty] | 45
| Anthony romo | plumbing rough in and top out | [7 empty] | 45
| Anthony romo | hvac rough in | [7 empty] | 45
| Anthony romo | Insulation | [7 empty] | 45
| Anthony romo | Sheetrock tape and bet texture | [7 empty] | 41
| Anthony romo | Paint
| Anthony romo | Tiles
| Anthony romo | Cabinets fabrication
| Anthony romo | Cabinets installation
| Anthony romo | Cabinet paint
| Anthony romo | Countertops
| Anthony romo | Flooring
| Anthony romo | Tiles backsplash
| Anthony romo | Finishing electrical | [5 empty] | 200
| Anthony romo | Finish plumbing | [5 empty] | 1000
| Anthony romo | Delivery week

## ROBERT CAMPBELL
CATEGORY | Process Name | SubProcess Name | DEPARTMENT | Week | FOR THIS PROJECT\ | COMMENTS | INSPECTION | Week
GENERAL CONDITIONS | Surveyor Documents |  | PLANING | 38
GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work |  | PLANING | 38
GENERAL CONDITIONS | Permits |  | PLANING | 38
GENERAL CONDITIONS | Post Permits |  | PROJECT MANAGER | 39
GENERAL CONDITIONS | Place Dumpsters |  | PROJECT MANAGER | 39
GENERAL CONDITIONS | DEMO OF STRUCTURE |  | PROJECT MANAGER | 39
SITE WORK | Tree Removal |  | PROJECT MANAGER | 39
SITE WORK | Grading and soil leveling |  | PROJECT MANAGER | 39
SITE WORK | Filling Dirt |  | PROJECT MANAGER | 39
FOUNDATION | Foundation Form and Excavation |  | PROJECT MANAGER | Week 40 | X |  |  | Week Week 40
FOUNDATION | Concrete Piers |  | PROJECT MANAGER | Week 40 | X |  |  | Week Week 40
FOUNDATION | Inground Plumbing |  | PROJECT MANAGER | 41
FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar |  | PROJECT MANAGER | Week 42 | X | INSPECTION | INSPECTION | Week Week 42
FOUNDATION | Concrete Pour |  | PROJECT MANAGER | Week 43 | X | we wait 3 weeks after |  | Week Week 43
GENERAL CONDITIONS | Demo Preparation |  | PROJECT MANAGER | 44 |  | For remodeling
FRAMING | Framing |  | PROJECT MANAGER | Week 44 | X | for remodeling is week 1 |  | Week Week 44
EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) |  | PROJECT MANAGER | Week 44 | X | same week as framing |  | Week Week 44
DOORS AND WINDOWS | Exterior Windows and Doors |  | PROJECT MANAGER | Week 44 | X | same week as framing |  | Week Week 44
EXTERIOR SHEATING | External Water Proofing |  | PROJECT MANAGER | Week 44 | X | same week as framing | INSPECTION | Week Week 44
ROOFING | Roofing |  | PROJECT MANAGER | Week 45 | X | next week after framing |  | Week Week 45
PLUMBING | Plumbing Rough In |  | PROJECT MANAGER | 45 |  | it can be the same week as roofing | INSPECTION
ELECTRICAL | Electrical Rough In |  | PROJECT MANAGER | Week 45 | X |  | INSPECTION | Week Week 45
MECHANICAL | Mechanic (HVAC) Rough in |  | PROJECT MANAGER | Week 45 | X |  | INSPECTION | Week Week 45
ELECTRICAL | Communications and Data Rough In |  | PROJECT MANAGER | 45
OTHERS | Things that goes inside the walls |  | PROJECT MANAGER | 45
INSULATION | Wall Insulation |  | PROJECT MANAGER | Week 45 | X |  | INSPECTION | Week Week 45
INSULATION | Roof Insulation (New Houses |  | PROJECT MANAGER | Week 45 | X |  | INSPECTION | Week Week 45
DRYWALL | Sheet Rock |  | PROJECT MANAGER | Week 46 | X | one week after the insulaiton inspection |  | Week Week 46
DRYWALL | Hardybacker Installation |  | PROJECT MANAGER | Week 46 | X | same as sheet rock |  | Week Week 46
DRYWALL | Wet Areas Water Proofing Redguard |  | PROJECT MANAGER | Week 46 | X | same as sheet rock |  | Week Week 46
DRYWALL | Tape Bet and Texture |  | PROJECT MANAGER | Week 46 | X | same as sheet rock |  | Week Week 46
TILES | Tiles |  | PROJECT MANAGER | Week 47 | X | one week after sheetrock |  | Week Week 47
DOORS AND WINDOWS | Interior Doors Installation |  | PROJECT MANAGER | 47 |  | one week after sheetrock
CARPENTRY | Finish Carpentry |  | PROJECT MANAGER | 47 |  | one week after sheetrock
PAINT | Paint Prep |  | PROJECT MANAGER | Week 48 | X | one week after interior door installation |  | Week Week 48
PAINT | Painting of Walls |  | PROJECT MANAGER | Week 48 | X | Same week as paint prep |  | Week Week 48
PAINT | Painting of Ceiling |  | PROJECT MANAGER | Week 48 | X | Same week as paint prep |  | Week Week 48
FLOORING | Leveling and floating of floors |  | PROJECT MANAGER | Week 48 | X | One week after paiting |  | Week Week 48
FLOORING | Floor Installation |  | PROJECT MANAGER | Week 48 | X | Same week as floor installation |  | Week Week 48
FLOORING | Moldures and Baseboard Installation |  | PROJECT MANAGER | Week 49 | X | One wee after floor installation |  | Week Week 49
PAINT | Trim, baseboards and Mantel Painting |  | PROJECT MANAGER | Week 50 | X | One week after moldures and baseboard installation |  | Week Week 50
CABINETS | Kitchen Cabinets Installation |  | PROJECT MANAGER | 12 |  | After Floor Installation
CABINETS | Vanities Installation |  | PROJECT MANAGER | 50 |  | After Floor Installation
COUNTERTOP | Countertop Intallation |  | PROJECT MANAGER | 51 |  | After Kitcen and Vanities Installation
OTHERS | Smoke Detectors Installation |  | PROJECT MANAGER | 52 |  | After COuntertops Installation
PLUMBING | Fixture Installation |  | PROJECT MANAGER | 52 |  | After COuntertops Installation
ELECTRICAL | Electrodomestic Installation |  | PROJECT MANAGER | 52 |  | After COuntertops Installation
ELECTRICAL | Accesories Installation |  | PROJECT MANAGER | Week 52 | X | After COuntertops Installation |  | Week Week 52
OTHERS | Finishes and Touch ups |  | PROJECT MANAGER | Week 53 | X | After all accesories Installed |  | Week Week 53
OTHERS | DELIVERY |  | PROJECT MANAGER | Week 54 | X | One week after |  | Week Week 54

## Robert Campbel Final
CATEGORY | Process Name | DEPARTMENT | WEEK | Start | End
GENERAL CONDITIONS | Project Site Preparation and Signs | PROJECT MANAGER | Week 38 | 2023-09-18 | 2023-09-24
FOUNDATION | Foundation Form and Excavation | PROJECT MANAGER | Week 38 | 2023-09-18 | 2023-09-24
FOUNDATION | Concrete Piers | PROJECT MANAGER | Week 38 | 2023-09-18 | 2023-09-24
FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar | PROJECT MANAGER | Week 38 | 2023-09-18 | 2023-09-24
FOUNDATION | Concrete Pour | PROJECT MANAGER | Week 38 | 2023-09-18 | 2023-09-24
FRAMING | Framing | PROJECT MANAGER | Week 39 | 2023-09-25 | 2023-10-01
EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) | PROJECT MANAGER | Week 40 | 2023-10-02 | 2023-10-08
DOORS AND WINDOWS | Exterior Windows and Doors | PROJECT MANAGER | Week 40 | 2023-10-02 | 2023-10-08
EXTERIOR SHEATING | External Water Proofing | PROJECT MANAGER | Week 40 | 2023-10-02 | 2023-10-08
ROOFING | Roofing | PROJECT MANAGER | Week 41 | 2023-10-09 | 2023-10-15
ELECTRICAL | Electrical Rough In | PROJECT MANAGER | Week 42 | 2023-10-16 | 2023-10-22
MECHANICAL | Mechanic (HVAC) Rough in | PROJECT MANAGER | Week 42 | 2023-10-16 | 2023-10-22
INSULATION | Wall Insulation | PROJECT MANAGER | Week 42 | 2023-10-16 | 2023-10-22
INSULATION | Roof Insulation (New Houses | PROJECT MANAGER | Week 42 | 2023-10-16 | 2023-10-22
DRYWALL | Sheet Rock | PROJECT MANAGER | Week 42 | 2023-10-16 | 2023-10-22
DRYWALL | Tape Bet and Texture | PROJECT MANAGER | Week 42 | 2023-10-16 | 2023-10-22
TILES | Tiles | PROJECT MANAGER | Week 43 | 2023-10-23 | 2023-10-29
PAINT | Paint Prep | PROJECT MANAGER | Week 43 | 2023-10-23 | 2023-10-29
PAINT | Painting of Walls | PROJECT MANAGER | Week 43 | 2023-10-23 | 2023-10-29
PAINT | Painting of Ceiling | PROJECT MANAGER | Week 43 | 2023-10-23 | 2023-10-29
FLOORING | Leveling and floating of floors | PROJECT MANAGER | Week 44 | 2023-10-30 | 2023-11-05
FLOORING | Floor Installation | PROJECT MANAGER | Week 44 | 2023-10-30 | 2023-11-05
FLOORING | Moldures and Baseboard Installation | PROJECT MANAGER | Week 44 | 2023-10-30 | 2023-11-05
PAINT | Trim, baseboards and Mantel Painting | PROJECT MANAGER | Week 44 | 2023-10-30 | 2023-11-05
ELECTRICAL | Accesories Installation | PROJECT MANAGER | Week 45 | 2023-11-06 | 2023-11-12
OTHERS | Finishes and Touch ups | PROJECT MANAGER | Week 45 | 2023-11-06 | 2023-11-12
OTHERS | DELIVERY | PROJECT MANAGER | Week 45 | 2023-11-06 | 2023-11-12
Formulas:
Start = VLOOKUP([WEEK],aweeks,2,0)
End = VLOOKUP([WEEK],aweeks,3,0)

## weeks
Week number | From Date | To Date
Week 52, 2022 | 2022-12-26 | 2023-01-01
Week 01 | 2023-01-02 | 2023-01-08
Week 02 | 2023-01-09 | 2023-01-15
Week 03 | 2023-01-16 | 2023-01-22
Week 04 | 2023-01-23 | 2023-01-29
Week 05 | 2023-01-30 | 2023-02-05
Week 06 | 2023-02-06 | 2023-02-12
Week 07 | 2023-02-13 | 2023-02-19
Week 08 | 2023-02-20 | 2023-02-26
Week 09 | 2023-02-27 | 2023-03-05
Week 10 | 2023-03-06 | 2023-03-12
Week 11 | 2023-03-13 | 2023-03-19
Week 12 | 2023-03-20 | 2023-03-26
Week 13 | 2023-03-27 | 2023-04-02
Week 14 | 2023-04-03 | 2023-04-09
Week 15 | 2023-04-10 | 2023-04-16
Week 16 | 2023-04-17 | 2023-04-23
Week 17 | 2023-04-24 | 2023-04-30
Week 18 | 2023-05-01 | 2023-05-07
Week 19 | 2023-05-08 | 2023-05-14
Week 20 | 2023-05-15 | 2023-05-21
Week 21 | 2023-05-22 | 2023-05-28
Week 22 | 2023-05-29 | 2023-06-04
Week 23 | 2023-06-05 | 2023-06-11
Week 24 | 2023-06-12 | 2023-06-18
Week 25 | 2023-06-19 | 2023-06-25
Week 26 | 2023-06-26 | 2023-07-02
Week 27 | 2023-07-03 | 2023-07-09
Week 28 | 2023-07-10 | 2023-07-16
Week 29 | 2023-07-17 | 2023-07-23
Week 30 | 2023-07-24 | 2023-07-30
Week 31 | 2023-07-31 | 2023-08-06
Week 32 | 2023-08-07 | 2023-08-13
Week 33 | 2023-08-14 | 2023-08-20
Week 34 | 2023-08-21 | 2023-08-27
Week 35 | 2023-08-28 | 2023-09-03
Week 36 | 2023-09-04 | 2023-09-10
Week 37 | 2023-09-11 | 2023-09-17
Week 38 | 2023-09-18 | 2023-09-24
Week 39 | 2023-09-25 | 2023-10-01
Week 40 | 2023-10-02 | 2023-10-08
Week 41 | 2023-10-09 | 2023-10-15
Week 42 | 2023-10-16 | 2023-10-22
Week 43 | 2023-10-23 | 2023-10-29
Week 44 | 2023-10-30 | 2023-11-05
Week 45 | 2023-11-06 | 2023-11-12
Week 46 | 2023-11-13 | 2023-11-19
Week 47 | 2023-11-20 | 2023-11-26
Week 48 | 2023-11-27 | 2023-12-03
Week 49 | 2023-12-04 | 2023-12-10
Week 50 | 2023-12-11 | 2023-12-17
Week 51 | 2023-12-18 | 2023-12-24
Week 52 | 2023-12-25 | 2023-12-31
Week 01, 2024 | 2024-01-01 | 2024-01-07

## AMANDA
CATEGORY | Process Name | SubProcess Name | DEPARTMENT | WEEK | COMMENTS | INSPECTION
GENERAL CONDITIONS | Surveyor Documents |  | PLANING
GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work |  | PLANING
GENERAL CONDITIONS | Permits |  | PLANING
GENERAL CONDITIONS | Post Permits |  | PROJECT MANAGER | 1
GENERAL CONDITIONS | Place Dumpsters | x | PROJECT MANAGER | 1
GENERAL CONDITIONS | DEMO OF STRUCTURE | x | PROJECT MANAGER | 1
SITE WORK | Tree Removal |  | PROJECT MANAGER | 1
SITE WORK | Grading and soil leveling | x | PROJECT MANAGER | 1
SITE WORK | n-6 |  | PROJECT MANAGER | 1
FOUNDATION | Foundation Form and Excavation | x | PROJECT MANAGER | 2
FOUNDATION | Concrete Piers | x | PROJECT MANAGER | 2
FOUNDATION | Inground Plumbing | x | PROJECT MANAGER | 3
FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar |  | PROJECT MANAGER | 4 | INSPECTION | INSPECTION
FOUNDATION | Concrete Pour | x | PROJECT MANAGER | 5 | we wait 3 weeks after
GENERAL CONDITIONS | Demo Preparation | x | PROJECT MANAGER | 6 | For remodeling
FRAMING | Framing | x | PROJECT MANAGER | 6 | for remodeling is week 1
EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) | x | PROJECT MANAGER | 6 | same week as framing
DOORS AND WINDOWS | Exterior Windows and Doors | x | PROJECT MANAGER | 6 | same week as framing
EXTERIOR SHEATING | External Water Proofing | x | PROJECT MANAGER | 6 | same week as framing | INSPECTION
ROOFING | Roofing | x | PROJECT MANAGER | 7 | next week after framing
PLUMBING | Plumbing Rough In | x | PROJECT MANAGER | 7 | it can be the same week as roofing | INSPECTION
ELECTRICAL | Electrical Rough In | x | PROJECT MANAGER | 7 |  | INSPECTION
MECHANICAL | Mechanic (HVAC) Rough in | x | PROJECT MANAGER | 7 |  | INSPECTION
ELECTRICAL | Communications and Data Rough In |  | PROJECT MANAGER | 7
OTHERS | Things that goes inside the walls |  | PROJECT MANAGER | 7
INSULATION | Wall Insulation | x | PROJECT MANAGER | 7 |  | INSPECTION
INSULATION | Roof Insulation (New Houses | x | PROJECT MANAGER | 7 |  | INSPECTION
DRYWALL | Sheet Rock | x | PROJECT MANAGER | 8 | one week after the insulaiton inspection
DRYWALL | Hardybacker Installation | x | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Wet Areas Water Proofing Redguard | x | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Tape Bet and Texture | x | PROJECT MANAGER | 8 | same as sheet rock
TILES | Tiles | x | PROJECT MANAGER | 9 | one week after sheetrock
DOORS AND WINDOWS | Interior Doors Installation | x | PROJECT MANAGER | 9 | one week after sheetrock
CARPENTRY | Finish Carpentry | x | PROJECT MANAGER | 9 | one week after sheetrock
PAINT | Paint Prep | x | PROJECT MANAGER | 10 | one week after interior door installation
PAINT | Painting of Walls | x | PROJECT MANAGER | 10 | Same week as paint prep
PAINT | Painting of Ceiling | x | PROJECT MANAGER | 10 | Same week as paint prep
FLOORING | Leveling and floating of floors | x | PROJECT MANAGER | 10 | One week after paiting
FLOORING | Floor Installation | x | PROJECT MANAGER | 10 | Same week as floor installation
FLOORING | Moldures and Baseboard Installation | x | PROJECT MANAGER | 11 | One wee after floor installation
PAINT | Trim, baseboards and Mantel Painting | x | PROJECT MANAGER | 12 | One week after moldures and baseboard installation
CABINETS | Kitchen Cabinets Installation | x | PROJECT MANAGER | 12 | After Floor Installation
CABINETS | Vanities Installation | x | PROJECT MANAGER | 12 | After Floor Installation
COUNTERTOP | Countertop Intallation | x | PROJECT MANAGER | 13 | After Kitcen and Vanities Installation
OTHERS | Smoke Detectors Installation | x | PROJECT MANAGER | 14 | After COuntertops Installation
PLUMBING | Fixture Installation | x | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Electrodomestic Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Accesories Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
OTHERS | Finishes and Touch ups | x | PROJECT MANAGER | 15 | After all accesories Installed
OTHERS | DELIVERY | x | PROJECT MANAGER | 16 | One week after

## SUBCONTRACTORS
NAME | PHONE NUMBER | TRADES | CERTIFIED? | LANGUAGES
ANTHONY REYES |  | ELECTRICIAN | YES | ENGLISH ADV
ELISEO |  | PLUMBER / GAS | NO | ENGLISH ADV
SALVADOR SERRANO |  | COUNTERTOPS / STONE | N/A | ENGLISH ADV
FRANSICO LEMUS |  | HVAC | YES | ENGLISH ADV
LUIS DOMINGUEZ |  | TILE | N/A | ENGLISH ADV
BRYAM PORTILLO |  | ALL IN | N/A | ENGLISH ADV
HENRY VILCHEZ |  | CARPENTRY | N/A | SPANISH
JOSE ALFARO ALIAS JOSE ROLANDO |  | ALL IN | N/A | SPANISH WITH SON
HECTOR |  | PAINTING
EFRAIN HERNANDEZ |  | ALL IN | N/A
JAIME |  | ALL IN | N/A
FERNANDO FERRETIS (FZ CARPENTRY) |  | FRAMING AND SIDING |  | ENGLISH ADV
DAVID | 469.475.2180 | BRICKS |  | ENGLISH
JUAN LOPEZ (LOPEZ FOUNDATION) |  | FOUNDATION | YES | ENGLISH
BENITO | 214.926.4898 |  |  | SPANISH
RUBEN | 945.209.1150 | SHOWER GLASS
GILBERTO | 214.475.9351 | BRICKS
STRUCTURAL ENGINEER STEVEN | 214.991.5117 | STRUCTURAL ENGINEER

## NEW
CATEGORY | Process Name | SubProcess Name | DEPARTMENT | WEEK | COMMENTS | INSPECTION
GENERAL CONDITIONS | Surveyor Documents |  | PLANING
GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work |  | PLANING
GENERAL CONDITIONS | Permits |  | PLANING
GENERAL CONDITIONS | Post Permits |  | PROJECT MANAGER | 1
GENERAL CONDITIONS | Place Dumpsters |  | PROJECT MANAGER | 1
GENERAL CONDITIONS | DEMO OF STRUCTURE |  | PROJECT MANAGER | 1
SITE WORK | Tree Removal |  | PROJECT MANAGER | 1
SITE WORK | Grading and soil leveling |  | PROJECT MANAGER | 1
SITE WORK | Filling Dirt |  | PROJECT MANAGER | 1
FOUNDATION | Foundation Form and Excavation |  | PROJECT MANAGER | 2
FOUNDATION | Concrete Piers |  | PROJECT MANAGER | 2
FOUNDATION | Inground Plumbing |  | PROJECT MANAGER | 3
FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar |  | PROJECT MANAGER | 4 | INSPECTION | INSPECTION
FOUNDATION | Concrete Pour |  | PROJECT MANAGER | 5 | we wait 3 weeks after
GENERAL CONDITIONS | Demo Preparation |  | PROJECT MANAGER | 6 | For remodeling
FRAMING | Framing |  | PROJECT MANAGER | 6 | for remodeling is week 1
EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) |  | PROJECT MANAGER | 6 | same week as framing
DOORS AND WINDOWS | Exterior Windows and Doors |  | PROJECT MANAGER | 6 | same week as framing
EXTERIOR SHEATING | External Water Proofing |  | PROJECT MANAGER | 6 | same week as framing | INSPECTION
ROOFING | Roofing |  | PROJECT MANAGER | 7 | next week after framing
PLUMBING | Plumbing Rough In |  | PROJECT MANAGER | 7 | it can be the same week as roofing | INSPECTION
ELECTRICAL | Electrical Rough In |  | PROJECT MANAGER | 7 |  | INSPECTION
MECHANICAL | Mechanic (HVAC) Rough in |  | PROJECT MANAGER | 7 |  | INSPECTION
ELECTRICAL | Communications and Data Rough In |  | PROJECT MANAGER | 7
OTHERS | Things that goes inside the walls |  | PROJECT MANAGER | 7
INSULATION | Wall Insulation |  | PROJECT MANAGER | 7 |  | INSPECTION
INSULATION | Roof Insulation (New Houses |  | PROJECT MANAGER | 7 |  | INSPECTION
DRYWALL | Sheet Rock |  | PROJECT MANAGER | 8 | one week after the insulaiton inspection
DRYWALL | Hardybacker Installation |  | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Wet Areas Water Proofing Redguard |  | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Tape Bet and Texture |  | PROJECT MANAGER | 8 | same as sheet rock
TILES | Tiles |  | PROJECT MANAGER | 9 | one week after sheetrock
DOORS AND WINDOWS | Interior Doors Installation |  | PROJECT MANAGER | 9 | one week after sheetrock
CARPENTRY | Finish Carpentry |  | PROJECT MANAGER | 9 | one week after sheetrock
PAINT | Paint Prep |  | PROJECT MANAGER | 10 | one week after interior door installation
PAINT | Painting of Walls |  | PROJECT MANAGER | 10 | Same week as paint prep
PAINT | Painting of Ceiling |  | PROJECT MANAGER | 10 | Same week as paint prep
FLOORING | Leveling and floating of floors |  | PROJECT MANAGER | 10 | One week after paiting
FLOORING | Floor Installation |  | PROJECT MANAGER | 10 | Same week as floor installation
FLOORING | Moldures and Baseboard Installation |  | PROJECT MANAGER | 11 | One wee after floor installation
PAINT | Trim, baseboards and Mantel Painting |  | PROJECT MANAGER | 12 | One week after moldures and baseboard installation
CABINETS | Kitchen Cabinets Installation |  | PROJECT MANAGER | 12 | After Floor Installation
CABINETS | Vanities Installation |  | PROJECT MANAGER | 12 | After Floor Installation
COUNTERTOP | Countertop Intallation |  | PROJECT MANAGER | 13 | After Kitcen and Vanities Installation
OTHERS | Smoke Detectors Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
PLUMBING | Fixture Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Electrodomestic Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Accesories Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
OTHERS | Finishes and Touch ups |  | PROJECT MANAGER | 15 | After all accesories Installed
OTHERS | DELIVERY |  | PROJECT MANAGER | 16 | One week after

## PATT CRUMPTOM
CATEGORY | Process Name | SubProcess Name | DEPARTMENT | WEEK | COMMENTS | INSPECTION
GENERAL CONDITIONS | Surveyor Documents |  | PLANING
GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work |  | PLANING
GENERAL CONDITIONS | Permits |  | PLANING
GENERAL CONDITIONS | Post Permits |  | PROJECT MANAGER | 1
GENERAL CONDITIONS | Place Dumpsters |  | PROJECT MANAGER | 1
GENERAL CONDITIONS | DEMO OF STRUCTURE |  | PROJECT MANAGER | 1
SITE WORK | Tree Removal |  | PROJECT MANAGER | 1
SITE WORK | Grading and soil leveling |  | PROJECT MANAGER | 1
SITE WORK | Filling Dirt |  | PROJECT MANAGER | 1
FOUNDATION | Foundation Form and Excavation |  | PROJECT MANAGER | 2
FOUNDATION | Concrete Piers |  | PROJECT MANAGER | 2
FOUNDATION | Inground Plumbing |  | PROJECT MANAGER | 3
FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar |  | PROJECT MANAGER | 4 | INSPECTION | INSPECTION
FOUNDATION | Concrete Pour |  | PROJECT MANAGER | 5 | we wait 3 weeks after
GENERAL CONDITIONS | Demo Preparation |  | PROJECT MANAGER | 6 | For remodeling
FRAMING | Framing |  | PROJECT MANAGER | 6 | for remodeling is week 1
EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) |  | PROJECT MANAGER | 6 | same week as framing
DOORS AND WINDOWS | Exterior Windows and Doors |  | PROJECT MANAGER | 6 | same week as framing
EXTERIOR SHEATING | External Water Proofing |  | PROJECT MANAGER | 6 | same week as framing | INSPECTION
ROOFING | Roofing |  | PROJECT MANAGER | 7 | next week after framing
PLUMBING | Plumbing Rough In |  | PROJECT MANAGER | 7 | it can be the same week as roofing | INSPECTION
ELECTRICAL | Electrical Rough In |  | PROJECT MANAGER | 7 |  | INSPECTION
MECHANICAL | Mechanic (HVAC) Rough in |  | PROJECT MANAGER | 7 |  | INSPECTION
ELECTRICAL | Communications and Data Rough In |  | PROJECT MANAGER | 7
OTHERS | Things that goes inside the walls |  | PROJECT MANAGER | 7
INSULATION | Wall Insulation |  | PROJECT MANAGER | 7 |  | INSPECTION
INSULATION | Roof Insulation (New Houses |  | PROJECT MANAGER | 7 |  | INSPECTION
DRYWALL | Sheet Rock |  | PROJECT MANAGER | 8 | one week after the insulaiton inspection
DRYWALL | Hardybacker Installation |  | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Wet Areas Water Proofing Redguard |  | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Tape Bet and Texture |  | PROJECT MANAGER | 8 | same as sheet rock
TILES | Tiles |  | PROJECT MANAGER | 9 | one week after sheetrock
DOORS AND WINDOWS | Interior Doors Installation |  | PROJECT MANAGER | 9 | one week after sheetrock
CARPENTRY | Finish Carpentry |  | PROJECT MANAGER | 9 | one week after sheetrock
PAINT | Paint Prep |  | PROJECT MANAGER | 10 | one week after interior door installation
PAINT | Painting of Walls |  | PROJECT MANAGER | 10 | Same week as paint prep
PAINT | Painting of Ceiling |  | PROJECT MANAGER | 10 | Same week as paint prep
FLOORING | Leveling and floating of floors |  | PROJECT MANAGER | 10 | One week after paiting
FLOORING | Floor Installation |  | PROJECT MANAGER | 10 | Same week as floor installation
FLOORING | Moldures and Baseboard Installation |  | PROJECT MANAGER | 11 | One wee after floor installation
PAINT | Trim, baseboards and Mantel Painting |  | PROJECT MANAGER | 12 | One week after moldures and baseboard installation
CABINETS | Kitchen Cabinets Installation |  | PROJECT MANAGER | 12 | After Floor Installation
CABINETS | Vanities Installation |  | PROJECT MANAGER | 12 | After Floor Installation
COUNTERTOP | Countertop Intallation |  | PROJECT MANAGER | 13 | After Kitcen and Vanities Installation
OTHERS | Smoke Detectors Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
PLUMBING | Fixture Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Electrodomestic Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Accesories Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
OTHERS | Finishes and Touch ups |  | PROJECT MANAGER | 15 | After all accesories Installed
OTHERS | DELIVERY |  | PROJECT MANAGER | 16 | One week after

## Sheet5
CATEGORY | Process Name | SubProcess Name | DEPARTMENT | WEEK | COMMENTS | INSPECTION
GENERAL CONDITIONS | Surveyor Documents | 0 | PLANING
GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work | X | PLANING
GENERAL CONDITIONS | Permits | X | PLANING
GENERAL CONDITIONS | Post Permits | X | PROJECT MANAGER | 1
GENERAL CONDITIONS |  |  | PROJECT MANAGER | 1
GENERAL CONDITIONS | DEMO OF STRUCTURE | X | PROJECT MANAGER | 1
SITE WORK | Tree Removal | 0 | PROJECT MANAGER | 1
SITE WORK | Grading and soil leveling | 0 | PROJECT MANAGER | 1
SITE WORK | Filling Dirt | 0 | PROJECT MANAGER | 1
FOUNDATION | Foundation Form and Excavation | X | PROJECT MANAGER | 2
FOUNDATION | Concrete Piers |  | PROJECT MANAGER | 2
FOUNDATION | Inground Plumbing | X | PROJECT MANAGER | 3
FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar | X | PROJECT MANAGER | 4 | INSPECTION | INSPECTION
FOUNDATION | Concrete Pour | X | PROJECT MANAGER | 5 | we wait 3 weeks after
GENERAL CONDITIONS | Demo Preparation | X | PROJECT MANAGER | 6 | For remodeling
FRAMING | Framing Structure | X | PROJECT MANAGER | 6 | for remodeling is week 1
FRAMING | Framing Outdoors (patio / backyard) | x
EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) | X | PROJECT MANAGER | 6 | same week as framing
DOORS AND WINDOWS | Exterior Windows and Doors | X | PROJECT MANAGER | 6 | same week as framing
EXTERIOR SHEATING | External Water Proofing | X | PROJECT MANAGER | 6 | same week as framing | INSPECTION
ROOFING | Roofing | X | PROJECT MANAGER | 7 | next week after framing
PLUMBING | Plumbing Rough In | X | PROJECT MANAGER | 7 | it can be the same week as roofing | INSPECTION
ELECTRICAL | Electrical Rough In | X | PROJECT MANAGER | 7 |  | INSPECTION
MECHANICAL | Mechanic (HVAC) Rough in | X | PROJECT MANAGER | 7 |  | INSPECTION
ELECTRICAL | Communications and Data Rough In | 0 | PROJECT MANAGER | 7
OTHERS | Things that goes inside the walls |  | PROJECT MANAGER | 7
INSULATION | Wall Insulation | X | PROJECT MANAGER | 7 |  | INSPECTION
INSULATION | Roof Insulation (New Houses | X | PROJECT MANAGER | 7 |  | INSPECTION
DRYWALL | Sheet Rock | X | PROJECT MANAGER | 8 | one week after the insulaiton inspection
DRYWALL | Hardybacker Installation | X | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Wet Areas Water Proofing Redguard | X | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Tape Bet and Texture | X | PROJECT MANAGER | 8 | same as sheet rock
TILES | Tiles | X | PROJECT MANAGER | 9 | one week after sheetrock
DOORS AND WINDOWS | Interior Doors Installation | X | PROJECT MANAGER | 9 | one week after sheetrock
CARPENTRY | Finish Carpentry | X | PROJECT MANAGER | 9 | one week after sheetrock
PAINT | Paint Prep | X | PROJECT MANAGER | 10 | one week after interior door installation
PAINT | Painting of Walls | X | PROJECT MANAGER | 10 | Same week as paint prep
PAINT | Painting of Ceiling | X | PROJECT MANAGER | 10 | Same week as paint prep
FLOORING | Leveling and floating of floors | X | PROJECT MANAGER | 10 | One week after paiting
FLOORING | Floor Installation | X | PROJECT MANAGER | 10 | Same week as floor installation
FLOORING | Moldures and Baseboard Installation | X | PROJECT MANAGER | 11 | One wee after floor installation
PAINT | Trim, baseboards and Mantel Painting | X | PROJECT MANAGER | 12 | One week after moldures and baseboard installation
CABINETS | Kitchen Cabinets Installation | X | PROJECT MANAGER | 12 | After Floor Installation
CABINETS | Vanities Installation | X | PROJECT MANAGER | 12 | After Floor Installation
COUNTERTOP | Countertop Intallation | X | PROJECT MANAGER | 13 | After Kitcen and Vanities Installation
OTHERS | Smoke Detectors Installation | X | PROJECT MANAGER | 14 | After COuntertops Installation
PLUMBING | Fixture Installation | X | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Electrodomestic Installation | X | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Accesories Installation | X | PROJECT MANAGER | 14 | After COuntertops Installation
OTHERS | Finishes and Touch ups | X | PROJECT MANAGER | 15 | After all accesories Installed
OTHERS | DELIVERY | X | PROJECT MANAGER | 16 | One week after

## Sheet6
CATEGORY | Process Name | SubProcess Name | DEPARTMENT | WEEK | COMMENTS | INSPECTION
GENERAL CONDITIONS | Surveyor Documents | 0 | PLANING
GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work | X | PLANING
GENERAL CONDITIONS | Permits | X | PLANING
GENERAL CONDITIONS | Post Permits | X | PROJECT MANAGER | 1
GENERAL CONDITIONS |  |  | PROJECT MANAGER | 1
GENERAL CONDITIONS | DEMO OF STRUCTURE | X | PROJECT MANAGER | 1
SITE WORK | Tree Removal | 0 | PROJECT MANAGER | 1
SITE WORK | Grading and soil leveling | 0 | PROJECT MANAGER | 1
SITE WORK | Filling Dirt | 0 | PROJECT MANAGER | 1
FOUNDATION | Foundation Form and Excavation | X | PROJECT MANAGER | 2
FOUNDATION | Concrete Piers |  | PROJECT MANAGER | 2
FOUNDATION | Inground Plumbing | X | PROJECT MANAGER | 3
FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar | X | PROJECT MANAGER | 4 | INSPECTION | INSPECTION
FOUNDATION | Concrete Pour | X | PROJECT MANAGER | 5 | we wait 3 weeks after
GENERAL CONDITIONS | Demo Preparation | X | PROJECT MANAGER | 6 | For remodeling
FRAMING | Framing Structure | X | PROJECT MANAGER | 6 | for remodeling is week 1
FRAMING | Framing Outdoors (patio / backyard) | x
EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) | X | PROJECT MANAGER | 6 | same week as framing
DOORS AND WINDOWS | Exterior Windows and Doors | X | PROJECT MANAGER | 6 | same week as framing
EXTERIOR SHEATING | External Water Proofing | X | PROJECT MANAGER | 6 | same week as framing | INSPECTION
ROOFING | Roofing | X | PROJECT MANAGER | 7 | next week after framing
PLUMBING | Plumbing Rough In | X | PROJECT MANAGER | 7 | it can be the same week as roofing | INSPECTION
ELECTRICAL | Electrical Rough In | X | PROJECT MANAGER | 7 |  | INSPECTION
MECHANICAL | Mechanic (HVAC) Rough in | X | PROJECT MANAGER | 7 |  | INSPECTION
ELECTRICAL | Communications and Data Rough In | 0 | PROJECT MANAGER | 7
OTHERS | Things that goes inside the walls |  | PROJECT MANAGER | 7
INSULATION | Wall Insulation | X | PROJECT MANAGER | 7 |  | INSPECTION
INSULATION | Roof Insulation (New Houses | X | PROJECT MANAGER | 7 |  | INSPECTION
DRYWALL | Sheet Rock | X | PROJECT MANAGER | 8 | one week after the insulaiton inspection
DRYWALL | Hardybacker Installation | X | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Wet Areas Water Proofing Redguard | X | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Tape Bet and Texture | X | PROJECT MANAGER | 8 | same as sheet rock
TILES | Tiles | X | PROJECT MANAGER | 9 | one week after sheetrock
DOORS AND WINDOWS | Interior Doors Installation | X | PROJECT MANAGER | 9 | one week after sheetrock
CARPENTRY | Finish Carpentry | X | PROJECT MANAGER | 9 | one week after sheetrock
PAINT | Paint Prep | X | PROJECT MANAGER | 10 | one week after interior door installation
PAINT | Painting of Walls | X | PROJECT MANAGER | 10 | Same week as paint prep
PAINT | Painting of Ceiling | X | PROJECT MANAGER | 10 | Same week as paint prep
FLOORING | Leveling and floating of floors | X | PROJECT MANAGER | 10 | One week after paiting
FLOORING | Floor Installation | X | PROJECT MANAGER | 10 | Same week as floor installation
FLOORING | Moldures and Baseboard Installation | X | PROJECT MANAGER | 11 | One wee after floor installation
PAINT | Trim, baseboards and Mantel Painting | X | PROJECT MANAGER | 12 | One week after moldures and baseboard installation
CABINETS | Kitchen Cabinets Installation | X | PROJECT MANAGER | 12 | After Floor Installation
CABINETS | Vanities Installation | X | PROJECT MANAGER | 12 | After Floor Installation
COUNTERTOP | Countertop Intallation | X | PROJECT MANAGER | 13 | After Kitcen and Vanities Installation
OTHERS | Smoke Detectors Installation | X | PROJECT MANAGER | 14 | After COuntertops Installation
PLUMBING | Fixture Installation | X | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Electrodomestic Installation | X | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Accesories Installation | X | PROJECT MANAGER | 14 | After COuntertops Installation
OTHERS | Finishes and Touch ups | X | PROJECT MANAGER | 15 | After all accesories Installed
OTHERS | DELIVERY | X | PROJECT MANAGER | 16 | One week after
espesor del slab
profundidad
tipo de varilla
tipo de cemento. Camion o de Home Depot

## Sheet4
IF THERE IS DEMO THEN THERE WILL BE DUMPSTER

## ADDITION
CATEGORY | Process Name | SubProcess Name | DEPARTMENT | WEEK | COMMENTS | INSPECTION | START WEEK
GENERAL CONDITIONS | Surveyor Documents |  | PLANING
GENERAL CONDITIONS | Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work |  | PLANING
GENERAL CONDITIONS | Permits |  | PLANING
GENERAL CONDITIONS | Post Permits |  | PROJECT MANAGER | 1
GENERAL CONDITIONS | Surveyor Property Delimitation |  | PROJECT MANAGER | 1
GENERAL CONDITIONS | DEMO OF STRUCTURE |  | PROJECT MANAGER | 1
SITE WORK | Tree Removal |  | PROJECT MANAGER | 1
SITE WORK | Grading and soil leveling |  | PROJECT MANAGER | 1
SITE WORK | Filling Dirt |  | PROJECT MANAGER | 1
FOUNDATION | Foundation Form and Excavation |  | PROJECT MANAGER | 2
FOUNDATION | Concrete Piers |  | PROJECT MANAGER | 2
FOUNDATION | Inground Plumbing |  | PROJECT MANAGER | 3
FOUNDATION | Trenching and Rebar Post Tension or Vanilla Rebar |  | PROJECT MANAGER | 4 | INSPECTION | INSPECTION
FOUNDATION | Concrete Pour |  | PROJECT MANAGER | 5 | we wait 3 weeks after
GENERAL CONDITIONS | Demo Preparation |  | PROJECT MANAGER | 6 | For remodeling
FRAMING | Framing |  | PROJECT MANAGER | 6 | for remodeling is week 1
EXTERIOR SHEATING | Exterior Sheating (Walls and Roof) |  | PROJECT MANAGER | 6 | same week as framing
DOORS AND WINDOWS | Exterior Windows and Doors |  | PROJECT MANAGER | 6 | same week as framing
EXTERIOR SHEATING | External Water Proofing |  | PROJECT MANAGER | 6 | same week as framing | INSPECTION
ROOFING | Roofing |  | PROJECT MANAGER | 7 | next week after framing
PLUMBING | Plumbing |  | PROJECT MANAGER | 7 | it can be the same week as roofing | INSPECTION
ELECTRICAL | Electrical |  | PROJECT MANAGER | 7 | it can be the same week as roofing | INSPECTION
MECHANICAL | Mechanic (HVAC) |  | PROJECT MANAGER | 7 | it can be the same week as roofing | INSPECTION
ELECTRICAL | Communications and Data |  | PROJECT MANAGER | 7 | it can be the same week as roofing
OTHERS | Things that goes inside the walls |  | PROJECT MANAGER | 7 | it can be the same week as roofing
INSULATION | Wall Insulation |  | PROJECT MANAGER | 7 | it can be the same week as roofing | INSPECTION
INSULATION | Roof Insulation (New Houses |  | PROJECT MANAGER | 7 | it can be the same week as roofing | INSPECTION
DRYWALL | Sheet Rock |  | PROJECT MANAGER | 8 | one week after the insulaiton inspection
DRYWALL | Hardybacker Installation |  | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Wet Areas Water Proofing Redguard |  | PROJECT MANAGER | 8 | same as sheet rock
DRYWALL | Tape Bet and Texture |  | PROJECT MANAGER | 8 | same as sheet rock
TILES | Tiles |  | PROJECT MANAGER | 9 | one week after sheetrock
DOORS AND WINDOWS | Interior Doors Installation |  | PROJECT MANAGER | 9 | one week after sheetrock
CARPENTRY | Finish Carpentry |  | PROJECT MANAGER | 9 | one week after sheetrock
PAINT | Paint Prep |  | PROJECT MANAGER | 10 | one week after sheetrock
PAINT | Painting of Walls |  | PROJECT MANAGER | 10 | Same week as paint prep
PAINT | Painting of Ceiling |  | PROJECT MANAGER | 10 | Same week as paint prep
FLOORING | Leveling and floating of floors |  | PROJECT MANAGER | 10 | One week after paiting
FLOORING | Floor Installation |  | PROJECT MANAGER | 10 | Same week as floor installation
FLOORING | Moldures and Baseboard Installation |  | PROJECT MANAGER | 11 | One wee after floor installation
PAINT | Trim, baseboards and Mantel Painting |  | PROJECT MANAGER | 12 | One week after moldures and baseboard installation
CABINETS | Kitchen Cabinets Installation |  | PROJECT MANAGER | 12 | After Floor Installation
CABINETS | Vanities Installation |  | PROJECT MANAGER | 12 | After Floor Installation
COUNTERTOP | Countertop Intallation |  | PROJECT MANAGER | 13 | After Kitchen and Vanities Installation
OTHERS | Smoke Detectors Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
PLUMBING | Fixture Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Electrodomestic Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
ELECTRICAL | Accesories Installation |  | PROJECT MANAGER | 14 | After COuntertops Installation
OTHERS | Finishes and Touch ups |  | PROJECT MANAGER | 15 | After all accesories Installed
OTHERS | DELIVERY |  | PROJECT MANAGER | 16 | One week after
|  |  | Week Start | 1
1-00 GENERAL CONDITIONS TOTAL | 1
2.00 SITE WORK TOTALS | 1
3.00 FOUNDATION TOTAL | 2
4.00 ELECTRICAL | 4
5.00 PLUMBING | 4
6.0 FRAMING | 3
7.0 EXTERIOR SHEATING | 3
8.0 ROOFING | 4
9.0 DOORS AND WINDOWS | 3
10.0 PAINT | 5
11.0 INSULATION | 4
12.0 FLOORING | 6
13.0 STUCCO / SIDING | 3
14.0 HVAC | 4
15.0 TILES | 5
17.0 GLASS | 7
18.0 CABINETS | 7
19.0 COUNTERTOPS | 8
20.0 DRYWALL | 4