## MAIN PROCESS
TRADE	Task	Status	Sub	Start week	End week	Obs	Actual Date	End Date	Negotiated	Ball Park	Budget	Cost	WO	38
GENERAL CONDITIONS	Surveyor Documents		PLANING	38
GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work		PLANING	38
GENERAL CONDITIONS	Permits		PLANING	38
GENERAL CONDITIONS	Post Permits		PROJECT MANAGER	39
GENERAL CONDITIONS	Place Dumpsters		PROJECT MANAGER	39
GENERAL CONDITIONS	DEMO OF STRUCTURE		PROJECT MANAGER	39
SITE WORK	Tree Removal		PROJECT MANAGER	39
SITE WORK	Grading and soil leveling		PROJECT MANAGER	39
SITE WORK	Filling Dirt		PROJECT MANAGER	39
FOUNDATION	Foundation Form and Excavation		PROJECT MANAGER	40
FOUNDATION	Concrete Piers		PROJECT MANAGER	40
PLUMBING	Inground Plumbing		PROJECT MANAGER	41
FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar		PROJECT MANAGER	42		INSPECTION	INSPECTION
FOUNDATION	Concrete Pour		PROJECT MANAGER	43		we wait 3 weeks after
GENERAL CONDITIONS	Demo Preparation		PROJECT MANAGER	44		For remodeling
FRAMING	Framing		PROJECT MANAGER	44		for remodeling is week 1
EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)		PROJECT MANAGER	44		same week as framing
DOORS AND WINDOWS	Exterior Windows and Doors		PROJECT MANAGER	44		same week as framing
EXTERIOR SHEATING	External Water Proofing		PROJECT MANAGER	44		same week as framing	INSPECTION
SIDING / BRICK	Siding or bricl		PROJECT MANAGER	45		next week after framing
ROOFING	Roofing		PROJECT MANAGER	45		next week after framing
PLUMBING	Plumbing Rough In and Top out		PROJECT MANAGER	45		it can be the same week as roofing	INSPECTION
ELECTRICAL	Electrical Rough In		PROJECT MANAGER	45		it can be the same week as roofing	INSPECTION
MECHANICAL	Mechanic (HVAC) Rough in		PROJECT MANAGER	45		it can be the same week as roofing	INSPECTION
ELECTRICAL	Communications and Data Rough In		PROJECT MANAGER	45		it can be the same week as roofing
OTHERS	Things that goes inside the walls		PROJECT MANAGER	45		it can be the same week as roofing
INSULATION	Wall Insulation		PROJECT MANAGER	45		one week after rought ins	INSPECTION
INSULATION	Roof Insulation (New Houses		PROJECT MANAGER	45		At anymoment after rought ins	INSPECTION
DRYWALL	Sheet Rock		PROJECT MANAGER	46		one week after the insulaiton inspection
DRYWALL	Hardybacker Installation		PROJECT MANAGER	46		same as sheet rock
DRYWALL	Wet Areas Water Proofing Redguard		PROJECT MANAGER	46		same as sheet rock
DRYWALL	Tape Bet and Texture		PROJECT MANAGER	46		same as sheet rock
TILES	Tiles		PROJECT MANAGER	47		one week after sheetrock
DOORS AND WINDOWS	Interior Doors Installation		PROJECT MANAGER	47		one week after sheetrock
CARPENTRY	Finish Carpentry		PROJECT MANAGER	47		one week after sheetrock
PAINT	Paint		PROJECT MANAGER	48		one week after interior door installation
PAINT	Painting of Walls		PROJECT MANAGER	48		Same week as paint prep
PAINT	Painting of Ceiling		PROJECT MANAGER	48		Same week as paint prep
FLOORING	Leveling and floating of floors		PROJECT MANAGER	48		One week after paiting
FLOORING	Floor Installation		PROJECT MANAGER	48		Same week as floor installation
FLOORING	Moldures and Baseboard Installation		PROJECT MANAGER	49		One wee after floor installation
FLOORING	Trim, baseboards and Mantel Painting		PROJECT MANAGER	50		One week after moldures and baseboard installation
CABINETS	Kitchen Cabinets Fabrication		PROJECT MANAGER	46		At any moment after drywall
CABINETS	Vanities Cabinets Fabrication		PROJECT MANAGER	46		At any moment after drywall
CABINETS	Kitchen Cabinets Installation		PROJECT MANAGER	12		After Floor Installation
CABINETS	Vanities Installation		PROJECT MANAGER	50		After Floor Installation
COUNTERTOP	Countertop Intallation		PROJECT MANAGER	51		After Kitcen and Vanities Installation
TILES	Tiles Backsplash		PROJECT MANAGER	52		After COuntertops Installation
OTHERS	Smoke Detectors Installation		PROJECT MANAGER	52		After COuntertops Installation
ROOFING	Gutters		PROJECT MANAGER	52		After COuntertops Installation
GLASS	Shower Glass, Mirrors and other accesories		PROJECT MANAGER	52		After COuntertops Installation
PLUMBING	Fixture Installation		PROJECT MANAGER	52		After COuntertops Installation
ELECTRICAL	Accesories Installation		PROJECT MANAGER	#REF!		After COuntertops Installation
OTHERS	Finishes and Touch ups		PROJECT MANAGER	#REF!		After all accesories Installed
OTHERS	DELIVERY		PROJECT MANAGER	#REF!		One week after

## SPECIFICATIONS
ELECTRICAL	OVEN	60 AMP	60/3
ELECTRICAL	DISHWASHER	20AMP	12/2
ELECTRICAL	COOKTOP	60 AMP	60/3
ELECTRICAL	COOKTOP	40 AMP	10/3
ELECTRICAL	COOKTOP	50AMP	8/3
ELECTRICAL	REFRIGERATOR	20AMP	12/2

## Dave barron
CATEGORY	Process Name	SubProcess Name	DEPARTMENT	WEEK	COMMENTS	INSPECTION		START WEEK	38
GENERAL CONDITIONS	Surveyor Documents		PLANING	38
GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work		PLANING	38
GENERAL CONDITIONS	Permits		PLANING	38
GENERAL CONDITIONS	Post Permits		PROJECT MANAGER	39
GENERAL CONDITIONS	Place Dumpsters		PROJECT MANAGER	39
GENERAL CONDITIONS	DEMO OF STRUCTURE		PROJECT MANAGER	39
SITE WORK	Tree Removal		PROJECT MANAGER	39
SITE WORK	Grading and soil leveling		PROJECT MANAGER	39
SITE WORK	Filling Dirt		PROJECT MANAGER	39
FOUNDATION	Foundation Form and Excavation		PROJECT MANAGER	40
FOUNDATION	Concrete Piers		PROJECT MANAGER	40
FOUNDATION	Inground Plumbing		PROJECT MANAGER	41
FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar		PROJECT MANAGER	42	INSPECTION	INSPECTION
FOUNDATION	Concrete Pour		PROJECT MANAGER	43	we wait 3 weeks after
GENERAL CONDITIONS	Demo Preparation		PROJECT MANAGER	44	For remodeling
FRAMING	Framing		PROJECT MANAGER	44	for remodeling is week 1
EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)		PROJECT MANAGER	44	same week as framing
DOORS AND WINDOWS	Exterior Windows and Doors		PROJECT MANAGER	44	same week as framing
EXTERIOR SHEATING	External Water Proofing		PROJECT MANAGER	44	same week as framing	INSPECTION
ROOFING	Roofing		PROJECT MANAGER	45	next week after framing
PLUMBING	Plumbing Rough In		PROJECT MANAGER	45	it can be the same week as roofing	INSPECTION
ELECTRICAL	Electrical Rough In		PROJECT MANAGER	45		INSPECTION
MECHANICAL	Mechanic (HVAC) Rough in		PROJECT MANAGER	45		INSPECTION
ELECTRICAL	Communications and Data Rough In		PROJECT MANAGER	45
OTHERS	Things that goes inside the walls		PROJECT MANAGER	45
INSULATION	Wall Insulation		PROJECT MANAGER	45		INSPECTION
INSULATION	Roof Insulation (New Houses		PROJECT MANAGER	45		INSPECTION
DRYWALL	Sheet Rock		PROJECT MANAGER	46	one week after the insulaiton inspection
DRYWALL	Hardybacker Installation		PROJECT MANAGER	46	same as sheet rock
DRYWALL	Wet Areas Water Proofing Redguard		PROJECT MANAGER	46	same as sheet rock
DRYWALL	Tape Bet and Texture		PROJECT MANAGER	46	same as sheet rock
TILES	Tiles		PROJECT MANAGER	47	one week after sheetrock
DOORS AND WINDOWS	Interior Doors Installation		PROJECT MANAGER	47	one week after sheetrock
CARPENTRY	Finish Carpentry		PROJECT MANAGER	47	one week after sheetrock
PAINT	Paint Prep		PROJECT MANAGER	48	one week after interior door installation
PAINT	Painting of Walls		PROJECT MANAGER	48	Same week as paint prep
PAINT	Painting of Ceiling		PROJECT MANAGER	48	Same week as paint prep
FLOORING	Leveling and floating of floors		PROJECT MANAGER	48	One week after paiting
FLOORING	Floor Installation		PROJECT MANAGER	48	Same week as floor installation
FLOORING	Moldures and Baseboard Installation		PROJECT MANAGER	49	One wee after floor installation
PAINT	Trim, baseboards and Mantel Painting		PROJECT MANAGER	50	One week after moldures and baseboard installation
CABINETS	Kitchen Cabinets Installation		PROJECT MANAGER	12	After Floor Installation
CABINETS	Vanities Installation		PROJECT MANAGER	50	After Floor Installation
COUNTERTOP	Countertop Intallation		PROJECT MANAGER	51	After Kitcen and Vanities Installation
OTHERS	Smoke Detectors Installation		PROJECT MANAGER	52	After COuntertops Installation
PLUMBING	Fixture Installation		PROJECT MANAGER	52	After COuntertops Installation
ELECTRICAL	Electrodomestic Installation		PROJECT MANAGER	52	After COuntertops Installation
ELECTRICAL	Accesories Installation		PROJECT MANAGER	52	After COuntertops Installation
OTHERS	Finishes and Touch ups		PROJECT MANAGER	53	After all accesories Installed
OTHERS	DELIVERY		PROJECT MANAGER	54	One week after

Daniel Powell	concreto				39
Daniel Powell	Framing				42
Daniel Powell	exterior sheeting				43
Daniel Powell	door windows				43
Daniel Powell	Roofing				43
Daniel Powell	Gutters				45
Daniel Powell	Bricks				43
Daniel Powell	electrical rough in				43
Daniel Powell	plumbing rough in and top out				43
Daniel Powell	hvac rough in				43
Daniel Powell	Insulation				45
Daniel Powell	Sheetrock tape and bet texture				46
Daniel Powell	Paint				46
Daniel Powell	Tiles				46
Daniel Powell	Finishing electrical				47
Daniel Powell	Finish plumbing				47
Daniel Powell	Other touch ups				48

## TASK SCHEDULED
WO	CUSTOMER NAME	CUSTOMER ADDRESS	CODE	DESCRIPTION	UNIT / WEEK	QUANTITY	TYPE	BUDGET
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	Inground Plumbing	WEEK	39	TASK
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	Plumbing Rough In & Top out	WEEK	46	TASK
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	Fixture Installation	WEEK	51	TASK
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	LABOR PER SERVICE - ADDITION	UNIT	3	LABOR	1,125.00
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	LABOR PER SERVICE -REMOVE AND REPLACE	UNIT	6	LABOR	540.00
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	LABOR PER SERVICE - INSTALL	UNIT	1	LABOR	60.00
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	BUILD UP SHOWER BASE	SQ FT	28	LABOR	770.00
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	SHOWER FAUCET - BG	UNIT	1	MATERIAL	275.00
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	BATHROOM FAUCET - BG	UNIT	2	MATERIAL	250.00
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	SINK - BG	UNIT	1	MATERIAL	200.00
PALO001	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PLUMBING	ROMAN FAUCET - BG	UNIT	1	MATERIAL	100.00
PALO0011	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PAINT	LABOR - NEW CONSTRUCTION (BUILDING SQ FT)	SQ FT	625 '	LABOR	1,312.50
PALO0011	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PAINT	LABOR - TRIM PAINT	LNFT	92 '	LABOR	66.24
PALO0011	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PAINT	LABOR - FRONT DOOR PAINT	EA		LABOR	0.00
PALO0011	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PAINT	MATERIAL - WALL PAINT	UNIT	2 '	MATERIAL	210.00
PALO0011	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PAINT	MATERIAL - CEILING PAINT	UNIT	1 '	MATERIAL	105.00
PALO0011	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PAINT	MATERIAL - TRIM PAINT	UNIT	1 '	MATERIAL	51.00
PALO0011	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PAINT	OTHER MATERIALS	GLOBAL	1 '	MATERIAL	348.00
PALO002	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FOUNDATION	Foundation Form and Excavation	WEEK	38	TASK
PALO002	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FOUNDATION	Concrete Piers	WEEK	39	TASK
PALO002	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar	WEEK	40	TASK
PALO002	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FOUNDATION	Concrete Pour	WEEK	41	TASK
PALO002	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FOUNDATION TOTAL	FORM WORK	SQ FT	204	ALL INCLUDED	128.52
PALO002	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FOUNDATION TOTAL	PIERS	UNIT	12	ALL INCLUDED	2,688.00
PALO002	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FOUNDATION TOTAL	GRADE BEAMS / FOOTINGS	LF	99	ALL INCLUDED	519.75
PALO002	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FOUNDATION TOTAL	CONCRETE SLAB	SQ FT	204	ALL INCLUDED	1,356.60
PALO003	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ELECTRICAL	Electrical Rough In	WEEK	46	TASK
PALO003	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ELECTRICAL	HVAC ROugh In	WEEK	46	TASK
PALO003	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ELECTRICAL	Accesories and Fixture Installation	WEEK	51	TASK
PALO003	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ELECTRICAL	LABOR - ADDITION - WIRING	SQ FT	204 '	LABOR	1,020.00
PALO003	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ELECTRICAL	LED RECESSED LIGHT	UNIT	15	MATERIAL	187.50
PALO003	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ELECTRICAL	DECORATIVE LIGHT FIXTURE	UNIT	2	MATERIAL	50.00
PALO003	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ELECTRICAL	CEILING EXHAUST FAN, REF. M.E.P	UNIT	2	MATERIAL	350.00
PALO003	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ELECTRICAL	ELECTRICAL - MINOR	UNIT	11	LABOR	1,375.00
PALO003	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ELECTRICAL	EXAUST FAN	UNIT	1	MATERIAL	30.00
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FRAMING	Framing	WEEK	43	TASK
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)	WEEK	44	TASK
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DOORS AND WINDOWS	Exterior Windows and Doors	WEEK	44	TASK
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	EXTERIOR SHEATING	External Water Proofing	WEEK	44	TASK
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FRAMING	NEW CONSTRUCTION FRAMING - LABOR	SF	308	LABOR	1,101.10
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FRAMING	NEW CONSTRUCTION FRAMING - MATERIAL	SF	338	LABOR	2,230.80
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FRAMING	ADDITION REFRAME - STRUCTURAL - LABOR	SF	204	LABOR	1,065.90
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FRAMING	ADDITION REFRAME - STRUCTURAL - MATERIAL	SF	225	LABOR	1,485.00
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	EXTERIOR SHEATING	LABOR (SURFACE SQ FT) - SHEATING	SQ FT	232	LABOR	208.80
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	EXTERIOR SHEATING	ZIP SYSTEM 4FT X 8 FT - ROOF SHEATING	UNIT	24	MATERIAL	348.48
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	EXTERIOR SHEATING	ZIP SYSTEM 4FT X 8 FT - WALL SHEATING	UNIT	8	MATERIAL	116.16
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	EXTERIOR SHEATING	ZIP SYSTEM TAPE X 90 FT	UNIT	4	MATERIAL	59.40
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DOORS AND WINDOWS	INTERIOR MDP PREFAB DOORS 80¨	UN	3	MATERIAL	648.00
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DOORS AND WINDOWS	POCKET DOOR	UN	1	MATERIAL	510.00
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DOORS AND WINDOWS	VYNIL WINDOWS - NEW CONSTRUCTION	UN	2	MATERIAL	816.00
PALO004	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DOORS AND WINDOWS	VYNIL WINDOWS - REMOVE AND REPLACE	UN	1	LABOR	588.00
PALO005	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	SIDING / BRICK	Siding or bricks	WEEK	46	TASK
PALO005	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	STUCCO / SIDING	LABOR - WALL - BRICKS	SQ FT	328 '	LABOR	885.60
PALO005	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	STUCCO / SIDING	MATERIALS - WALL - BRICKS	SQ FT	360 '	MATERIAL	1,188.00
PALO006	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ROOFING	Roofing	WEEK	45	TASK
PALO006	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ROOFING	LABOR (CONSTRUCTION SQ FT) - SHINGLES	SQ FT	771	ALL INCLUDED	763.29
PALO006	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ROOFING	SHINGLES	UNIT	9	ALL INCLUDED	504.90
PALO006	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ROOFING	ROOF PROTECTOR UNDERLAYMENT	SQ FT	771	ALL INCLUDED	339.24
PALO006	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ROOFING	GALVANIZED FLASHING	UNIT	3	ALL INCLUDED	462.00
PALO006	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ROOFING	GAF WEATHERWATCH 100 LN FT (200 SQFT)	UNIT	3	ALL INCLUDED	231.00
PALO006	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ROOFING	GAF PRO START 120 LN FT - STARTER TRIP SHINGLES	UNIT	6	ALL INCLUDED	145.13
PALO006	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ROOFING	COBRA EXHAUST VENT - RIDGE VENT 20 LN FT	UNIT	1	ALL INCLUDED	30.25
PALO007	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	INSULATION	Wall Insulation	WEEK	47	TASK
PALO007	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	INSULATION	LABOR - INSTALLATION COST PER WALL ROLL	SQ FT	232 '	LABOR	111.36
PALO007	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	INSULATION	R15 WALL INSULATION (33 BAGS X 1000 SQ FT)	SQ FT	15 '	MATERIAL	171.00
PALO008	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	INSULATION	Roof Insulation	WEEK	49	TASK
PALO008	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	INSULATION	LABOR - INSTALLATION COST PER CEILING BLOWING-IN	SQ FT	204 '	LABOR	134.64
PALO008	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	INSULATION	R30 BLOWN INSULATION (15 BAGS X 1000 SQ FT)	SQ FT	12 '	MATERIAL	309.60
PALO009	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DRYWALL	Sheet Rock	WEEK	48	TASK
PALO009	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DRYWALL	Tape Bet and Texture	WEEK	48	TASK
PALO009	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DOORS AND WINDOWS	Interior Doors Installation	WEEK	49	TASK
PALO009	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DRYWALL	LABOR - ADDITION WALL - PER SHEET (HANG TAPE BED AND	EA	15 '	LABOR	765.00
PALO009	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DRYWALL	LABOR - ADDITION CEILING - PER SHEET (HANG, TAPE, BED A	EA	7 '	LABOR	504.00
PALO009	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DRYWALL	LABOR - PATCH CEILING - PER SHEET (HANG, TAPE, BED AND	EA		LABOR	373.50
PALO009	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DRYWALL	MATERIALS - WALLS	EA	17 '	MATERIAL	209.10
PALO009	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DRYWALL	MATERIALS - CEILINGS	EA	8 '	MATERIAL	98.40
PALO009	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DRYWALL	OTHER MATERIALS	EA	1 '	MATERIAL	210.00
PALO010	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	TILES	Tiles	WEEK	49	TASK
PALO010	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	TILES	LABOR - FLOOR TILES INSTALLATION	SQ FT	98 '	LABOR	705.60
PALO010	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	TILES	LABOR - SHOWER FLOOR TILES INSTALLATION	SQ FT	28 '	LABOR	588.00
PALO010	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	TILES	LABOR - SHOWER WALL TILES INSTALLATION	SQ FT	120 '	LABOR	1,116.00
PALO010	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	TILES	TILES - FLOOR	SQ FT	107 '	MATERIAL	288.90
PALO010	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	TILES	TILES - SHOWER WALLS	SQFT	132 '	MATERIAL	594.00
PALO010	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	TILES	TILES - SHOWER FLOOR	SQ FT	31 '	MATERIAL	223.20
PALO010	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	TILES	OTHER MATERIALS	EA	1 '	MATERIAL	330.00
PALO011	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	PAINT	Painting	WEEK	49	TASK
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	Leveling and floating of floors	WEEK	50	TASK
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	Floor Installation	WEEK	50	TASK
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	Moldures and Baseboard Installation	WEEK	50	TASK
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	Trim, baseboards and Mantel Painting	WEEK	50	TASK
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	LABOR - INSTALLATION CLICK FLOORING LVP	SQ FT	336 '	LABOR	504.00
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	LABOR - INSTALLATION CARPET	SQ FT	522 '	LABOR	689.04
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	LABOR - INSTALLATION VINYL FLOOR INSTALLATION	LN FT	89 '	LABOR	96.12
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	LUXURY VINYL FLOORING	SQ FT	370 '	MATERIAL	1,221.00
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	CARPET	SQ FT	575 '	MATERIAL	1,345.50
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	CUSTOM BASEBOARDS	EA	92 '	MATERIAL	231.84
PALO012	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	FLOORING	OTHER MATERIAL	EA	1 '	MATERIAL	330.00
PALO013	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	CABINETS	Custom Cabinets Fabrication	WEEK	48	TASK
PALO013	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	CABINETS	Resurface Kitchen Cabinets	WEEK	51	TASK
PALO013	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	CABINETS	Vanities Installation	WEEK	51	TASK
PALO013	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	CABINETS	CUSTOM PANTRY CABINET PER LN FT	LN FT	2 '	ALL INCLUDED	648.00
PALO013	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	CABINETS	RESURFACE KITCHEN CABINETS	LN FT	45 '	ALL INCLUDED	3,510.00
PALO013	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	CABINETS	PRE FAB VANITY 72 IN W/QUARTZ	EA	1 '	ALL INCLUDED	1,530.00
PALO014	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	ROOFING	Gutters	WEEK	51	TASK
PALO015	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	GLASS	Glass Installation	WEEK	51	TASK
PALO015	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DRAIN SYSTEM	Install Drain System	WEEK	52	TASK
PALO015	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	GLASS	SHOWER GLASS PANEL 3FT TO 4FT	EA	1 '	ALL INCLUDED	510.00
PALO016	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	DRAIN SYSTEM	BASIN DRAIN	EA	1 '	ALL INCLUDED	1,080.00
X	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	GENERAL CONDITIONS	Surveyor Documents	WEEK	38	TASK
X	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work	WEEK	38	TASK
X	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	GENERAL CONDITIONS	Permits	WEEK	38	TASK
X	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	GENERAL CONDITIONS	DEMO OF STRUCTURE	WEEK	39	TASK
X	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	OTHERS	DELIVERY	WEEK	52	TASK
X	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	GENERAL CONDITIONS TOTAL	DUMPSTER FEES - ISYD	EA	4	LABOR	2,112.00
X	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	GENERAL CONDITIONS TOTAL	GENERAL PROJECT CLEANING - M	EA	1	LABOR	280.00
X	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	GENERAL CONDITIONS TOTAL	CITY PERMITS	EA	1	LABOR	2,800.00
X	Anthony Romo	1731 Palo Duro Trail Grapevine, TX 76051	GENERAL CONDITIONS TOTAL	DEMO	CY	7	LABOR	840.00
LAKE001	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	3.00 FOUNDATION TOTAL	FORM WORK	SQ FT	240	ALL INCLUDED
LAKE001	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	3.00 FOUNDATION TOTAL	PIERS	UNIT	16	ALL INCLUDED
LAKE001	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	3.00 FOUNDATION TOTAL	GRADE BEAMS / FOOTINGS	LF	108	ALL INCLUDED
LAKE001	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	3.00 FOUNDATION TOTAL	CONCRETE SLAB	SQ FT	240	ALL INCLUDED
LAKE001	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	FOUNDATION	Foundation Form and Excavation	WEEK	38	TASK
LAKE001	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar	WEEK	39	TASK
LAKE001	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	FOUNDATION	Concrete Pour	WEEK	39	TASK
LAKE0012	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	12.0 FLOORING	LABOR - POLISHED AND SEALED CONCRETE	SQ FT	240	LABOR
LAKE0012	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	12.0 FLOORING	LABOR - INSTALLATION TRIM AND BASEBOARDS	LN FT	64	LABOR
LAKE0012	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	12.0 FLOORING	POLISHED AND SEALED CONCRETE	SQ FT	264	LABOR
LAKE0012	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	12.0 FLOORING	SOLID WOOD BASEBOARDS	LN FT	70	MATERIAL
LAKE0012	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	12.0 FLOORING	OTHER MATERIAL	EA	1	MATERIAL
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	1-00 GENERAL CONDITIONS TOTAL	DEMO	CY	6	LABOR
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	6.0 FRAMING	ADDITION REFRAME - STRUCTURAL - LABOR	SF	240	LABOR
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	6.0 FRAMING	ADDITION REFRAME - STRUCTURAL - MATERIAL	SF	264	MATERIAL
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	7.0 EXTERIOR SHEATING	LABOR (SURFACE SQ FT) - SHEATING	SQ FT	512	LABOR
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	7.0 EXTERIOR SHEATING	ZIP SYSTEM 4FT X 8 FT - ROOF SHEATING	UNIT	8	MATERIAL
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	7.0 EXTERIOR SHEATING	ZIP SYSTEM 4FT X 8 FT - WALL SHEATING	UNIT	16	MATERIAL
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	7.0 EXTERIOR SHEATING	ZIP SYSTEM TAPE X 90 FT	UNIT	7	MATERIAL
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	9.0 DOORS AND WINDOWS	INTERIOR MDP PREFAB DOORS 80¨	UN	2	MATERIAL
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	9.0 DOORS AND WINDOWS	EXTERIOR ALUMINUM PREFAB DOORS 80¨	UN	1	MATERIAL
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	9.0 DOORS AND WINDOWS	VYNIL WINDOWS - NEW CONSTRUCTION	UN	2	MATERIAL
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	GENERAL CONDITIONS	DEMO	WEEK	41	TASK
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	FRAMING	Framing	WEEK	41	TASK
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)	WEEK	43	TASK
LAKE002	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	DOORS AND WINDOWS	Exterior Windows and Doors	WEEK	43	TASK
LAKE003	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	13.0 STUCCO / SIDING	LABOR - WALL - BRICKS	SQ FT	512	LABOR
LAKE003	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	13.0 STUCCO / SIDING	MATERIALS - WALL - BRICKS	SQ FT	563	MATERIAL
LAKE003	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	SIDING / BRICK	Bricks	WEEK	43	TASK
LAKE004	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	8.0 ROOFING	LABOR (CONSTRUCTION SQ FT) - SHINGLES	SQ FT	343	ALL INCLUDED
LAKE004	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	8.0 ROOFING	SHINGLES	UNIT	6	ALL INCLUDED
LAKE004	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	8.0 ROOFING	ROOF PROTECTOR UNDERLAYMENT	SQ FT	298	ALL INCLUDED
LAKE004	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	ROOFING	Roofing	WEEK	43	TASK
LAKE005	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	4.00 ELECTRICAL	LABOR - ADDITION - SUBPANEL	UNIT	1	LABOR
LAKE005	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	4.00 ELECTRICAL	LABOR - ADDITION - WIRING	SQ FT	240	LABOR
LAKE005	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	4.00 ELECTRICAL	LED RECESSED LIGHT	UNIT	4	MATERIAL
LAKE005	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	ELECTRICAL	Electrical Rough In	WEEK	43	TASK
LAKE005	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	ELECTRICAL	Accesories Installation	WEEK	47	TASK
LAKE006	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	14.0 HVAC	A/C DUCTING	EA	1	ALL INCLUDED
LAKE006	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	MECHANICAL	Mechanic (HVAC) Rough in	WEEK	43	TASK
LAKE007	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	11.0 INSULATION	LABOR - INSTALLATION COST PER WALL ROLL	SQ FT	512	LABOR
LAKE007	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	11.0 INSULATION	R15 WALL INSULATION (33 BAGS X 1000 SQ FT)	SQ FT	19	MATERIAL
LAKE007	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	INSULATION	Wall Insulation	WEEK	44	TASK
LAKE008	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	11.0 INSULATION	LABOR - INSTALLATION COST PER CEILING BLOWING-IN	SQ FT	240	LABOR
LAKE008	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	11.0 INSULATION	R30 BLOWN INSULATION (15 BAGS X 1000 SQ FT)	SQ FT	9	MATERIAL
LAKE008	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	INSULATION	Roof Insulation	WEEK	44	TASK
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	10.0 PAINT	LABOR - WALLS UP TO 10 FT	SQ FT	512	LABOR
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	10.0 PAINT	LABOR - CEILING	SQ FT	240	LABOR
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	10.0 PAINT	LABOR - TRIM PAINT	LNFT	64	LABOR
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	10.0 PAINT	MATERIAL - WALL PAINT	UNIT	2	MATERIAL
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	10.0 PAINT	MATERIAL - CEILING PAINT	UNIT	1	MATERIAL
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	10.0 PAINT	MATERIAL - TRIM PAINT	UNIT	1	MATERIAL
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	10.0 PAINT	OTHER MATERIALS	GLOBAL	1	MATERIAL
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	20.0 DRYWALL	LABOR - ADDITION WALL - PER SHEET (HANG TAPE BED AND TEXTURE)	EA	17	LABOR
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	20.0 DRYWALL	LABOR - ADDITION CEILING - PER SHEET (HANG, TAPE, BED AND TEXTURE)	EA	9	LABOR
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	20.0 DRYWALL	MATERIALS - WALLS	EA	19	MATERIAL
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	20.0 DRYWALL	MATERIALS - CEILINGS	EA	11	MATERIAL
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	20.0 DRYWALL	OTHER MATERIALS	EA	1	MATERIAL
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	DRYWALL	Sheet Rock	WEEK	46	TASK
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	DRYWALL	Tape Bet and Texture	WEEK	46	TASK
LAKE009	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	PAINT	Painting	WEEK	46	TASK
LAKE010	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	15.0 TILES	LABOR - FLOOR TILES INSTALLATION	SQ FT	25	LABOR
LAKE010	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	TILES	Tiles Installation	WEEK	46	TASK
LAKE011	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	ROOFING	Gutters	WEEK	47	TASK
LAKE012	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	FLOORING	Flooring Polished Concrete	WEEK	47	TASK
X	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	1-00 GENERAL CONDITIONS TOTAL	FORM SURVEY	EA	1
X	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	1-00 GENERAL CONDITIONS TOTAL	DUMPSTER FEES - ISYD	EA	3
X	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	1-00 GENERAL CONDITIONS TOTAL	GENERAL PROJECT CLEANING - M	EA	1
X	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	1-00 GENERAL CONDITIONS TOTAL	ARCHITECTURAL SET OF PLANS - ADDITION	SQ FT	240
X	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	1-00 GENERAL CONDITIONS TOTAL	STRUCTURAL SET OF PLANS - ADDITION	SQ FT	240
X	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	1-00 GENERAL CONDITIONS TOTAL	STRUCTURAL ENGINEERING REPORT	EA	1
X	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	1-00 GENERAL CONDITIONS TOTAL	ENGINEERING FOUNDATION REPORT	EA	1
X	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	1-00 GENERAL CONDITIONS TOTAL	CITY PERMITS	EA	1
x	Robert Campbell	111 Lakeside LnLittle Elm, TX 75068	OTHERS	Delivery Week	WEEK	48	TASK
x	Cindy Ferguson	733 Yale Dr Allen, TX 75002	1-00 GENERAL CONDITIONS TOTAL	DUMPSTER FEES - ISYD	EA	2	X
x	Cindy Ferguson	733 Yale Dr Allen, TX 75002	1-00 GENERAL CONDITIONS TOTAL	GENERAL PROJECT CLEANING - M	EA	1	X
x	Cindy Ferguson	733 Yale Dr Allen, TX 75002	GENERAL CONDITIONS	Surveyor Documents	WEEK	38	TASK
x	Cindy Ferguson	733 Yale Dr Allen, TX 75002	GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work	WEEK	38	TASK
x	Cindy Ferguson	733 Yale Dr Allen, TX 75002	GENERAL CONDITIONS	Permits	WEEK	38	TASK
x	Cindy Ferguson	733 Yale Dr Allen, TX 75002	GENERAL CONDITIONS	Post Permits	WEEK	38	TASK
x	Cindy Ferguson	733 Yale Dr Allen, TX 75002	GENERAL CONDITIONS	Place Dumpsters	WEEK	38	TASK
x	Cindy Ferguson	733 Yale Dr Allen, TX 75002	OTHERS	DELIVERY WEEK	WEEK	42	TASK
YALE001	Cindy Ferguson	733 Yale Dr Allen, TX 75002	1-00 GENERAL CONDITIONS TOTAL	DEMO	CY	7	LABOR
YALE001	Cindy Ferguson	733 Yale Dr Allen, TX 75002	GENERAL CONDITIONS	DEMO OF STRUCTURE	WEEK	38	TASK
YALE002	Cindy Ferguson	733 Yale Dr Allen, TX 75002	4.00 ELECTRICAL	ELECTRICAL - MAJOR	UNIT	8	LABOR
YALE002	Cindy Ferguson	733 Yale Dr Allen, TX 75002	4.00 ELECTRICAL	LED RECESSED LIGHT	UNIT	4	MATERIAL
YALE002	Cindy Ferguson	733 Yale Dr Allen, TX 75002	4.00 ELECTRICAL	DECORATIVE LIGHT FIXTURE	UNIT	1	MATERIAL
YALE002	Cindy Ferguson	733 Yale Dr Allen, TX 75002	ELECTRICAL	Electrical Rough In	WEEK	38	TASK
YALE002	Cindy Ferguson	733 Yale Dr Allen, TX 75002	ELECTRICAL	Accesories Installation	WEEK	41	TASK
YALE003	Cindy Ferguson	733 Yale Dr Allen, TX 75002	5.00 PLUMBING	LABOR PER SERVICE - REMODELING & RELOCATING	UNIT	6	LABOR
YALE003	Cindy Ferguson	733 Yale Dr Allen, TX 75002	5.00 PLUMBING	KITCHEN FAUCET - BG	UNIT	1	MATERIAL
YALE003	Cindy Ferguson	733 Yale Dr Allen, TX 75002	5.00 PLUMBING	KITCHEN SINK - BG	UNIT	1	MATERIAL
YALE003	Cindy Ferguson	733 Yale Dr Allen, TX 75002	5.00 PLUMBING	POT FILLER - BG	UNIT	1	MATERIAL
YALE003	Cindy Ferguson	733 Yale Dr Allen, TX 75002	PLUMBING	Inground Plumbing	WEEK	38	TASK
YALE003	Cindy Ferguson	733 Yale Dr Allen, TX 75002	PLUMBING	Plumbing Rough In	WEEK	38	TASK
YALE003	Cindy Ferguson	733 Yale Dr Allen, TX 75002	PLUMBING	Fixture Installation	WEEK	41	TASK
YALE004	Cindy Ferguson	733 Yale Dr Allen, TX 75002	6.0 FRAMING	LABOR - LOAD BEARING WALL OPEN CONCEPT	LN FT	16	LABOR
YALE004	Cindy Ferguson	733 Yale Dr Allen, TX 75002	6.0 FRAMING	MATERIAL - LOAD BEARING WALL OPEN CONCEPT	LN FT	16	MATERIAL
YALE004	Cindy Ferguson	733 Yale Dr Allen, TX 75002	FRAMING	Framing	WEEK	38	TASK
YALE005	Cindy Ferguson	733 Yale Dr Allen, TX 75002	10.0 PAINT	LABOR - WALLS UP TO 10 FT	SQ FT	522 '	LABOR
YALE005	Cindy Ferguson	733 Yale Dr Allen, TX 75002	10.0 PAINT	LABOR - CEILING	SQ FT	1722 '	LABOR
YALE005	Cindy Ferguson	733 Yale Dr Allen, TX 75002	10.0 PAINT	LABOR - INTERIOR DOOR PAINT	EA	1 '	LABOR
YALE005	Cindy Ferguson	733 Yale Dr Allen, TX 75002	10.0 PAINT	LABOR - TRIM PAINT	LNFT	67 '	LABOR
YALE005	Cindy Ferguson	733 Yale Dr Allen, TX 75002	10.0 PAINT	LABOR - REMOVING POPCORN CEILIJNG	SQ FT	1722 '	LABOR
YALE005	Cindy Ferguson	733 Yale Dr Allen, TX 75002	10.0 PAINT	MATERIAL - WALL PAINT	UNIT	2 '	MATERIAL
YALE005	Cindy Ferguson	733 Yale Dr Allen, TX 75002	10.0 PAINT	MATERIAL - CEILING PAINT	UNIT	5 '	MATERIAL
YALE005	Cindy Ferguson	733 Yale Dr Allen, TX 75002	10.0 PAINT	MATERIAL - TRIM PAINT	UNIT	1 '	MATERIAL
YALE005	Cindy Ferguson	733 Yale Dr Allen, TX 75002	10.0 PAINT	OTHER MATERIALS	GLOBAL	1 '	MATERIAL
YALE005	Cindy Ferguson	733 Yale Dr Allen, TX 75002	PAINT	Painting	WEEK	39	TASK
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	12.0 FLOORING	LABOR - INSTALLATION CLICK FLOORING LVP	SQ FT	1722 '	LABOR
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	12.0 FLOORING	LABOR - INSTALLATION TRIM AND BASEBOARDS	LN FT	76 '	LABOR
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	12.0 FLOORING	LABOR - REMOVE FLOOR TILE	SQFT	282 '	LABOR
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	12.0 FLOORING	LABOR - CROWN MOLDING	LN FT	76 '	LABOR
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	12.0 FLOORING	CROWN MOLDING	LN FT	80 '	MATERIAL
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	12.0 FLOORING	LUXURY VINYL FLOORING	SQ FT	1895 '	MATERIAL
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	12.0 FLOORING	SOLID WOOD BASEBOARDS	LN FT	80 '	MATERIAL
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	12.0 FLOORING	OTHER MATERIAL	EA	1 '	MATERIAL
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	FLOORING	Leveling and floating of floors	WEEK	40	TASK
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	FLOORING	Floor Installation	WEEK	40	TASK
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	FLOORING	Moldures and Baseboard Installation	WEEK	40	TASK
YALE006	Cindy Ferguson	733 Yale Dr Allen, TX 75002	FLOORING	Trim, baseboards and Mantel Painting	WEEK	40	TASK
YALE007	Cindy Ferguson	733 Yale Dr Allen, TX 75002	13.0 STUCCO / SIDING	WALL - BRICKS	UNIT	1 '	LABOR
YALE007	Cindy Ferguson	733 Yale Dr Allen, TX 75002	SIDING / BRICK	Siding or bricks or stucco	WEEK	40	TASK
YALE008	Cindy Ferguson	733 Yale Dr Allen, TX 75002	15.0 TILES	LABOR - BACKSPLASH TILES INSTALLATION	SQ FT	110 '	LABOR
YALE008	Cindy Ferguson	733 Yale Dr Allen, TX 75002	15.0 TILES	TILES - BACKSPLASH	SQ FT	115 '	MATERIAL
YALE008	Cindy Ferguson	733 Yale Dr Allen, TX 75002	15.0 TILES	OTHER MATERIALS	EA	2 '	MATERIAL
YALE008	Cindy Ferguson	733 Yale Dr Allen, TX 75002	TILES	Tiles Backsplash	WEEK	41	TASK
YALE009	Cindy Ferguson	733 Yale Dr Allen, TX 75002	18.0 CABINETS	CUSTOM BASE CABINET PER LN FT	LN FT	19 '	ALL INCLUDED
YALE009	Cindy Ferguson	733 Yale Dr Allen, TX 75002	18.0 CABINETS	CUSTOM UPPER CABINET PER LN FT	LN FT	30 '	ALL INCLUDED
YALE009	Cindy Ferguson	733 Yale Dr Allen, TX 75002	18.0 CABINETS	KITCHEN ISLAND PANELING	LN FT	16 '	ALL INCLUDED
YALE009	Cindy Ferguson	733 Yale Dr Allen, TX 75002	18.0 CABINETS	BREAKFAST NOOK SLIDING DOOR	UNIT	1 '	ALL INCLUDED
YALE009	Cindy Ferguson	733 Yale Dr Allen, TX 75002	CABINETS	Kitchen Cabinets Fabrication	WEEK	38	TASK
YALE009	Cindy Ferguson	733 Yale Dr Allen, TX 75002	CABINETS	Kitchen Island Fabrication	WEEK	38	TASK
YALE009	Cindy Ferguson	733 Yale Dr Allen, TX 75002	CABINETS	Kitchen Cabinets Installation	WEEK	40	TASK
YALE010	Cindy Ferguson	733 Yale Dr Allen, TX 75002	19.0 COUNTERTOPS	QUARTZ - PURE WHITE	SQFT	84 '	ALL INCLUDED
YALE010	Cindy Ferguson	733 Yale Dr Allen, TX 75002	COUNTERTOP	Countertop Intallation	WEEK	41	TASK
YALE011	Cindy Ferguson	733 Yale Dr Allen, TX 75002	20.0 DRYWALL	LABOR - REMODELING WALL - PER SHEET (HANG TAPE BED A	EA	5 '	LABOR
YALE011	Cindy Ferguson	733 Yale Dr Allen, TX 75002	20.0 DRYWALL	LABOR - REMODELING CEILING - PER SHEET (HANG, TAPE, B	EA	5 '	LABOR
YALE011	Cindy Ferguson	733 Yale Dr Allen, TX 75002	20.0 DRYWALL	MATERIALS - WALLS	EA	6 '	MATERIAL
YALE011	Cindy Ferguson	733 Yale Dr Allen, TX 75002	20.0 DRYWALL	MATERIALS - CEILINGS	EA	6 '	MATERIAL
YALE011	Cindy Ferguson	733 Yale Dr Allen, TX 75002	20.0 DRYWALL	OTHER MATERIALS	EA	1 '	MATERIAL
YALE011	Cindy Ferguson	733 Yale Dr Allen, TX 75002	DRYWALL	Sheet Rock	WEEK	38	TASK
YALE011	Cindy Ferguson	733 Yale Dr Allen, TX 75002	DRYWALL	Tape Bet and Texture	WEEK	39	TASK
COUNTY001	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	2.00 SITE WORK TOTALS	GRADING	UNIT	1	LABOR	1,080.00
COUNTY001	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	3.00 FOUNDATION TOTAL	FORM WORK	SQ FT	600	ALL INCLUDED	378.00
COUNTY001	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	3.00 FOUNDATION TOTAL	PIERS	UNIT	24	ALL INCLUDED	5,376.00
COUNTY001	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	3.00 FOUNDATION TOTAL	GRADE BEAMS / FOOTINGS	LF	170	ALL INCLUDED	892.50
COUNTY001	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	3.00 FOUNDATION TOTAL	CONCRETE SLAB	SQ FT	600	ALL INCLUDED	3,990.00
COUNTY001	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	SITE WORK	Grading and soil leveling	WEEK	38 '	TASK
COUNTY001	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	FOUNDATION	Foundation Form and Excavation	WEEK	38 '	TASK
COUNTY001	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	FOUNDATION	Concrete Piers	WEEK	38 '	TASK
COUNTY001	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar	WEEK	38 '	TASK
COUNTY001	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	FOUNDATION	Concrete Pour	WEEK	38 '	TASK
COUNTY002	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	4.00 ELECTRICAL	LABOR - ADDITION - SUBPANEL	SQ FT	600 '	LABOR	3,600.00
COUNTY002	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	4.00 ELECTRICAL	LED RECESSED LIGHT	UNIT	12	MATERIAL	150.00
COUNTY002	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	4.00 ELECTRICAL	CEILING FAN LIGHT FIXTURE	UNIT	2	MATERIAL	250.00
COUNTY002	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	4.00 ELECTRICAL	DECORATIVE LIGHT FIXTURE	UNIT	1	MATERIAL	75.00
COUNTY002	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	4.00 ELECTRICAL	EXAUST FAN	UNIT	1	MATERIAL	30.00
COUNTY002	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	ELECTRICAL	Electrical Rough In	WEEK	38 '	TASK
COUNTY002	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	ELECTRICAL	Electrical For HVAC	WEEK	39 '	TASK
COUNTY002	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	ELECTRICAL	Smoke Detectors Installation	WEEK	42 '	TASK
COUNTY002	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	ELECTRICAL	Accesories Installation	WEEK	42 '	TASK
COUNTY004	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	5.00 PLUMBING	LABOR PER SERVICE - ADDITION	UNIT	7	LABOR	2,625.00
COUNTY004	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	5.00 PLUMBING	TOILET - BG	UNIT	1	MATERIAL	175.00
COUNTY004	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	5.00 PLUMBING	SHOWER FAUCET - BG	UNIT	1	MATERIAL	275.00
COUNTY004	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	5.00 PLUMBING	BATHROOM FAUCET - BG	UNIT	1	MATERIAL	125.00
COUNTY004	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	5.00 PLUMBING	SINK - BG	UNIT	1	MATERIAL	200.00
COUNTY004	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	5.00 PLUMBING	SUPPORT BAR 18¨	UNIT	2	MATERIAL	80.00
COUNTY004	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	5.00 PLUMBING	SHOWER BASE WHITE 60 x 30	UNIT	1	LABOR	240.00
COUNTY004	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	PLUMBING	Inground Plumbing	WEEK	38 '	TASK
COUNTY004	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	PLUMBING	Plumbing Rough In	WEEK	38 '	TASK
COUNTY004	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	PLUMBING	Fixture Installation	WEEK	42 '	TASK
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	6.0 FRAMING	ADDITION REFRAME - STRUCTURAL - LABOR	SF	600	LABOR	3,135.00
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	6.0 FRAMING	ADDITION REFRAME - STRUCTURAL - MATERIAL	SF	660	MATERIAL	4,356.00
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	6.0 FRAMING	ADDING A WALL - LABOR (WALL SQ FT)	SF	108	LABOR	148.50
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	6.0 FRAMING	ADDING A WALL - MATERIAL (WALL SQ FT)	SF	118	MATERIAL	356.95
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	6.0 FRAMING	EXTERIOR DECKING - LABOR	SQ FT	120	LABOR	693.00
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	6.0 FRAMING	EXTERIOR DECKING - MATERIAL	SQ FT	132	MATERIAL	3,267.00
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	7.0 EXTERIOR SHEATING	LABOR (SURFACE SQ FT) - SHEATING	SQ FT	1380	LABOR	1,242.00
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	7.0 EXTERIOR SHEATING	ZIP SYSTEM 4FT X 8 FT - ROOF SHEATING	UNIT	28	MATERIAL	406.56
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	7.0 EXTERIOR SHEATING	ZIP SYSTEM 4FT X 8 FT - WALL SHEATING	UNIT	22	MATERIAL	319.44
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	7.0 EXTERIOR SHEATING	ZIP SYSTEM TAPE X 90 FT	UNIT	3	MATERIAL	44.55
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	9.0 DOORS AND WINDOWS	POCKET DOOR	UN	3	MATERIAL	1,530.00
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	9.0 DOORS AND WINDOWS	EXTERIOR ALUMINUM PREFAB DOORS 80¨	UN	1	MATERIAL	390.00
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	9.0 DOORS AND WINDOWS	VYNIL WINDOWS - NEW CONSTRUCTION	UN	7	MATERIAL	2,856.00
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	9.0 DOORS AND WINDOWS	STORM/SCREEN DOOR	UN	1	MATERIAL	270.00
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	GENERAL CONDITIONS	Demo Preparation	WEEK	38 '	TASK
COUNTY005	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	FRAMING	Patio Decking and Skirt	WEEK	39 '	TASK
COUNTY006	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	8.0 ROOFING	LABOR (CONSTRUCTION SQ FT) - SHINGLES	SQ FT	780	ALL INCLUDED	772.20
COUNTY006	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	8.0 ROOFING	SHINGLES	UNIT	27	ALL INCLUDED	1,514.70
COUNTY006	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	8.0 ROOFING	ROOF PROTECTOR UNDERLAYMENT	SQ FT	780	ALL INCLUDED	343.20
COUNTY006	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	8.0 ROOFING	GALVANIZED FLASHING	UNIT	1	ALL INCLUDED	154.00
COUNTY006	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	8.0 ROOFING	GAF WEATHERWATCH 100 LN FT (200 SQFT)	UNIT	3	ALL INCLUDED	231.00
COUNTY006	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	8.0 ROOFING	GAF PRO START 120 LN FT - STARTER TRIP SHINGLES	UNIT	1	ALL INCLUDED	24.19
COUNTY006	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	8.0 ROOFING	COBRA EXHAUST VENT - RIDGE VENT 20 LN FT	UNIT	1	ALL INCLUDED	30.25
COUNTY006	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	ROOFING	Roofing	WEEK	38 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	LABOR - WALLS UP TO 10 FT	SQ FT	1140 '	LABOR	1,026.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	LABOR - CEILING	SQ FT	600 '	LABOR	792.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	LABOR - SIDING PAINT ( EXTERIOR)	SQ FT	805 '	LABOR	821.10
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	LABOR - INTERIOR DOOR PAINT	EA	1 '	LABOR	108.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	LABOR - TRIM PAINT	LNFT	140 '	LABOR	100.80
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	LABOR - FRONT DOOR PAINT	EA	1 '	LABOR	330.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	MATERIAL - WALL PAINT	UNIT	3 '	MATERIAL	315.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	MATERIAL - CEILING PAINT	UNIT	1 '	MATERIAL	105.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	MATERIAL - TRIM PAINT	UNIT	1 '	MATERIAL	51.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	MATERIAL - DOORS PAINT	UNIT	2 '	MATERIAL	102.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	10.0 PAINT	OTHER MATERIALS	GLOBAL	1 '	MATERIAL	348.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	12.0 FLOORING	LABOR - INSTALLATION CLICK FLOORING LVP	SQ FT	660 '	LABOR	990.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	12.0 FLOORING	WATER RESISTANT LAMINATED FLOORS	SQ FT	726 '	LABOR	1,873.08
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	12.0 FLOORING	MDF BASEBOARDS	SQ FT	140 '	MATERIAL	184.80
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	12.0 FLOORING	OTHER MATERIAL	EA	1 '	MATERIAL	330.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	13.0 STUCCO / SIDING	LABOR - WALL - SIDING	SQ FT	630 '	LABOR	680.40
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	13.0 STUCCO / SIDING	MATERIALS - WALL - SIDING	SQ FT	693 '	MATERIAL	1,081.08
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	15.0 TILES	LABOR - SHOWER FLOOR TILES INSTALLATION	SQ FT	20 '	LABOR	420.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	15.0 TILES	LABOR - SHOWER WALL TILES INSTALLATION	SQ FT	104 '	LABOR	967.20
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	15.0 TILES	TILES - SHOWER WALLS	SQFT	114 '	MATERIAL	513.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	15.0 TILES	TILES - SHOWER FLOOR	SQ FT	22 '	MATERIAL	158.40
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	15.0 TILES	TILES - QUARTZ NICHE (36 IN)	EA	1 '	MATERIAL	72.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	15.0 TILES	OTHER MATERIALS	EA	1 '	MATERIAL	330.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	17.0 GLASS	SHOWER GLASS DOOR 5FT X 72 IN (FIXED - SLIDING)	EA	1 '	ALL INCLUDED	750.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	20.0 DRYWALL	LABOR - ADDITION WALL - PER SHEET (HANG TAPE BED AND TEXTURE)	EA	48 '	LABOR	2,448.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	20.0 DRYWALL	LABOR - ADDITION CEILING - PER SHEET (HANG, TAPE, BED AND TEXTURE)	EA	19 '	LABOR	1,368.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	20.0 DRYWALL	MATERIALS - WALLS	EA	53 '	MATERIAL	651.90
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	20.0 DRYWALL	MATERIALS - CEILINGS	EA	20 '	MATERIAL	246.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	20.0 DRYWALL	OTHER MATERIALS	EA	1 '	MATERIAL	210.00
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	SIDING / BRICK	Siding Installation	WEEK	40 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	DRYWALL	Sheet Rock	WEEK	40 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	DRYWALL	Hardybacker Installation	WEEK	40 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	DRYWALL	Wet Areas Water Proofing Redguard	WEEK	40 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	DRYWALL	Tape Bet and Texture	WEEK	40 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	TILES	Tiles	WEEK	40 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	DOORS AND WINDOWS	Interior Doors Installation	WEEK	40 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	PAINT	Painting	WEEK	40 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	FLOORING	Leveling and floating of floors	WEEK	41 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	FLOORING	Floor Installation	WEEK	41 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	FLOORING	Moldures and Baseboard Installation	WEEK	41 '	TASK
COUNTY007	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	FLOORING	Trim, baseboards and Mantel Painting	WEEK	41 '	TASK
COUNTY008	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	11.0 INSULATION	LABOR - INSTALLATION COST PER WALL ROLL	SQ FT	600 '	LABOR	288.00
COUNTY008	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	11.0 INSULATION	R15 WALL INSULATION (33 BAGS X 1000 SQ FT)	SQ FT	20 '	MATERIAL	228.00
COUNTY008	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	INSULATION	Wall Insulation	WEEK	39 '	TASK
COUNTY009	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	11.0 INSULATION	LABOR - INSTALLATION COST PER CEILING BLOWING-IN	SQ FT	600 '	LABOR	396.00
COUNTY009	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	11.0 INSULATION	R30 BLOWN INSULATION (15 BAGS X 1000 SQ FT)	SQ FT	9 '	MATERIAL	232.20
COUNTY010	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	14.0 HVAC	3 TON HVAC	EA	1 '	ALL INCLUDED	4,680.00
COUNTY010	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	MECHANICAL	Mechanic (HVAC) Rough in	WEEK	39 '	TASK
COUNTY010	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	MECHANICAL	Mechanic (HVAC) Final	WEEK	42 '	TASK
COUNTY011	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	18.0 CABINETS	PRE FAB VANITY 60 IN W/QUARTZ	EA	1 '	ALL INCLUDED	1,350.00
COUNTY011	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	18.0 CABINETS	PRE FAB KITCHEN BASE CABINET	LN FT	6 '	ALL INCLUDED	936.00
COUNTY011	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	CABINETS	Vanities Installation	WEEK	41 '	TASK
COUNTY012	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	19.0 COUNTERTOPS	QUARTZ - PURE WHITE	SQFT	15 '	ALL INCLUDED	855.00
COUNTY012	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	COUNTERTOP	Countertop Intallation	WEEK	41 '	TASK
COUNTY013	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	FOUNDATION	Foundation Hooks	WEEK	39 '	TASK
COUNTY013	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	ROOFING	Gutters	WEEK	42 '	TASK
X	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	1-00 GENERAL CONDITIONS TOTAL	DUMPSTER FEES - ISYD	EA	2	LABOR	1,056.00
X	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	1-00 GENERAL CONDITIONS TOTAL	GENERAL PROJECT CLEANING	SQ FT	744	LABOR	892.80
X	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	1-00 GENERAL CONDITIONS TOTAL	ARCHITECTURAL SET OF PLANS - ADDITION	SQ FT	744	LABOR	1,309.44
X	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	1-00 GENERAL CONDITIONS TOTAL	STRUCTURAL SET OF PLANS - ADDITION	SQ FT	744	LABOR	1,071.36
X	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	1-00 GENERAL CONDITIONS TOTAL	ENGINEERING FOUNDATION REPORT	EA	1	LABOR	680.00
X	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	1-00 GENERAL CONDITIONS TOTAL	DEMO	CY	12	LABOR	1,440.00
X	DAVE BARRON	13740 Co Rd 4041 Scurry, TX 75158	OTHERS	DELIVERY	WEEK	43 '	TASK
STROLL001	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PLUMBING	Plumbing Rough In	WEEK	42	TASK
STROLL001	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PLUMBING	Fixtures Installation	WEEK	49	TASK
STROLL001	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PLUMBING	TOILET - BG	UNIT	1	MATERIAL	175.00
STROLL001	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PLUMBING	SHOWER FAUCET - BG	UNIT	1	MATERIAL	275.00
STROLL001	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PLUMBING	BATHROOM FAUCET - BG	UNIT	1	MATERIAL	125.00
STROLL001	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PLUMBING	SINK - BG	UNIT	1	MATERIAL	200.00
STROLL001	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PLUMBING	LABOR PER SERVICE - NEW CONSTRUCTION	UNIT	8	LABOR	3,400.00
STROLL001	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PLUMBING	BUILD UP SHOWER BASE	SQ FT	30	LABOR	825.00
STROLL002	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	GENERAL CONDITIONS	DEMO OF STRUCTURE	WEEK	40	TASK
STROLL002	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	GENERAL CONDITIONS	DEMO	CY	34	LABOR	4,080.00
STROLL003	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	MECHANICAL	Mechanic (HVAC) Rough in	WEEK	42	TASK
STROLL003	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	SITE WORK TOTALS	A/C UNITS PAD	UN	1	MATERIAL	120.00
STROLL003	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	HVAC	3 TON HVAC	EA	1	ALL INCLUDED	4,680.00
STROLL004	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ELECTRICAL	Electrical Rough In	WEEK	42	TASK
STROLL004	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ELECTRICAL	Smoke Detectors Installation	WEEK	49	TASK
STROLL004	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ELECTRICAL	Accesories Installation	WEEK	49	TASK
STROLL004	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	OTHERS	DELIVERY	WEEK	50	TASK
STROLL004	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ELECTRICAL	LED RECESSED LIGHT	UNIT	16	MATERIAL	200.00
STROLL004	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ELECTRICAL	CEILING FAN	UNIT	1	MATERIAL	175.00
STROLL004	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ELECTRICAL	EXAUST FAN	UNIT	1	MATERIAL	30.00
STROLL004	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ELECTRICAL	LABOR - ADDITION - SUBPANEL	UNIT	1	LABOR	400.00
STROLL004	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ELECTRICAL	LABOR - ADDITION - WIRING	SQ FT	1000	LABOR	5,000.00
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FRAMING	Framing	WEEK	40	TASK
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)	WEEK	41	TASK
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DOORS AND WINDOWS	Exterior Windows and Doors	WEEK	41	TASK
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DOORS AND WINDOWS	Interior Doors Installation	WEEK	46	TASK
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FRAMING	ADDITION REFRAME - STRUCTURAL - MATERIAL	SF	1108	MATERIAL	7,312.80
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	EXTERIOR SHEATING	ZIP SYSTEM 4FT X 8 FT - ROOF SHEATING	UNIT	49.5	MATERIAL	718.74
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	EXTERIOR SHEATING	ZIP SYSTEM 4FT X 8 FT - WALL SHEATING	UNIT	42.9	MATERIAL	622.91
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	EXTERIOR SHEATING	ZIP SYSTEM TAPE X 90 FT	UNIT	14	MATERIAL	207.90
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DOORS AND WINDOWS	INTERIOR MDP PREFAB DOORS 80¨	UN	3	MATERIAL	648.00
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DOORS AND WINDOWS	WOODEN FRENCH DOORS 72 X 80	UN	2	MATERIAL	1,680.00
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DOORS AND WINDOWS	VYNIL WINDOWS - NEW CONSTRUCTION	UN	3	MATERIAL	1,224.00
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FRAMING	ADDITION REFRAME - STRUCTURAL - LABOR	SF	1008	LABOR	5,266.80
STROLL005	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	EXTERIOR SHEATING	LABOR (SURFACE SQ FT) - SHEATING	SQ FT	1008	LABOR	907.20
STROLL006	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ROOFING	Roofing	WEEK	41	TASK
STROLL006	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ROOFING	LABOR (CONSTRUCTION SQ FT) - SHINGLES	SQ FT	1441	ALL INCLUDED	1,426.59
STROLL006	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ROOFING	SHINGLES	UNIT	45	ALL INCLUDED	2,524.50
STROLL006	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ROOFING	ROOF PROTECTOR UNDERLAYMENT	SQ FT	1441	ALL INCLUDED	634.04
STROLL006	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ROOFING	GALVANIZED FLASHING	UNIT	2	ALL INCLUDED	308.00
STROLL006	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ROOFING	GAF WEATHERWATCH 100 LN FT (200 SQFT)	UNIT	1	ALL INCLUDED	77.00
STROLL006	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ROOFING	GAF PRO START 120 LN FT - STARTER TRIP SHINGLES	UNIT	1	ALL INCLUDED	24.19
STROLL006	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ROOFING	COBRA EXHAUST VENT - RIDGE VENT 20 LN FT	UNIT	1	ALL INCLUDED	30.25
STROLL007	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PAINT	Painting	WEEK	46	TASK
STROLL007	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PAINT	MATERIAL - WALL PAINT	UNIT	2	MATERIAL	210.00
STROLL007	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PAINT	MATERIAL - CEILING PAINT	UNIT	1	MATERIAL	105.00
STROLL007	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PAINT	MATERIAL - TRIM PAINT	UNIT	1	MATERIAL	51.00
STROLL007	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PAINT	MATERIAL - DOORS PAINT	UNIT	1	MATERIAL	51.00
STROLL007	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PAINT	OTHER MATERIALS	GLOBAL	1	MATERIAL	348.00
STROLL007	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PAINT	LABOR - NEW CONSTRUCTION (BUILDING SQ FT)	SQ FT	1008	LABOR	2,116.80
STROLL007	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PAINT	LABOR - CEILING	SQ FT	1008	LABOR	1,330.56
STROLL007	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	PAINT	LABOR - TRIM PAINT	LNFT	160	LABOR	115.20
STROLL008	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	INSULATION	Wall Insulation	WEEK	43	TASK
STROLL008	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	INSULATION	R15 WALL INSULATION (33 BAGS X 1000 SQ FT)	SQ FT	33	MATERIAL	376.20
STROLL008	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	INSULATION	LABOR - INSTALLATION COST PER WALL ROLL	SQ FT	1008	LABOR	483.84
STROLL009	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FLOORING	Leveling and floating of floors	WEEK	47	TASK
STROLL009	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FLOORING	Floor Installation	WEEK	47	TASK
STROLL009	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FLOORING	Moldures and Baseboard Installation	WEEK	47	TASK
STROLL009	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FLOORING	Trim, baseboards and Mantel Painting	WEEK	47	TASK
STROLL009	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FLOORING	CARPET	SQ FT	990	MATERIAL	2,316.60
STROLL009	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FLOORING	MDF BASEBOARDS	SQ FT	1008	MATERIAL	1,330.56
STROLL009	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FLOORING	OTHER MATERIAL	EA	1	MATERIAL	330.00
STROLL009	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	FLOORING	LABOR - INSTALLATION CARPET	SQ FT	990	LABOR	1,306.80
STROLL010	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	SIDING / BRICK	Bricks Installation	WEEK	41	TASK
STROLL010	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	STUCCO / SIDING / BRICK	MATERIALS - WALL - BRICKS	SQ FT	1012	MATERIAL	5,009.40
STROLL010	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	STUCCO / SIDING / BRICK	LABOR - WALL - BRICKS	SQ FT	920	LABOR	3,726.00
STROLL011	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	TILES	Tiles	WEEK	46	TASK
STROLL011	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	TILES	TILES - FLOOR	SQ FT	33	MATERIAL	89.10
STROLL011	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	TILES	TILES - SHOWER WALLS	SQFT	158	MATERIAL	711.00
STROLL011	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	TILES	TILES - SHOWER FLOOR	SQ FT	33	MATERIAL	237.60
STROLL011	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	TILES	TILES - QUARTZ NICHE (36 IN)	EA	1	MATERIAL	72.00
STROLL011	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	TILES	OTHER MATERIALS	EA	1	MATERIAL	330.00
STROLL011	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	TILES	LABOR - FLOOR TILES INSTALLATION	SQ FT	30	LABOR	216.00
STROLL011	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	TILES	LABOR - SHOWER FLOOR TILES INSTALLATION	SQ FT	30	LABOR	630.00
STROLL011	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	TILES	LABOR - SHOWER WALL TILES INSTALLATION	SQ FT	144	LABOR	1,339.20
STROLL012	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	GLASS	Glass Installation	WEEK	49	TASK
STROLL012	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	GLASS	SHOWER GLASS DOOR 5FT X 72 IN (FIXED - SLIDING)	EA	1	MATERIAL	750.00
STROLL013	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	CABINETS	Vanities Installation	WEEK	48	TASK
STROLL013	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	CABINETS	PRE FAB VANITY 60 IN W/QUARTZ	EA	1	MATERIAL	1,350.00
STROLL014	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DRYWALL	Sheet Rock	WEEK	45	TASK
STROLL014	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DRYWALL	Hardybacker Installation	WEEK	45	TASK
STROLL014	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DRYWALL	Wet Areas Water Proofing Redguard	WEEK	45	TASK
STROLL014	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DRYWALL	Tape Bet and Texture	WEEK	45	TASK
STROLL014	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DRYWALL	MATERIALS - WALLS	EA	55	MATERIAL	676.50
STROLL014	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DRYWALL	MATERIALS - CEILINGS	EA	35	MATERIAL	430.50
STROLL014	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DRYWALL	LABOR - ADDITION WALL - PER SHEET (HANG TAPE BED AND TEXTURE)	EA	50	LABOR	2,550.00
STROLL014	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	DRYWALL	LABOR - ADDITION CEILING - PER SHEET (HANG, TAPE, BED AND TEXTURE)	EA	35	LABOR	2,520.00
STROLL015	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	INSULATION	Roof Insulation (New Houses	WEEK	45	TASK
STROLL015	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	INSULATION	R30 BLOWN INSULATION (15 BAGS X 1000 SQ FT)	SQ FT	15	MATERIAL	387.00
STROLL015	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	INSULATION	LABOR - INSTALLATION COST PER CEILING BLOWING-IN	SQ FT	1008	LABOR	665.28
STROLL016	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	ROOFING	Gutters	WEEK	49	TASK
X	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	GENERAL CONDITIONS	Surveyor Documents	WEEK	38	TASK
X	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work	WEEK	38	TASK
X	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	GENERAL CONDITIONS	Permits	WEEK	38	TASK
X	AMAN MOHAMMED	3505 Stroll Rd Plano, TX 75025	GENERAL CONDITIONS	Post Permits	WEEK	39	TASK

## BACK UP
WORK ORDERS	Customer	Task	Sub	Status	Negotiated	Ball Park	Budget	Cost	Obs	Start week	End week	Actual Date	End Date
	Dave barron	Patio decking and skirt						1800		39
	Dave barron	Proveedor de siding e vinyl						4000		40
	Dave barron	HVAC inside	Frncisco					3500	ya pagamos 3500	38
	Dave Barron	Electrical hvac	Anthony					1800		39		09/26
	Dave barron	Spray foam insulation						3000		39
	Dave barron	Roofing replace	Bryan					2000		39
	Dave barron	piso drywall y tile	nico					9000		39	41
	Dave barron	comprar materiales						10000		39
	Dave barron	Fixture electrical and plumbing						1000		42
	Dave barron	Gutters						1000		40		37100
	Dave barron	Other touch up								43
	Dave barron	Ganchos						1000		39
	Amanda	concreto						3000		38
	Amanda	Framing						2600		39
	Amanda	exterior sheeting						600		40
	Amanda	door windows						600		40
	Amanda	electrical rough in						1000		40
	Amanda	plumbing rough in and top out						2000		40
	Amanda	hvac rough in								40
	Amanda	Insulation								40
	Amanda	Sheetrock tape and bet texture								41
	Amanda	Paint								41
	Amanda	Tiles								40
	Amanda	Cabinets fabrication								40	40
	Amanda	Cabinets installation								41
	Amanda	Cabinet paint								42
	Amanda	Countertops								43
	Amanda	Flooring								42
	Amanda	Tiles backsplash								43
	Amanda	Finishing electrical						200		44
	Amanda	Finish plumbing						1000		44
	Amanda	Delivery week								45
x	Robert Campbell	concreto								38 39
x	Robert Campbell	Framing								41
x	Robert Campbell	exterior sheeting								43
x	Robert Campbell	door windows								43
x	Robert Campbell	Roofing								43
x	Robert Campbell	Gutters								45
x	Robert Campbell	Bricks								43
x	Robert Campbell	electrical rough in								43
x	Robert Campbell	hvac rough in								43	Only move air ducts
x	Robert Campbell	Insulation								44 44
x	Robert Campbell	Sheetrock tape and bet texture								46
x	Robert Campbell	Paint								46
x	Robert Campbell	Tiles								46
x	Robert Campbell	Finishing electrical								47
x	Robert Campbell	Delivery week								48
	Anthony romo	Concrete form								38
	Anthony romo	Inground plumbing								39	Inspection
	Anthony romo	Prepour rebar form								40
	Anthony romo	Concrete pour								41
	Anthony romo	Framing								43
	Anthony romo	exterior sheeting								44
	Anthony romo	door windows								44
	Anthony romo	electrical rough in								45
	Anthony romo	plumbing rough in and top out								45
	Anthony romo	hvac rough in								45
	Anthony romo	Insulation								45
	Anthony romo	Sheetrock tape and bet texture								41
	Anthony romo	Paint
	Anthony romo	Tiles
	Anthony romo	Cabinets fabrication
	Anthony romo	Cabinets installation
	Anthony romo	Cabinet paint
	Anthony romo	Countertops
	Anthony romo	Flooring
	Anthony romo	Tiles backsplash
	Anthony romo	Finishing electrical						200
	Anthony romo	Finish plumbing						1000
	Anthony romo	Delivery week

## ROBERT CAMPBELL
CATEGORY	Process Name	SubProcess Name	DEPARTMENT	Week	FOR THIS PROJECT\	COMMENTS	INSPECTION	Week
GENERAL CONDITIONS	Surveyor Documents		PLANING	38
GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work		PLANING	38
GENERAL CONDITIONS	Permits		PLANING	38
GENERAL CONDITIONS	Post Permits		PROJECT MANAGER	39
GENERAL CONDITIONS	Place Dumpsters		PROJECT MANAGER	39
GENERAL CONDITIONS	DEMO OF STRUCTURE		PROJECT MANAGER	39
SITE WORK	Tree Removal		PROJECT MANAGER	39
SITE WORK	Grading and soil leveling		PROJECT MANAGER	39
SITE WORK	Filling Dirt		PROJECT MANAGER	39
FOUNDATION	Foundation Form and Excavation		PROJECT MANAGER	Week 40	X			Week Week 40
FOUNDATION	Concrete Piers		PROJECT MANAGER	Week 40	X			Week Week 40
FOUNDATION	Inground Plumbing		PROJECT MANAGER	41
FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar		PROJECT MANAGER	Week 42	X	INSPECTION	INSPECTION	Week Week 42
FOUNDATION	Concrete Pour		PROJECT MANAGER	Week 43	X	we wait 3 weeks after		Week Week 43
GENERAL CONDITIONS	Demo Preparation		PROJECT MANAGER	44		For remodeling
FRAMING	Framing		PROJECT MANAGER	Week 44	X	for remodeling is week 1		Week Week 44
EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)		PROJECT MANAGER	Week 44	X	same week as framing		Week Week 44
DOORS AND WINDOWS	Exterior Windows and Doors		PROJECT MANAGER	Week 44	X	same week as framing		Week Week 44
EXTERIOR SHEATING	External Water Proofing		PROJECT MANAGER	Week 44	X	same week as framing	INSPECTION	Week Week 44
ROOFING	Roofing		PROJECT MANAGER	Week 45	X	next week after framing		Week Week 45
PLUMBING	Plumbing Rough In		PROJECT MANAGER	45		it can be the same week as roofing	INSPECTION
ELECTRICAL	Electrical Rough In		PROJECT MANAGER	Week 45	X		INSPECTION	Week Week 45
MECHANICAL	Mechanic (HVAC) Rough in		PROJECT MANAGER	Week 45	X		INSPECTION	Week Week 45
ELECTRICAL	Communications and Data Rough In		PROJECT MANAGER	45
OTHERS	Things that goes inside the walls		PROJECT MANAGER	45
INSULATION	Wall Insulation		PROJECT MANAGER	Week 45	X		INSPECTION	Week Week 45
INSULATION	Roof Insulation (New Houses		PROJECT MANAGER	Week 45	X		INSPECTION	Week Week 45
DRYWALL	Sheet Rock		PROJECT MANAGER	Week 46	X	one week after the insulaiton inspection		Week Week 46
DRYWALL	Hardybacker Installation		PROJECT MANAGER	Week 46	X	same as sheet rock		Week Week 46
DRYWALL	Wet Areas Water Proofing Redguard		PROJECT MANAGER	Week 46	X	same as sheet rock		Week Week 46
DRYWALL	Tape Bet and Texture		PROJECT MANAGER	Week 46	X	same as sheet rock		Week Week 46
TILES	Tiles		PROJECT MANAGER	Week 47	X	one week after sheetrock		Week Week 47
DOORS AND WINDOWS	Interior Doors Installation		PROJECT MANAGER	47		one week after sheetrock
CARPENTRY	Finish Carpentry		PROJECT MANAGER	47		one week after sheetrock
PAINT	Paint Prep		PROJECT MANAGER	Week 48	X	one week after interior door installation		Week Week 48
PAINT	Painting of Walls		PROJECT MANAGER	Week 48	X	Same week as paint prep		Week Week 48
PAINT	Painting of Ceiling		PROJECT MANAGER	Week 48	X	Same week as paint prep		Week Week 48
FLOORING	Leveling and floating of floors		PROJECT MANAGER	Week 48	X	One week after paiting		Week Week 48
FLOORING	Floor Installation		PROJECT MANAGER	Week 48	X	Same week as floor installation		Week Week 48
FLOORING	Moldures and Baseboard Installation		PROJECT MANAGER	Week 49	X	One wee after floor installation		Week Week 49
PAINT	Trim, baseboards and Mantel Painting		PROJECT MANAGER	Week 50	X	One week after moldures and baseboard installation		Week Week 50
CABINETS	Kitchen Cabinets Installation		PROJECT MANAGER	12		After Floor Installation
CABINETS	Vanities Installation		PROJECT MANAGER	50		After Floor Installation
COUNTERTOP	Countertop Intallation		PROJECT MANAGER	51		After Kitcen and Vanities Installation
OTHERS	Smoke Detectors Installation		PROJECT MANAGER	52		After COuntertops Installation
PLUMBING	Fixture Installation		PROJECT MANAGER	52		After COuntertops Installation
ELECTRICAL	Electrodomestic Installation		PROJECT MANAGER	52		After COuntertops Installation
ELECTRICAL	Accesories Installation		PROJECT MANAGER	Week 52	X	After COuntertops Installation		Week Week 52
OTHERS	Finishes and Touch ups		PROJECT MANAGER	Week 53	X	After all accesories Installed		Week Week 53
OTHERS	DELIVERY		PROJECT MANAGER	Week 54	X	One week after		Week Week 54

## Robert Campbel Final
CATEGORY	Process Name	DEPARTMENT	WEEK	Start	End
GENERAL CONDITIONS	Project Site Preparation and Signs	PROJECT MANAGER	Week 38	September 18, 2023	September 24, 2023
FOUNDATION	Foundation Form and Excavation	PROJECT MANAGER	Week 38	September 18, 2023	September 24, 2023
FOUNDATION	Concrete Piers	PROJECT MANAGER	Week 38	September 18, 2023	September 24, 2023
FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar	PROJECT MANAGER	Week 38	September 18, 2023	September 24, 2023
FOUNDATION	Concrete Pour	PROJECT MANAGER	Week 38	September 18, 2023	September 24, 2023
FRAMING	Framing	PROJECT MANAGER	Week 39	September 25, 2023	October 1, 2023
EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)	PROJECT MANAGER	Week 40	October 2, 2023	October 8, 2023
DOORS AND WINDOWS	Exterior Windows and Doors	PROJECT MANAGER	Week 40	October 2, 2023	October 8, 2023
EXTERIOR SHEATING	External Water Proofing	PROJECT MANAGER	Week 40	October 2, 2023	October 8, 2023
ROOFING	Roofing	PROJECT MANAGER	Week 41	October 9, 2023	October 15, 2023
ELECTRICAL	Electrical Rough In	PROJECT MANAGER	Week 42	October 16, 2023	October 22, 2023
MECHANICAL	Mechanic (HVAC) Rough in	PROJECT MANAGER	Week 42	October 16, 2023	October 22, 2023
INSULATION	Wall Insulation	PROJECT MANAGER	Week 42	October 16, 2023	October 22, 2023
INSULATION	Roof Insulation (New Houses	PROJECT MANAGER	Week 42	October 16, 2023	October 22, 2023
DRYWALL	Sheet Rock	PROJECT MANAGER	Week 42	October 16, 2023	October 22, 2023
DRYWALL	Tape Bet and Texture	PROJECT MANAGER	Week 42	October 16, 2023	October 22, 2023
TILES	Tiles	PROJECT MANAGER	Week 43	October 23, 2023	October 29, 2023
PAINT	Paint Prep	PROJECT MANAGER	Week 43	October 23, 2023	October 29, 2023
PAINT	Painting of Walls	PROJECT MANAGER	Week 43	October 23, 2023	October 29, 2023
PAINT	Painting of Ceiling	PROJECT MANAGER	Week 43	October 23, 2023	October 29, 2023
FLOORING	Leveling and floating of floors	PROJECT MANAGER	Week 44	October 30, 2023	November 5, 2023
FLOORING	Floor Installation	PROJECT MANAGER	Week 44	October 30, 2023	November 5, 2023
FLOORING	Moldures and Baseboard Installation	PROJECT MANAGER	Week 44	October 30, 2023	November 5, 2023
PAINT	Trim, baseboards and Mantel Painting	PROJECT MANAGER	Week 44	October 30, 2023	November 5, 2023
ELECTRICAL	Accesories Installation	PROJECT MANAGER	Week 45	November 6, 2023	November 12, 2023
OTHERS	Finishes and Touch ups	PROJECT MANAGER	Week 45	November 6, 2023	November 12, 2023
OTHERS	DELIVERY	PROJECT MANAGER	Week 45	November 6, 2023	November 12, 2023

## weeks
Week number	From Date	To Date
Week 52, 2022	December 26, 2022	January 1, 2023
Week 01	January 2, 2023	January 8, 2023
Week 02	January 9, 2023	January 15, 2023
Week 03	January 16, 2023	January 22, 2023
Week 04	January 23, 2023	January 29, 2023
Week 05	January 30, 2023	February 5, 2023
Week 06	February 6, 2023	February 12, 2023
Week 07	February 13, 2023	February 19, 2023
Week 08	February 20, 2023	February 26, 2023
Week 09	February 27, 2023	March 5, 2023
Week 10	March 6, 2023	March 12, 2023
Week 11	March 13, 2023	March 19, 2023
Week 12	March 20, 2023	March 26, 2023
Week 13	March 27, 2023	April 2, 2023
Week 14	April 3, 2023	April 9, 2023
Week 15	April 10, 2023	April 16, 2023
Week 16	April 17, 2023	April 23, 2023
Week 17	April 24, 2023	April 30, 2023
Week 18	May 1, 2023	May 7, 2023
Week 19	May 8, 2023	May 14, 2023
Week 20	May 15, 2023	May 21, 2023
Week 21	May 22, 2023	May 28, 2023
Week 22	May 29, 2023	June 4, 2023
Week 23	June 5, 2023	June 11, 2023
Week 24	June 12, 2023	June 18, 2023
Week 25	June 19, 2023	June 25, 2023
Week 26	June 26, 2023	July 2, 2023
Week 27	July 3, 2023	July 9, 2023
Week 28	July 10, 2023	July 16, 2023
Week 29	July 17, 2023	July 23, 2023
Week 30	July 24, 2023	July 30, 2023
Week 31	July 31, 2023	August 6, 2023
Week 32	August 7, 2023	August 13, 2023
Week 33	August 14, 2023	August 20, 2023
Week 34	August 21, 2023	August 27, 2023
Week 35	August 28, 2023	September 3, 2023
Week 36	September 4, 2023	September 10, 2023
Week 37	September 11, 2023	September 17, 2023
Week 38	September 18, 2023	September 24, 2023
Week 39	September 25, 2023	October 1, 2023
Week 40	October 2, 2023	October 8, 2023
Week 41	October 9, 2023	October 15, 2023
Week 42	October 16, 2023	October 22, 2023
Week 43	October 23, 2023	October 29, 2023
Week 44	October 30, 2023	November 5, 2023
Week 45	November 6, 2023	November 12, 2023
Week 46	November 13, 2023	November 19, 2023
Week 47	November 20, 2023	November 26, 2023
Week 48	November 27, 2023	December 3, 2023
Week 49	December 4, 2023	December 10, 2023
Week 50	December 11, 2023	December 17, 2023
Week 51	December 18, 2023	December 24, 2023
Week 52	December 25, 2023	December 31, 2023
Week 01, 2024	January 1, 2024	January 7, 2024

## AMANDA
CATEGORY	Process Name	SubProcess Name	DEPARTMENT	WEEK	COMMENTS	INSPECTION
GENERAL CONDITIONS	Surveyor Documents		PLANING	0
GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work		PLANING	0
GENERAL CONDITIONS	Permits		PLANING	0
GENERAL CONDITIONS	Post Permits		PROJECT MANAGER	1
GENERAL CONDITIONS	Place Dumpsters	x	PROJECT MANAGER	1
GENERAL CONDITIONS	DEMO OF STRUCTURE	x	PROJECT MANAGER	1
SITE WORK	Tree Removal		PROJECT MANAGER	1
SITE WORK	Grading and soil leveling	x	PROJECT MANAGER	1
SITE WORK	n-6		PROJECT MANAGER	1
FOUNDATION	Foundation Form and Excavation	x	PROJECT MANAGER	2
FOUNDATION	Concrete Piers	x	PROJECT MANAGER	2
FOUNDATION	Inground Plumbing	x	PROJECT MANAGER	3
FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar		PROJECT MANAGER	4	INSPECTION	INSPECTION
FOUNDATION	Concrete Pour	x	PROJECT MANAGER	5	we wait 3 weeks after
GENERAL CONDITIONS	Demo Preparation	x	PROJECT MANAGER	6	For remodeling
FRAMING	Framing	x	PROJECT MANAGER	6	for remodeling is week 1
EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)	x	PROJECT MANAGER	6	same week as framing
DOORS AND WINDOWS	Exterior Windows and Doors	x	PROJECT MANAGER	6	same week as framing
EXTERIOR SHEATING	External Water Proofing	x	PROJECT MANAGER	6	same week as framing	INSPECTION
ROOFING	Roofing	x	PROJECT MANAGER	7	next week after framing
PLUMBING	Plumbing Rough In	x	PROJECT MANAGER	7	it can be the same week as roofing	INSPECTION
ELECTRICAL	Electrical Rough In	x	PROJECT MANAGER	7		INSPECTION
MECHANICAL	Mechanic (HVAC) Rough in	x	PROJECT MANAGER	7		INSPECTION
ELECTRICAL	Communications and Data Rough In		PROJECT MANAGER	7
OTHERS	Things that goes inside the walls		PROJECT MANAGER	7
INSULATION	Wall Insulation	x	PROJECT MANAGER	7		INSPECTION
INSULATION	Roof Insulation (New Houses	x	PROJECT MANAGER	7		INSPECTION
DRYWALL	Sheet Rock	x	PROJECT MANAGER	8	one week after the insulaiton inspection
DRYWALL	Hardybacker Installation	x	PROJECT MANAGER	8	same as sheet rock
DRYWALL	Wet Areas Water Proofing Redguard	x	PROJECT MANAGER	8	same as sheet rock
DRYWALL	Tape Bet and Texture	x	PROJECT MANAGER	8	same as sheet rock
TILES	Tiles	x	PROJECT MANAGER	9	one week after sheetrock
DOORS AND WINDOWS	Interior Doors Installation	x	PROJECT MANAGER	9	one week after sheetrock
CARPENTRY	Finish Carpentry	x	PROJECT MANAGER	9	one week after sheetrock
PAINT	Paint Prep	x	PROJECT MANAGER	10	one week after interior door installation
PAINT	Painting of Walls	x	PROJECT MANAGER	10	Same week as paint prep
PAINT	Painting of Ceiling	x	PROJECT MANAGER	10	Same week as paint prep
FLOORING	Leveling and floating of floors	x	PROJECT MANAGER	10	One week after paiting
FLOORING	Floor Installation	x	PROJECT MANAGER	10	Same week as floor installation
FLOORING	Moldures and Baseboard Installation	x	PROJECT MANAGER	11	One wee after floor installation
PAINT	Trim, baseboards and Mantel Painting	x	PROJECT MANAGER	12	One week after moldures and baseboard installation
CABINETS	Kitchen Cabinets Installation	x	PROJECT MANAGER	12	After Floor Installation
CABINETS	Vanities Installation	x	PROJECT MANAGER	12	After Floor Installation
COUNTERTOP	Countertop Intallation	x	PROJECT MANAGER	13	After Kitcen and Vanities Installation
OTHERS	Smoke Detectors Installation	x	PROJECT MANAGER	14	After COuntertops Installation
PLUMBING	Fixture Installation	x	PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Electrodomestic Installation		PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Accesories Installation		PROJECT MANAGER	14	After COuntertops Installation
OTHERS	Finishes and Touch ups	x	PROJECT MANAGER	15	After all accesories Installed
OTHERS	DELIVERY	x	PROJECT MANAGER	16	One week after

## SUBCONTRACTORS
NAME	PHONE NUMBER	TRADES	CERTIFIED?	LANGUAGES
ANTHONY REYES		ELECTRICIAN	YES	ENGLISH ADV
ELISEO		PLUMBER / GAS	NO	ENGLISH ADV
SALVADOR SERRANO		COUNTERTOPS / STONE	N/A	ENGLISH ADV
FRANSICO LEMUS		HVAC	YES	ENGLISH ADV
LUIS DOMINGUEZ		TILE	N/A	ENGLISH ADV
BRYAM PORTILLO		ALL IN	N/A	ENGLISH ADV
HENRY VILCHEZ		CARPENTRY	N/A	SPANISH
JOSE ALFARO ALIAS JOSE ROLANDO		ALL IN	N/A	SPANISH WITH SON
HECTOR		PAINTING
EFRAIN HERNANDEZ		ALL IN	N/A
JAIME		ALL IN	N/A
FERNANDO FERRETIS (FZ CARPENTRY)		FRAMING AND SIDING		ENGLISH ADV
DAVID	469.475.2180	BRICKS		ENGLISH
JUAN LOPEZ (LOPEZ FOUNDATION)		FOUNDATION	YES	ENGLISH
BENITO	214.926.4898			SPANISH
RUBEN	945.209.1150	SHOWER GLASS
GILBERTO	214.475.9351	BRICKS
STRUCTURAL ENGINEER STEVEN	214.991.5117	STRUCTURAL ENGINEER

## NEW
CATEGORY	Process Name	SubProcess Name	DEPARTMENT	WEEK	COMMENTS	INSPECTION
GENERAL CONDITIONS	Surveyor Documents		PLANING	0
GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work		PLANING	0
GENERAL CONDITIONS	Permits		PLANING	0
GENERAL CONDITIONS	Post Permits		PROJECT MANAGER	1
GENERAL CONDITIONS	Place Dumpsters		PROJECT MANAGER	1
GENERAL CONDITIONS	DEMO OF STRUCTURE		PROJECT MANAGER	1
SITE WORK	Tree Removal		PROJECT MANAGER	1
SITE WORK	Grading and soil leveling		PROJECT MANAGER	1
SITE WORK	Filling Dirt		PROJECT MANAGER	1
FOUNDATION	Foundation Form and Excavation		PROJECT MANAGER	2
FOUNDATION	Concrete Piers		PROJECT MANAGER	2
FOUNDATION	Inground Plumbing		PROJECT MANAGER	3
FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar		PROJECT MANAGER	4	INSPECTION	INSPECTION
FOUNDATION	Concrete Pour		PROJECT MANAGER	5	we wait 3 weeks after
GENERAL CONDITIONS	Demo Preparation		PROJECT MANAGER	6	For remodeling
FRAMING	Framing		PROJECT MANAGER	6	for remodeling is week 1
EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)		PROJECT MANAGER	6	same week as framing
DOORS AND WINDOWS	Exterior Windows and Doors		PROJECT MANAGER	6	same week as framing
EXTERIOR SHEATING	External Water Proofing		PROJECT MANAGER	6	same week as framing	INSPECTION
ROOFING	Roofing		PROJECT MANAGER	7	next week after framing
PLUMBING	Plumbing Rough In		PROJECT MANAGER	7	it can be the same week as roofing	INSPECTION
ELECTRICAL	Electrical Rough In		PROJECT MANAGER	7		INSPECTION
MECHANICAL	Mechanic (HVAC) Rough in		PROJECT MANAGER	7		INSPECTION
ELECTRICAL	Communications and Data Rough In		PROJECT MANAGER	7
OTHERS	Things that goes inside the walls		PROJECT MANAGER	7
INSULATION	Wall Insulation		PROJECT MANAGER	7		INSPECTION
INSULATION	Roof Insulation (New Houses		PROJECT MANAGER	7		INSPECTION
DRYWALL	Sheet Rock		PROJECT MANAGER	8	one week after the insulaiton inspection
DRYWALL	Hardybacker Installation		PROJECT MANAGER	8	same as sheet rock
DRYWALL	Wet Areas Water Proofing Redguard		PROJECT MANAGER	8	same as sheet rock
DRYWALL	Tape Bet and Texture		PROJECT MANAGER	8	same as sheet rock
TILES	Tiles		PROJECT MANAGER	9	one week after sheetrock
DOORS AND WINDOWS	Interior Doors Installation		PROJECT MANAGER	9	one week after sheetrock
CARPENTRY	Finish Carpentry		PROJECT MANAGER	9	one week after sheetrock
PAINT	Paint Prep		PROJECT MANAGER	10	one week after interior door installation
PAINT	Painting of Walls		PROJECT MANAGER	10	Same week as paint prep
PAINT	Painting of Ceiling		PROJECT MANAGER	10	Same week as paint prep
FLOORING	Leveling and floating of floors		PROJECT MANAGER	10	One week after paiting
FLOORING	Floor Installation		PROJECT MANAGER	10	Same week as floor installation
FLOORING	Moldures and Baseboard Installation		PROJECT MANAGER	11	One wee after floor installation
PAINT	Trim, baseboards and Mantel Painting		PROJECT MANAGER	12	One week after moldures and baseboard installation
CABINETS	Kitchen Cabinets Installation		PROJECT MANAGER	12	After Floor Installation
CABINETS	Vanities Installation		PROJECT MANAGER	12	After Floor Installation
COUNTERTOP	Countertop Intallation		PROJECT MANAGER	13	After Kitcen and Vanities Installation
OTHERS	Smoke Detectors Installation		PROJECT MANAGER	14	After COuntertops Installation
PLUMBING	Fixture Installation		PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Electrodomestic Installation		PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Accesories Installation		PROJECT MANAGER	14	After COuntertops Installation
OTHERS	Finishes and Touch ups		PROJECT MANAGER	15	After all accesories Installed
OTHERS	DELIVERY		PROJECT MANAGER	16	One week after

## PATT CRUMPTOM
CATEGORY	Process Name	SubProcess Name	DEPARTMENT	WEEK	COMMENTS	INSPECTION
GENERAL CONDITIONS	Surveyor Documents		PLANING	0
GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work		PLANING	0
GENERAL CONDITIONS	Permits		PLANING	0
GENERAL CONDITIONS	Post Permits		PROJECT MANAGER	1
GENERAL CONDITIONS	Place Dumpsters		PROJECT MANAGER	1
GENERAL CONDITIONS	DEMO OF STRUCTURE		PROJECT MANAGER	1
SITE WORK	Tree Removal		PROJECT MANAGER	1
SITE WORK	Grading and soil leveling		PROJECT MANAGER	1
SITE WORK	Filling Dirt		PROJECT MANAGER	1
FOUNDATION	Foundation Form and Excavation		PROJECT MANAGER	2
FOUNDATION	Concrete Piers		PROJECT MANAGER	2
FOUNDATION	Inground Plumbing		PROJECT MANAGER	3
FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar		PROJECT MANAGER	4	INSPECTION	INSPECTION
FOUNDATION	Concrete Pour		PROJECT MANAGER	5	we wait 3 weeks after
GENERAL CONDITIONS	Demo Preparation		PROJECT MANAGER	6	For remodeling
FRAMING	Framing		PROJECT MANAGER	6	for remodeling is week 1
EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)		PROJECT MANAGER	6	same week as framing
DOORS AND WINDOWS	Exterior Windows and Doors		PROJECT MANAGER	6	same week as framing
EXTERIOR SHEATING	External Water Proofing		PROJECT MANAGER	6	same week as framing	INSPECTION
ROOFING	Roofing		PROJECT MANAGER	7	next week after framing
PLUMBING	Plumbing Rough In		PROJECT MANAGER	7	it can be the same week as roofing	INSPECTION
ELECTRICAL	Electrical Rough In		PROJECT MANAGER	7		INSPECTION
MECHANICAL	Mechanic (HVAC) Rough in		PROJECT MANAGER	7		INSPECTION
ELECTRICAL	Communications and Data Rough In		PROJECT MANAGER	7
OTHERS	Things that goes inside the walls		PROJECT MANAGER	7
INSULATION	Wall Insulation		PROJECT MANAGER	7		INSPECTION
INSULATION	Roof Insulation (New Houses		PROJECT MANAGER	7		INSPECTION
DRYWALL	Sheet Rock		PROJECT MANAGER	8	one week after the insulaiton inspection
DRYWALL	Hardybacker Installation		PROJECT MANAGER	8	same as sheet rock
DRYWALL	Wet Areas Water Proofing Redguard		PROJECT MANAGER	8	same as sheet rock
DRYWALL	Tape Bet and Texture		PROJECT MANAGER	8	same as sheet rock
TILES	Tiles		PROJECT MANAGER	9	one week after sheetrock
DOORS AND WINDOWS	Interior Doors Installation		PROJECT MANAGER	9	one week after sheetrock
CARPENTRY	Finish Carpentry		PROJECT MANAGER	9	one week after sheetrock
PAINT	Paint Prep		PROJECT MANAGER	10	one week after interior door installation
PAINT	Painting of Walls		PROJECT MANAGER	10	Same week as paint prep
PAINT	Painting of Ceiling		PROJECT MANAGER	10	Same week as paint prep
FLOORING	Leveling and floating of floors		PROJECT MANAGER	10	One week after paiting
FLOORING	Floor Installation		PROJECT MANAGER	10	Same week as floor installation
FLOORING	Moldures and Baseboard Installation		PROJECT MANAGER	11	One wee after floor installation
PAINT	Trim, baseboards and Mantel Painting		PROJECT MANAGER	12	One week after moldures and baseboard installation
CABINETS	Kitchen Cabinets Installation		PROJECT MANAGER	12	After Floor Installation
CABINETS	Vanities Installation		PROJECT MANAGER	12	After Floor Installation
COUNTERTOP	Countertop Intallation		PROJECT MANAGER	13	After Kitcen and Vanities Installation
OTHERS	Smoke Detectors Installation		PROJECT MANAGER	14	After COuntertops Installation
PLUMBING	Fixture Installation		PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Electrodomestic Installation		PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Accesories Installation		PROJECT MANAGER	14	After COuntertops Installation
OTHERS	Finishes and Touch ups		PROJECT MANAGER	15	After all accesories Installed
OTHERS	DELIVERY		PROJECT MANAGER	16	One week after

## Sheet5
CATEGORY	Process Name	SubProcess Name	DEPARTMENT	WEEK	COMMENTS	INSPECTION
GENERAL CONDITIONS	Surveyor Documents	0	PLANING	0
GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work	X	PLANING	0
GENERAL CONDITIONS	Permits	X	PLANING	0
GENERAL CONDITIONS	Post Permits	X	PROJECT MANAGER	1
GENERAL CONDITIONS			PROJECT MANAGER	1
GENERAL CONDITIONS	DEMO OF STRUCTURE	X	PROJECT MANAGER	1
SITE WORK	Tree Removal	0	PROJECT MANAGER	1
SITE WORK	Grading and soil leveling	0	PROJECT MANAGER	1
SITE WORK	Filling Dirt	0	PROJECT MANAGER	1
FOUNDATION	Foundation Form and Excavation	X	PROJECT MANAGER	2
FOUNDATION	Concrete Piers		PROJECT MANAGER	2
FOUNDATION	Inground Plumbing	X	PROJECT MANAGER	3
FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar	X	PROJECT MANAGER	4	INSPECTION	INSPECTION
FOUNDATION	Concrete Pour	X	PROJECT MANAGER	5	we wait 3 weeks after
GENERAL CONDITIONS	Demo Preparation	X	PROJECT MANAGER	6	For remodeling
FRAMING	Framing Structure	X	PROJECT MANAGER	6	for remodeling is week 1
FRAMING	Framing Outdoors (patio / backyard)	x
EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)	X	PROJECT MANAGER	6	same week as framing
DOORS AND WINDOWS	Exterior Windows and Doors	X	PROJECT MANAGER	6	same week as framing
EXTERIOR SHEATING	External Water Proofing	X	PROJECT MANAGER	6	same week as framing	INSPECTION
ROOFING	Roofing	X	PROJECT MANAGER	7	next week after framing
PLUMBING	Plumbing Rough In	X	PROJECT MANAGER	7	it can be the same week as roofing	INSPECTION
ELECTRICAL	Electrical Rough In	X	PROJECT MANAGER	7		INSPECTION
MECHANICAL	Mechanic (HVAC) Rough in	X	PROJECT MANAGER	7		INSPECTION
ELECTRICAL	Communications and Data Rough In	0	PROJECT MANAGER	7
OTHERS	Things that goes inside the walls		PROJECT MANAGER	7
INSULATION	Wall Insulation	X	PROJECT MANAGER	7		INSPECTION
INSULATION	Roof Insulation (New Houses	X	PROJECT MANAGER	7		INSPECTION
DRYWALL	Sheet Rock	X	PROJECT MANAGER	8	one week after the insulaiton inspection
DRYWALL	Hardybacker Installation	X	PROJECT MANAGER	8	same as sheet rock
DRYWALL	Wet Areas Water Proofing Redguard	X	PROJECT MANAGER	8	same as sheet rock
DRYWALL	Tape Bet and Texture	X	PROJECT MANAGER	8	same as sheet rock
TILES	Tiles	X	PROJECT MANAGER	9	one week after sheetrock
DOORS AND WINDOWS	Interior Doors Installation	X	PROJECT MANAGER	9	one week after sheetrock
CARPENTRY	Finish Carpentry	X	PROJECT MANAGER	9	one week after sheetrock
PAINT	Paint Prep	X	PROJECT MANAGER	10	one week after interior door installation
PAINT	Painting of Walls	X	PROJECT MANAGER	10	Same week as paint prep
PAINT	Painting of Ceiling	X	PROJECT MANAGER	10	Same week as paint prep
FLOORING	Leveling and floating of floors	X	PROJECT MANAGER	10	One week after paiting
FLOORING	Floor Installation	X	PROJECT MANAGER	10	Same week as floor installation
FLOORING	Moldures and Baseboard Installation	X	PROJECT MANAGER	11	One wee after floor installation
PAINT	Trim, baseboards and Mantel Painting	X	PROJECT MANAGER	12	One week after moldures and baseboard installation
CABINETS	Kitchen Cabinets Installation	X	PROJECT MANAGER	12	After Floor Installation
CABINETS	Vanities Installation	X	PROJECT MANAGER	12	After Floor Installation
COUNTERTOP	Countertop Intallation	X	PROJECT MANAGER	13	After Kitcen and Vanities Installation
OTHERS	Smoke Detectors Installation	X	PROJECT MANAGER	14	After COuntertops Installation
PLUMBING	Fixture Installation	X	PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Electrodomestic Installation	X	PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Accesories Installation	X	PROJECT MANAGER	14	After COuntertops Installation
OTHERS	Finishes and Touch ups	X	PROJECT MANAGER	15	After all accesories Installed
OTHERS	DELIVERY	X	PROJECT MANAGER	16	One week after

## Sheet6
CATEGORY	Process Name	SubProcess Name	DEPARTMENT	WEEK	COMMENTS	INSPECTION
GENERAL CONDITIONS	Surveyor Documents	0	PLANING	0
GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work	X	PLANING	0
GENERAL CONDITIONS	Permits	X	PLANING	0
GENERAL CONDITIONS	Post Permits	X	PROJECT MANAGER	1
GENERAL CONDITIONS			PROJECT MANAGER	1
GENERAL CONDITIONS	DEMO OF STRUCTURE	X	PROJECT MANAGER	1
SITE WORK	Tree Removal	0	PROJECT MANAGER	1
SITE WORK	Grading and soil leveling	0	PROJECT MANAGER	1
SITE WORK	Filling Dirt	0	PROJECT MANAGER	1
FOUNDATION	Foundation Form and Excavation	X	PROJECT MANAGER	2
FOUNDATION	Concrete Piers		PROJECT MANAGER	2
FOUNDATION	Inground Plumbing	X	PROJECT MANAGER	3
FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar	X	PROJECT MANAGER	4	INSPECTION	INSPECTION
FOUNDATION	Concrete Pour	X	PROJECT MANAGER	5	we wait 3 weeks after
GENERAL CONDITIONS	Demo Preparation	X	PROJECT MANAGER	6	For remodeling
FRAMING	Framing Structure	X	PROJECT MANAGER	6	for remodeling is week 1
FRAMING	Framing Outdoors (patio / backyard)	x
EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)	X	PROJECT MANAGER	6	same week as framing
DOORS AND WINDOWS	Exterior Windows and Doors	X	PROJECT MANAGER	6	same week as framing
EXTERIOR SHEATING	External Water Proofing	X	PROJECT MANAGER	6	same week as framing	INSPECTION
ROOFING	Roofing	X	PROJECT MANAGER	7	next week after framing
PLUMBING	Plumbing Rough In	X	PROJECT MANAGER	7	it can be the same week as roofing	INSPECTION
ELECTRICAL	Electrical Rough In	X	PROJECT MANAGER	7		INSPECTION
MECHANICAL	Mechanic (HVAC) Rough in	X	PROJECT MANAGER	7		INSPECTION
ELECTRICAL	Communications and Data Rough In	0	PROJECT MANAGER	7
OTHERS	Things that goes inside the walls		PROJECT MANAGER	7
INSULATION	Wall Insulation	X	PROJECT MANAGER	7		INSPECTION
INSULATION	Roof Insulation (New Houses	X	PROJECT MANAGER	7		INSPECTION
DRYWALL	Sheet Rock	X	PROJECT MANAGER	8	one week after the insulaiton inspection
DRYWALL	Hardybacker Installation	X	PROJECT MANAGER	8	same as sheet rock
DRYWALL	Wet Areas Water Proofing Redguard	X	PROJECT MANAGER	8	same as sheet rock
DRYWALL	Tape Bet and Texture	X	PROJECT MANAGER	8	same as sheet rock
TILES	Tiles	X	PROJECT MANAGER	9	one week after sheetrock
DOORS AND WINDOWS	Interior Doors Installation	X	PROJECT MANAGER	9	one week after sheetrock
CARPENTRY	Finish Carpentry	X	PROJECT MANAGER	9	one week after sheetrock
PAINT	Paint Prep	X	PROJECT MANAGER	10	one week after interior door installation
PAINT	Painting of Walls	X	PROJECT MANAGER	10	Same week as paint prep
PAINT	Painting of Ceiling	X	PROJECT MANAGER	10	Same week as paint prep
FLOORING	Leveling and floating of floors	X	PROJECT MANAGER	10	One week after paiting
FLOORING	Floor Installation	X	PROJECT MANAGER	10	Same week as floor installation
FLOORING	Moldures and Baseboard Installation	X	PROJECT MANAGER	11	One wee after floor installation
PAINT	Trim, baseboards and Mantel Painting	X	PROJECT MANAGER	12	One week after moldures and baseboard installation
CABINETS	Kitchen Cabinets Installation	X	PROJECT MANAGER	12	After Floor Installation
CABINETS	Vanities Installation	X	PROJECT MANAGER	12	After Floor Installation
COUNTERTOP	Countertop Intallation	X	PROJECT MANAGER	13	After Kitcen and Vanities Installation
OTHERS	Smoke Detectors Installation	X	PROJECT MANAGER	14	After COuntertops Installation
PLUMBING	Fixture Installation	X	PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Electrodomestic Installation	X	PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Accesories Installation	X	PROJECT MANAGER	14	After COuntertops Installation
OTHERS	Finishes and Touch ups	X	PROJECT MANAGER	15	After all accesories Installed
OTHERS	DELIVERY	X	PROJECT MANAGER	16	One week after

espesor del slab
profundidad
tipo de varilla
tipo de cemento. Camion o de Home Depot

## Sheet4
IF THERE IS DEMO THEN THERE WILL BE DUMPSTER

## ADDITION
CATEGORY	Process Name	SubProcess Name	DEPARTMENT	WEEK	COMMENTS	INSPECTION		START WEEK
GENERAL CONDITIONS	Surveyor Documents		PLANING	0
GENERAL CONDITIONS	Architecture, MEP, RES Check, Structural, Cover Sheet and Scope of work		PLANING	0
GENERAL CONDITIONS	Permits		PLANING	0
GENERAL CONDITIONS	Post Permits		PROJECT MANAGER	1
GENERAL CONDITIONS	Surveyor Property Delimitation		PROJECT MANAGER	1
GENERAL CONDITIONS	DEMO OF STRUCTURE		PROJECT MANAGER	1
SITE WORK	Tree Removal		PROJECT MANAGER	1
SITE WORK	Grading and soil leveling		PROJECT MANAGER	1
SITE WORK	Filling Dirt		PROJECT MANAGER	1
FOUNDATION	Foundation Form and Excavation		PROJECT MANAGER	2
FOUNDATION	Concrete Piers		PROJECT MANAGER	2
FOUNDATION	Inground Plumbing		PROJECT MANAGER	3
FOUNDATION	Trenching and Rebar Post Tension or Vanilla Rebar		PROJECT MANAGER	4	INSPECTION	INSPECTION
FOUNDATION	Concrete Pour		PROJECT MANAGER	5	we wait 3 weeks after
GENERAL CONDITIONS	Demo Preparation		PROJECT MANAGER	6	For remodeling
FRAMING	Framing		PROJECT MANAGER	6	for remodeling is week 1
EXTERIOR SHEATING	Exterior Sheating (Walls and Roof)		PROJECT MANAGER	6	same week as framing
DOORS AND WINDOWS	Exterior Windows and Doors		PROJECT MANAGER	6	same week as framing
EXTERIOR SHEATING	External Water Proofing		PROJECT MANAGER	6	same week as framing	INSPECTION
ROOFING	Roofing		PROJECT MANAGER	7	next week after framing
PLUMBING	Plumbing		PROJECT MANAGER	7	it can be the same week as roofing	INSPECTION
ELECTRICAL	Electrical		PROJECT MANAGER	7	it can be the same week as roofing	INSPECTION
MECHANICAL	Mechanic (HVAC)		PROJECT MANAGER	7	it can be the same week as roofing	INSPECTION
ELECTRICAL	Communications and Data		PROJECT MANAGER	7	it can be the same week as roofing
OTHERS	Things that goes inside the walls		PROJECT MANAGER	7	it can be the same week as roofing
INSULATION	Wall Insulation		PROJECT MANAGER	7	it can be the same week as roofing	INSPECTION
INSULATION	Roof Insulation (New Houses		PROJECT MANAGER	7	it can be the same week as roofing	INSPECTION
DRYWALL	Sheet Rock		PROJECT MANAGER	8	one week after the insulaiton inspection
DRYWALL	Hardybacker Installation		PROJECT MANAGER	8	same as sheet rock
DRYWALL	Wet Areas Water Proofing Redguard		PROJECT MANAGER	8	same as sheet rock
DRYWALL	Tape Bet and Texture		PROJECT MANAGER	8	same as sheet rock
TILES	Tiles		PROJECT MANAGER	9	one week after sheetrock
DOORS AND WINDOWS	Interior Doors Installation		PROJECT MANAGER	9	one week after sheetrock
CARPENTRY	Finish Carpentry		PROJECT MANAGER	9	one week after sheetrock
PAINT	Paint Prep		PROJECT MANAGER	10	one week after sheetrock
PAINT	Painting of Walls		PROJECT MANAGER	10	Same week as paint prep
PAINT	Painting of Ceiling		PROJECT MANAGER	10	Same week as paint prep
FLOORING	Leveling and floating of floors		PROJECT MANAGER	10	One week after paiting
FLOORING	Floor Installation		PROJECT MANAGER	10	Same week as floor installation
FLOORING	Moldures and Baseboard Installation		PROJECT MANAGER	11	One wee after floor installation
PAINT	Trim, baseboards and Mantel Painting		PROJECT MANAGER	12	One week after moldures and baseboard installation
CABINETS	Kitchen Cabinets Installation		PROJECT MANAGER	12	After Floor Installation
CABINETS	Vanities Installation		PROJECT MANAGER	12	After Floor Installation
COUNTERTOP	Countertop Intallation		PROJECT MANAGER	13	After Kitchen and Vanities Installation
OTHERS	Smoke Detectors Installation		PROJECT MANAGER	14	After COuntertops Installation
PLUMBING	Fixture Installation		PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Electrodomestic Installation		PROJECT MANAGER	14	After COuntertops Installation
ELECTRICAL	Accesories Installation		PROJECT MANAGER	14	After COuntertops Installation
OTHERS	Finishes and Touch ups		PROJECT MANAGER	15	After all accesories Installed
OTHERS	DELIVERY		PROJECT MANAGER	16	One week after

			Week Start	1
1-00 GENERAL CONDITIONS TOTAL	1
2.00 SITE WORK TOTALS	1
3.00 FOUNDATION TOTAL	2
4.00 ELECTRICAL	4
5.00 PLUMBING	4
6.0 FRAMING	3
7.0 EXTERIOR SHEATING	3
8.0 ROOFING	4
9.0 DOORS AND WINDOWS	3
10.0 PAINT	5
11.0 INSULATION	4
12.0 FLOORING	6
13.0 STUCCO / SIDING	3
14.0 HVAC	4
15.0 TILES	5
17.0 GLASS	7
18.0 CABINETS	7
19.0 COUNTERTOPS	8
20.0 DRYWALL	4